## Sheet1
Data Taking Sequence - Tower A
Date: 3/14/05 Mon
Author: Gary Godfrey, Larry Wai, Eduardo, Lester
References: | LAT-TD-03489-02 Ad Hoc Committee on End to End Testing
LAT-MD-00575-01 SVAC LAT Plan for LAT Integration at SLAC
and verbal Eduardo SVAC revisions
LAT-TD-04136-01 VG and CR Data Runs for LAT Integration
Notes: | 1) New runs automatically start when the file size reaches 100 Mbytes.
Before=
|  |  |  | Total Hrs Single BayTowerA= | 86 | 54
Physical setups | Script (Python) .py | Suite (XML file) | ID | Schema | Run Time [Hrs] | Eduar Short [Hrs]
Tow Vert | calCalibSimple |  |  |  | 1 | 1
| calCalib |  | C-1 | SingleBay/TowerA | 1.5 | 1.5
|  |  | C-2 | SingleBay/TowerA | 1.5 | 1.5
|  |  | C-3 | SingleBay/TowerA | 1.5 | 1.5
|  |  | C-4 | SingleBay/TowerA | 1.5 | 1.5
Charge Injections | TkrThresholCal |  | TE 601 | SingleBay/TowerA | 1 | 1
| TkrTotGain |  | TE 602 | SingleBay/TowerA | 1 | 1
| TkrThrDispersion |  | TE 604 | SingleBay/TowerA | 1 | 1
| TkrDeadTime |  | TE 703 | SingleBay/TowerA | 1 | 1
| TkrReadOutNoise |  | TE 704 | SingleBay/TowerA | 1 | 1
Charge Injections | calibDAC |  |  | SingleBay/TowerA | 2 | 2
Charge Injections | calibGen |  |  | SingleBay/TowerA | 2 | 2
Tow Vert | intSuite | CosmicsBaseline | 1-1 | SingleBay/TowerA | 1 | 2
|  |  | 7-1 | SingleBay/TowerA | 1 | 1
|  |  | 8-1 | SingleBay/TowerA | 1
Tow Vert | intSuite | CosmicTracker | 2-3 | SingleBay/TowerA | 1 | 1
|  |  | 2-4 | SingleBay/TowerA | 1
|  |  | 2-5 | SingleBay/TowerA | 1
|  |  | 2-6 | SingleBay/TowerA | 1 | 1
|  |  | 2-7 | SingleBay/TowerA | 1 | 1
Tow Vert | intSuite | CosmicCal | 2-10 | SingleBay/TowerA | 1
|  |  | 2-11 | SingleBay/TowerA | 1
Tow Vert | intSuite | CosmicBCRTS | 3-1 | SingleBay/TowerA | 1 | 1
|  |  | 3-2 | SingleBay/TowerA | 1 | 1
|  |  | 3-3 | SingleBay/TowerA | 1
Tow Vert + 27 volts | intSuite | Cosmic2-1 | 2-1 | SingleBay/TowerA | 1
Tow Vert + 29 volts | intSuite | Cosmic2-2 | 2-2 | SingleBay/TowerA | 1
Tow Vert + Pulser 1 KHz | intSuite | Pulser1KHz | 4-1 | SingleBay/TowerA | 1 | 1
|  |  | 8-2 | SingleBay/TowerA | 1
|  |  | 8-6 | SingleBay/TowerA | 1 | 1
Tow Vert + Pulser 5 KHz | intSuite | Pulser5KHz | 4-2 | SingleBay/TowerA | 1 | 1
|  |  | 8-3 | SingleBay/TowerA | 1
|  |  | 8-7 | SingleBay/TowerA | 1
Tow Vert + Pulser 10 KHz | intSuite | Pulser10KHz | 4-3 | SingleBay/TowerA | 1 | 1
|  |  | 8-4 | SingleBay/TowerA | 1
|  |  | 8-8 | SingleBay/TowerA | 1 | 1
Tow Vert+Pulser10 KHz+27v | intSuite | Pulser5-1 | 5-1 | SingleBay/TowerA | 1
Tow Vert+Pulser10 KHz+29v | intSuite | Pulser5-2 | 5-2 | SingleBay/TowerA | 1
Tow Vert+Pulser10 KHz | intSuite | PulserTracker | 5-3 | SingleBay/TowerA | 1 | 1
|  |  | 5-4 | SingleBay/TowerA | 1
|  |  | 5-5 | SingleBay/TowerA | 1
|  |  | 5-6 | SingleBay/TowerA | 1 | 1
|  |  | 5-7 | SingleBay/TowerA | 1 | 1
Tow Vert + Pulser 10 KHz | intSuite | PulserCal | 5-10 | SingleBay/TowerA | 1
|  |  | 5-11 | SingleBay/TowerA | 1
Tow Vert + Pulser 20 KHz | intSuite | Pulser20KHz | 4-4 | SingleBay/TowerA | 1 | 1
|  |  | 8-5 | SingleBay/TowerA | 1
|  |  | 8-9 | SingleBay/TowerA | 1
Tow Vert + Source 4 KHz | intSuite | Amer4-5 | 4-5 | SingleBay/TowerA | 1 | 1
Tow Vert+Source+Pulser1KHz | intSuite | Amer4-6 | 4-6 | SingleBay/TowerA | 1 | 1
Tow Vert+Pulser1KHz | intSuite | Amer4-7 | 4-7 | SingleBay/TowerA | 1 | 1
Tow Horiz + VG 1" | intSuite | vdg9-1_9-2 | 9-1 | SingleBay/TowerA | 1 | 1
|  |  | 9-2 | SingleBay/TowerA | 1 | 1
TowHoriz+VG OFF+BeforeB-16 | intSuite | vdgB-11 | B-11 | SingleBay/TowerA | 1 | 1
Tow Horiz + VG 1" | intSuite | vdgB-16 | B-16 | SingleBay/TowerA | 8 | 4
Tow Horiz+VG 1"+Pulser1KHz | intSuite | vdg9-5 | 9-5 | SingleBay/TowerA | 1 | 1
Tow Horiz+VG 1"+Pulser10KHz | intSuite | vdg9-6 | 9-6 | SingleBay/TowerA | 1 | 1
Tow Horiz + VG 2" | intSuite | vdg9-3 | 9-3 | SingleBay/TowerA | 1 | 1
Tow Horiz + VG 4" | intSuite | vdg9-4 | 9-4 | SingleBay/TowerA | 1 | 1
Tow Horiz+tilt from zen+VG 1" | intSuite | vdg9-7 | 9-7 | SingleBay/TowerA | 1 | 1
Tow Horiz+tilt from zen+VG 1" | intSuite | vdg9-8 | 9-8 | SingleBay/TowerA | 1 | 1
After Cal discs calibrated
Tow Vert | intSuite | calCosmicBaseline | 1-2 | SingleBay/TowerA | 1
|  |  | 2-8 | SingleBay/TowerA | 1
|  |  | 2-9 | SingleBay/TowerA | 1
Tow Vert + Pulser 10 KHz | intSuite | calCosmicPulser | 5-8 | SingleBay/TowerA | 1
|  |  | 5-9 | SingleBay/TowerA | 1
Tow Vert + Mu Telescope | intSuite | calCosmicB-7 | B-7 | SingleBay/TowerA | 4
Tow Vert + Mu Telescope | intSuite | calCosmicSVAC | B-1 | SingleBay/TowerA | 2 | 2
|  |  | B-9 | SingleBay/TowerA | 2 | 2
|  |  | B-12 | SingleBay/TowerA | 1 | 1
|  |  |  | Total hours Grid Tower A= | 35 | 35
Tower A in Grid
Tow Vert | calCalibSimple |  |  |  | 1 | 1
| calCalib |  | C-1 | SingleBay/TowerA | 1.5 | 1.5
|  |  | C-2 | SingleBay/TowerA | 1.5 | 1.5
|  |  | C-3 | SingleBay/TowerA | 1.5 | 1.5
|  |  | C-4 | SingleBay/TowerA | 1.5 | 1.5
| TkrThresholCal |  | TE 601 | Grid/TowerA | 1 | 1
| TkrTotGain |  | TE 602 | Grid/TowerA | 1 | 1
| TkrThrDispersion |  | TE 604 | Grid/TowerA | 1 | 1
| calibDAC |  |  | Grid/TowerA | 2 | 2
| calibGen |  |  | Grid/TowerA | 2 | 2
| muTrig |  |  | Grid/TowerA | 1 | 1
Grid Vert | intSuite | SVACB-2 | B-2 | Grid/TowerA | 4 | 4
|  | SVACB-13 | B-13 | Grid/TowerA | 1 | 1
Grid Vert | intSuite | SVACB-10 | B-10 | Grid/TowerA | 15 | 15