## 1. Intro and Overivew
LAT Tracker Parts Status |  | Status Date: | 2004-09-30
|  | Print Date: | 2004-09-30 16:04
2. Mechanical Parts Bill of Material Trees
Tower Assembly
Flex Cables
TKR-Grid Interface Hardware
Tower Top Mount and Align Hardware
Trays Assemblies
Bottom Tray Assembly
Top Tray Assembly
Mid-Tray Regular Converter Assembly
Mid-Tray No Converter Assembly
Mid-Tray Heavy Converter Assembly
3. EEE Assemblies Bill of Material Trees
Flex Cable Details
Ladder Assembly
Bias Circuit Assembly
TMCM Assemblies
4. Mechanical Ground Support Equipment
TKR Ground Configuration Assembly
Shipping Configuration Assembly
Thermal-Vac Configuration Assembly
Lifting Configuration Assembly
4. Parts List
Change Log
2004-09-30 | >Mech Parts flight hardware changes: DS-00722 Top Assy released; DS-01273 and DS-01274 Y Sidewalls Assy's revised; DS-03968 Top Tray Aux Assy released
>Updated status on MGSE Parts. All assembly and configuration assembly drawings have been released except the Turn-Over and Thermal-Vacuum Configuration Assemblies.
>Mid Tray flight hardware drawings are still in work. Release status shown is for earlier revision which are incomplete but still being used for tray construction.
>Cleaned out obsolete parts and obsoleted any drawing numbers not used
2004-09-07 | >Checked drawing trees for all Mech Parts against final parts lists on assembly drawings
>Checked and updated drawing trees for MGSE against final parts lists on assembly and configuration assembly drawings
2004-07-23 | >General update to drawing release status after last of flight hardware drawings were released
>Re-worked 'MGSE Parts List' to include TKR+Base Plate Assy and TKR Ground Config Assy, which consolidate most of the drawing trees for the Configuration Assemblies.
>Update status of MGSE. Many parts have been released.
>Updated parts list for LAT-DS-00722 Tower Module Assy to agree with latest draft
2004-06-30 | >Updated MGSE sheet with final parts lists for shipping container and cable holding plate. >Added first pass at TKR Tower Assembly parts list, but this still needs completion
2004-06-24 | >Split off MGSE into 'Mech GSE Parts Tree' sheet, and re-numbered 'Parts List' to as sheet 5.
>Completed and validated parts list for Top and Bottom Tray assemblies with payload.
2004-06-22 | >Re-worked Mid Tray trees to include all bill of material information, including changing Aeroglaze primers to 9924 from 9929.
>Added detail to MGSE list to include known drawings. Still missing most hardware
>Changed parts status as needed
2004-06-15 | >Added MGSE drawing status to Mech Parts Tree. Still need some more updating of MGSE bills of materials. Added other miscellaneous updates.
2004-06-08 | >Miscellaneous updates to parts status.
2004-06-01 | >Mech: updated release status; all Flex Cable dwg's released and Auth for Prod; cleaned up Interface Hardware section and added Eccentric Cone assembly drawing; added section and drawings for top tray Corner Mount Brackets (all dwg's offline right now)
>Elec: all Flex Cable dwg's, including Gerber files and schematics, released and Auth for Prod.
2004-05-25 | >Mech: updated drawing status; changed production status of all mid-tray assemblies to "Hold," until drawings are complete
>Elec: C-1 Flex Cable gerber file was DS00335, is 00342; added DS-00130 TMCM Schematic
>Deleted obsolete 'TMCM' sheet. All TMCM parts information shows up on the 'EEE Assy Trees' sheet
2004-05-20 | >Started tracking and summarizing changes
>Added hyperlinks to major assemblies. Consolidated status date to automate updates
>All Flex Cable drawings and Gerber files went into release cycle. Top and Bottom Tray insert drawings released and Top Tray MCM Closeout released. Now all Top and Bottom Tray parts are Auth. For Prod. Except grounding lug and assembly bolts on Bottom Tray.
2004-09-30 | = Latest update shown above, for use in setting status date

## 2. Mechanical Parts Tree
|  | 2. Tracker Mechanical Assemblies and Parts Disposition | [7 empty] | Updated: | 2004-09-30 | Printed: | 2004-09-30 16:04
[10 empty] | Document Status from LAT Docs | [5 empty] | H'Ware Need Dates |  |  |  |  | H'Ware Order Status |  |  |  | Shipping Status |  |  | Disposition
# | Lvl | Next Assy | BOM # | Doc / Part # | Dwg Link | Type | Title / Description | Rev | Status | Release Date | Work Authorization | Status Date | Disposition/Comments/Date | Flt Dsn | Status Date | at SLAC | at INFN | Supplied by | Status Date | SLAC P.O. # | Quantity Ordered | Qty Needed | Spares | Rec'd at SLAC | Ship Date | Shipper # | Rec'd at INFN | Work Order # | NCR (if any)
1 |  |  |  | 1 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
2 | Tower Assembly | bar: 2 to 25
3 | 1 | LAT-DS-01627 |  | LAT-DS-00722 | Dwg | SA | Tracker Module Assembly | 2 | Signed-Off | 2004-09-29 | Auth for Flight Prod | 2004-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 2 | LAT-DS-00722 | 1 | LAT-DS-00764 | Dwg | SA | Top Tray Assy with Payload | 4 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 2 | LAT-DS-00722 | 2 | LAT-DS-00180 | Dwg | SA | Mid Tray Reg Convert Ass'y w/Payload | 4 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 2 | LAT-DS-00722 | 3 | LAT-DS-00747 | Dwg | SA | Mid Tray Hvy Convert Ass'y w/Payload | 3 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 2 | LAT-DS-00722 | 4 | LAT-DS-00181 | Dwg | SA | Mid Tray No Convert Ass'y w/Payload | 4 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 2 | LAT-DS-00722 | 5 | LAT-DS-00051 | Dwg | SA | Bottom Tray Assembly w/ Payload | 2 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 2 | LAT-DS-00722 | 6 | LAT-DS-01271 | Dwg | SA | Sidewall +X Assembly | 3 | Signed-Off | 2004-05-11 | Auth for Flight Prod | 2004-09-30 | 0 | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 2 | LAT-DS-00722 | 7 | LAT-DS-01272 | Dwg | SA | Sidewall -X Assembly | 3 | Signed-Off | 2004-05-11 | Auth for Flight Prod | 2004-09-30 | 0 | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 2 | LAT-DS-00722 | 8 | LAT-DS-01273 | Dwg | SA | Sidewall +Y Assembly | 3 | Signed-Off | 2004-09-15 | Auth for Flight Prod | 2004-09-30 | Updated to include paint masking | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 2 | LAT-DS-00722 | 9 | LAT-DS-01274 | Dwg | SA | Sidewall -Y Assembly | 4 | Signed-Off | 2004-09-15 | Auth for Flight Prod | 2004-09-30 | Updated to include paint masking | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 2 | LAT-DS-00722 | 10 | LAT-DS-03183 | Dwg | SA | C-0 Bent Assembly | 2 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 2 | LAT-DS-00722 | 11 | LAT-DS-03184 | Dwg | SA | C-1 Bent Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 2 | LAT-DS-00722 | 12 | LAT-DS-03185 | Dwg | SA | C-2 Bent Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 2 | LAT-DS-00722 | 13 | LAT-DS-03186 | Dwg | SA | C-3 Bent Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 2 | LAT-DS-00722 | 14 | LAT-DS-03187 | Dwg | SA | C-4 Bent Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 2 | LAT-DS-00722 | 15 | LAT-DS-03188 | Dwg | SA | C-5 Bent Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 2 | LAT-DS-00722 | 16 | LAT-DS-03189 | Dwg | SA | C-6 Bent Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 2 | LAT-DS-00722 | 17 | LAT-DS-03190 | Dwg | SA | C-7 Bent Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 2 | LAT-DS-00722 | 18 | LAT-DS-01804 | Dwg | SA | Heat Strap Assembly | 3 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-23 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 2 | LAT-DS-00722 | 19 | LAT-DS-02090 | Dwg | PF | Heat Strap Tie Down Strap | 3 | Signed-Off | 2004-07-26 | Auth for Flight Prod | 2004-09-07 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 2 | LAT-DS-00722 | 20 | LAT-DS-03998 | Dwg | PF | Cable Retaining Clip | 1 | Signed-Off | 2004-07-21 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 2 | LAT-DS-00722 | 21 | LAT-DS-03962 | Dwg | PF | Left-Hand Corner Mount Bracket | 1 | Signed-Off | 2004-07-21 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 2 | LAT-DS-00722 | 22 | LAT-DS-03961 | Dwg | PF | Double Corner Mount Bracket | 1 | Signed-Off | 2004-07-21 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 2 | LAT-DS-00722 | 23 | LAT-DS-03963 | Dwg | PF | Right-Hand Corner Mount Bracket | 1 | Signed-Off | 2004-07-21 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 2 | LAT-DS-00722 | 24 | LAT-DS-03964 | Dwg | PF | Single Corner Mount Bracket | 1 | Signed-Off | 2004-07-21 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 2 | LAT-DS-00722 | 25 | LAT-DS-02789 | Dwg | PF | Hex Bushing | 3 | Signed-Off | 2004-06-02 | Auth for Flight Prod | 2004-06-15 | Dwg released; OK to fab | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 2 | LAT-DS-00722 | 26 | LAT-DS-03925 | Dwg | PT | M5 x 0.8 Hex Nut | 1 | Signed-Off | 2004-06-02 | Auth for Flight Prod | 2004-06-15 | Dwg released; OK to fab | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 2 | LAT-DS-00722 | 27 | LAT-DS-04201 | Dwg | PF | M2.5 x 8 lg 100 deg Flat Hd Cap Scr | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 2 | LAT-DS-00722 | 28 | LAT-DS-04202 | Dwg | PF | M2.5 x 8 lg 120 deg Flat Hd Cap Scr | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 2 | LAT-DS-00722 | 29 | LAT-DS-04199 | Dwg | PF | M4 x 8 lg 100 deg Flat Hd Cap Scr | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 2 | LAT-DS-00722 | 30 | LAT-DS-04200 | Dwg | PF | M4 x 6 lg 100 deg Flat Hd Cap Scr | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 2 | LAT-DS-00722 | 31 | LAT-DS-02787 | Dwg | PF | Inner Eccentric Cone | 3 | Signed-Off | 2004-06-02 | Auth for Flight Prod | 2004-06-15 | Dwg released; OK to fab | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 2 | LAT-DS-00722 | 32 | LAT-DS-02788 | Dwg | PF | Outer Eccentric Cone | 4 | Signed-Off | 2004-06-02 | Auth for Flight Prod | 2004-06-15 | Dwg released; OK to fab | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 2 | LAT-DS-00722 | 33 | LAT-DS-02791 | Dwg | PF | Shoulder Stud | 5 | Signed-Off | 2004-07-21 | Auth for Flight Prod | 2004-07-22 | Mods incorporated to improve Nylok fit | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 2 | LAT-DS-00722 | 34 | LAT-DS-03506 | Dwg | PF | Installation Shims | 2 | Signed-Off | 2004-06-02 | Auth for Flight Prod | 2004-06-15 | Dwg released; OK to fab | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 2 | LAT-DS-00722 | 35 | DIN 912-A4 M4x8 | Dwg | MP | M4x0.7x8 LG SHCS, 316 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 2 | LAT-DS-00722 | 36 | NAS 1352-N04LB-6 | Dwg | PP | 4-40 UNC x 3/8 IN SHCS, A286 St Steel, Self-Locking | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 2004-09-07 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 2 | LAT-DS-00722 | 37 | ISO 7380-A2 M2 | Dwg | MP | M2x0.4x6 LG But Hd CS, 316 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 2 | LAT-DS-00722 | 38 | ISO 7380-A2 M2.5 | Dwg | MP | M2.5x0.45x2.5 LG But Hd CS, 316 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 2 | LAT-DS-00722 | 39 | Hysol EA-934NA | Dwg | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 2 | LAT-DS-00722 | 40 | Solithane 113/300 | Dwg | MT | Thread Lock | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 2 | LAT-DS-00722 | 41 | DIN 125 M2.5 | Dwg | PP | M2.5 Flat Washer x 6OD, 316 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 2 | LAT-DS-00722 | 42 | 3M 70-0060-4256-1 | Dwg | MT | Adhesive Transfer Tape 966 Clear, 1" W x 0.002" Thk | 0 | GSFC Pending | 0 | OK to Procure Mat'l | 2004-09-07 | 0 | 0 | 0 | 0 | 0 | INFN/Plyform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46
47 | Sidewall Assemblies | bar: 2 to 25
48 | 2 | LAT-DS-00722 |  | LAT-DS-01272 | Dwg | SA | Sidewall -X Assembly | 3 | Signed-Off | 2004-05-11 | Auth for Flight Prod | 2004-09-30 | 0 | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 3 | LAT-DS-01272 | 1 | LAT-DS-00303 | Dwg | PF | Sidewall -X Fabrication | 6 | Signed-Off | 2004-07-20 | Auth for Flight Prod | 2004-09-30 | 0 | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 3 | LAT-DS-01272 | 2 | LAT-DS-02203 | Dwg | PF | Sidewall Washer 4mm | 2 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-05-07 | 0 | Yes | 0 | 0 | 0 | SLAC | 2004-03-31 | 45155 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 3 | LAT-DS-01272 | 3 | LAT-DS-00909 | Dwg | PF | Sidewall Washer 2.5mm | 2 | Signed-Off | 2004-05-04 | Auth for Flight Prod | 2004-05-07 | 0 | Yes | 0 | 0 | 0 | SLAC | 2004-03-31 | 45155 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 3 | LAT-DS-01272 | 4 | Hysol EA-934NA |  | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 3 | LAT-DS-01272 | 5 | MIL-G-9954 |  | MT | Glass Beads .005"-.007" | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 3 | LAT-DS-01272 | 6 | AEROGLAZE Z306 |  | MT | Black Polyurethane Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 8 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
55 | 3 | LAT-DS-01272 | 7 | AEROGLAZE 9924 |  | MT | Primer for Z 306 Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 8 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
56 | 3 | LAT-DS-01272 | 8 | Hysol M-9-N |  | MT | Epoxy Ink White | 0 | GSFC Pending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 3 | LAT-DS-01272 | 9 | Cytec BR-127 |  | MT | Corrosion Inhibiting Primer | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 2004-05-04 | INFN to check if they have this material | 0 | 0 | 0 | 0 | SLAC | 2004-04-22 | Credit Card | 1 Gallon | ? | ? | Drop Ship | 2004-10-13 | N/A | ? | 0 | 0
58 | 2 | LAT-DS-00722 |  | LAT-DS-01271 | Dwg | SA | Sidewall +X Assembly | 3 | Signed-Off | 2004-05-11 | Auth for Flight Prod | 2004-09-30 | 0 | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | 3 | LAT-DS-01271 | 1 | LAT-DS-00304 | Dwg | PF | Sidewall +X Fabrication | 6 | Signed-Off | 2004-07-20 | Auth for Flight Prod | 2004-09-30 | 0 | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 3 | LAT-DS-01271 | 2 | LAT-DS-02203 | Dwg | PF | Sidewall Washer 4mm | 2 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-05-07 | 0 | Yes | 0 | 0 | 0 | SLAC | 2004-03-31 | 45155 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 3 | LAT-DS-01271 | 3 | LAT-DS-00909 | Dwg | PF | Sidewall Washer 2.5mm | 2 | Signed-Off | 2004-05-04 | Auth for Flight Prod | 2004-05-07 | 0 | Yes | 0 | 0 | 0 | SLAC | 2004-03-31 | 45155 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 3 | LAT-DS-01271 | 4 | Hysol EA-934NA |  | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 3 | LAT-DS-01271 | 5 | MIL-G-9954 |  | MT | Glass Beads .005"-.007" | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 3 | LAT-DS-01271 | 6 | AEROGLAZE Z306 |  | MT | Black Polyurethane Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 8 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
65 | 3 | LAT-DS-01271 | 7 | AEROGLAZE 9924 |  | MT | Primer for Z 306 Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 8 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
66 | 3 | LAT-DS-01271 | 8 | Hysol M-9-N |  | MT | Epoxy Ink White | 0 | GSFC Pending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | 3 | LAT-DS-01271 | 9 | Cytec BR-127 |  | MT | Corrosion Inhibiting Primer | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 2004-05-04 | INFN to check if they have this material | 0 | 0 | 0 | 0 | SLAC | 2004-04-22 | Credit Card | 1 Gallon | ? | ? | Drop Ship | 2004-10-13 | N/A | ? | 0 | 0
68 | 2 | LAT-DS-00722 |  | LAT-DS-01274 | Dwg | SA | Sidewall -Y Assembly | 4 | Signed-Off | 2004-09-15 | Auth for Flight Prod | 2004-09-30 | Updated to include paint masking | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | 3 | LAT-DS-01274 | 1 | LAT-DS-00305 | Dwg | PF | Sidewall -Y Fabrication | 6 | Signed-Off | 2004-07-20 | Auth for Flight Prod | 2004-09-30 | 0 | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | 3 | LAT-DS-01274 | 2 | LAT-DS-02203 | Dwg | PF | Sidewall Washer 4mm | 2 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-05-07 | 0 | Yes | 0 | 0 | 0 | SLAC | 2004-03-31 | 45155 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | 3 | LAT-DS-01274 | 3 | LAT-DS-00909 | Dwg | PF | Sidewall Washer 2.5mm | 2 | Signed-Off | 2004-05-04 | Auth for Flight Prod | 2004-05-07 | 0 | Yes | 0 | 0 | 0 | SLAC | 2004-03-31 | 45155 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 3 | LAT-DS-01274 | 4 | Hysol EA-934NA |  | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | 3 | LAT-DS-01274 | 5 | MIL-G-9954 |  | MT | Glass Beads .005"-.007" | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 | 3 | LAT-DS-01274 | 6 | AEROGLAZE Z306 |  | MT | Black Polyurethane Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 8 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
75 | 3 | LAT-DS-01274 | 7 | AEROGLAZE 9924 |  | MT | Primer for Z 306 Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 8 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
76 | 3 | LAT-DS-01274 | 8 | Hysol M-9-N |  | MT | Epoxy Ink White | 0 | GSFC Pending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | 3 | LAT-DS-01274 | 9 | Cytec BR-127 |  | MT | Corrosion Inhibiting Primer | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 2004-05-04 | INFN to check if they have this material | 0 | 0 | 0 | 0 | SLAC | 2004-04-22 | Credit Card | 1 Gallon | ? | ? | Drop Ship | 2004-10-13 | N/A | ? | 0 | 0
78 | 2 | LAT-DS-00722 |  | LAT-DS-01273 | Dwg | SA | Sidewall +Y Assembly | 3 | Signed-Off | 2004-09-15 | Auth for Flight Prod | 2004-09-30 | Updated to include paint masking | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | 3 | LAT-DS-01273 | 1 | LAT-DS-00306 | Dwg | PF | Sidewall +Y Fabrication | 6 | Signed-Off | 2004-07-20 | Auth for Flight Prod | 2004-09-30 | 0 | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | 3 | LAT-DS-01273 | 2 | LAT-DS-02203 | Dwg | PF | Sidewall Washer 4mm | 2 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-05-07 | 0 | Yes | 0 | 0 | 0 | SLAC | 2004-03-31 | 45155 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | 3 | LAT-DS-01273 | 3 | LAT-DS-00909 | Dwg | PF | Sidewall Washer 2.5mm | 2 | Signed-Off | 2004-05-04 | Auth for Flight Prod | 2004-05-07 | 0 | Yes | 0 | 0 | 0 | SLAC | 2004-03-31 | 45155 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | 3 | LAT-DS-01273 | 4 | Hysol EA-934NA |  | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | 3 | LAT-DS-01273 | 5 | MIL-G-9954 |  | MT | Glass Beads .005"-.007" | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | 3 | LAT-DS-01273 | 6 | AEROGLAZE Z306 |  | MT | Black Polyurethane Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 8 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
85 | 3 | LAT-DS-01273 | 7 | AEROGLAZE 9924 |  | MT | Primer for Z 306 Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 8 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
86 | 3 | LAT-DS-01273 | 8 | Hysol M-9-N |  | MT | Epoxy Ink White | 0 | GSFC Pending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | 3 | LAT-DS-01273 | 9 | Cytec BR-127 |  | MT | Corrosion Inhibiting Primer | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 2004-05-04 | INFN to check if they have this material | 0 | 0 | 0 | 0 | SLAC | 2004-04-22 | Credit Card | 1 Gallon | ? | ? | Drop Ship | 2004-10-13 | N/A | ? | 0 | 0
88 | Flex Cables | bar: 2 to 25
89 | 2 | LAT-DS-00722 |  | LAT-DS-03183 | Dwg | SA | C-0 Bent Assembly | 2 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | 2 | LAT-DS-00722 |  | LAT-DS-03184 | Dwg | SA | C-1 Bent Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | 2 | LAT-DS-00722 |  | LAT-DS-03185 | Dwg | SA | C-2 Bent Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | 2 | LAT-DS-00722 |  | LAT-DS-03186 | Dwg | SA | C-3 Bent Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | 2 | LAT-DS-00722 |  | LAT-DS-03187 | Dwg | SA | C-4 Bent Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | 2 | LAT-DS-00722 |  | LAT-DS-03188 | Dwg | SA | C-5 Bent Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | 2 | LAT-DS-00722 |  | LAT-DS-03189 | Dwg | SA | C-6 Bent Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | 2 | LAT-DS-00722 |  | LAT-DS-03190 | Dwg | SA | C-7 Bent Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | TKR-Grid Interface Hardware | bar: 2 to 25
98 | 2 | LAT-DS-00722 |  | LAT-DS-02090 | Dwg | PF | Heat Strap Tie Down Strap | 3 | Signed-Off | 2004-07-26 | Auth for Flight Prod | 2004-09-07 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | 2 | LAT-DS-00722 |  | LAT-DS-01804 | Dwg | SA | Heat Strap Assembly | 3 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-23 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | 2 | LAT-DS-01804 | 1 | LAT-DS-03681 | Dwg | PF | Heat Strap Inner | 2 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-23 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | 2 | LAT-DS-01804 | 2 | LAT-DS-03682 | Dwg | PF | Heat Strap Outer | 2 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-23 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | 2 | LAT-DS-01804 | 3 | Loctite 401 | Dwg | MT | Cyanoacrylate Adhesive | 0 | GSFC Pending | 0 | 0 | 2004-06-15 | Not yet approved; planned for heat straps only | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | 2 | LAT-DS-00722 |  | LAT-DS-03505 | Dwg | PF | Interface Parts Auxiliary Ass'y | 2 | Signed-Off | 2004-06-02 | Auth for Flight Prod | 2004-06-15 | Dwg released; OK to fab | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | Tower Top Mount and Align Hardware
105 | 2 | LAT-DS-00722 |  | LAT-DS-03968 | Dwg | SA | Top Tray Auxiliary Assembly | 1 | Signed-Off | 2004-09-29 | Auth for Flight Prod | 2004-09-30 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 | 2 | LAT-DS-00722 |  | LAT-DS-00764 | Dwg | SA | Top Tray Assy with Payload | 4 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 | 2 | LAT-DS-00722 |  | LAT-DS-03961 | Dwg | PF | Double Corner Mount Bracket | 1 | Signed-Off | 2004-07-21 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 | 2 | LAT-DS-00722 |  | LAT-DS-03962 | Dwg | PF | Left-Hand Corner Mount Bracket | 1 | Signed-Off | 2004-07-21 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
109 | 2 | LAT-DS-00722 |  | LAT-DS-03963 | Dwg | PF | Right-Hand Corner Mount Bracket | 1 | Signed-Off | 2004-07-21 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | 2 | LAT-DS-00722 |  | LAT-DS-03964 | Dwg | PF | Single Corner Mount Bracket | 1 | Signed-Off | 2004-07-21 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 | 2 | LAT-DS-00722 |  | LAT-DS-03998 | Dwg | PF | Cable Retaining Clip | 1 | Signed-Off | 2004-07-21 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
112 | Bottom Tray Assembly | bar: 2 to 25
113 | 2 | LAT-DS-00722 |  | LAT-DS-00051 | Dwg | SA | Bottom Tray Assembly w/ Payload | 2 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
114 | 3 | LAT-DS-00051 | 1 | LAT-DS-00050 | Dwg | SA | Bottom Tray Mech. Assy | 2 | Signed-Off | 2004-06-10 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
115 | 4 | LAT-DS-00050 | 1 | LAT-DS-00074 | Dwg | SA | MCM Closeout Wall Assy | 4 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
116 | 5 | LAT-DS-00074 | 1 | LAT-DS-00800 | Dwg | PF | MCM Closeout Wall | 8 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-05-07 | 0 | Yes | 0 | 0 | 0 | SLAC | 2004-03-31 | 43146 | 40 | 36 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
117 | 6 | LAT-DS-00800 | 1 | LAT-DS-02616 | Dwg | PF | MCM Closeout Wall M55J Detail-A | 2 | Signed-Off | 2004-03-29 | Auth for Flight Prod | 0 | 0 | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
118 | 6 | LAT-DS-00800 | 2 | LAT-DS-02617 | Dwg | PF | MCM Closeout Wall M55J Detail-B | 2 | Signed-Off | 2004-03-29 | Auth for Flight Prod | 0 | 0 | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
119 | 6 | LAT-DS-00800 | 3 | Allcomp 3D Carbon-Carbon |  | MT | Tray Closeouts | 0 | GSFC Pending | 0 | OK to Procure Mat'l | 0 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | 6 | LAT-DS-00800 | 4 | Hysol EA 9394 |  | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2004-03-16 | 47130 | 25 ea. 50 ml | N/A | N/A | 2003-06-16 | 0 | 0 | 0 | 0 | 0
121 | 6 | LAT-DS-00800 | 5 | MIL-G-9954 |  | MT | Glass Beads .005"-.007" | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
122 | 5 | LAT-DS-00074 | 2 | LAT-DS-01905 | Dwg | PF | M4 X 8.86 LG Insert | 4 | Signed-Off | 2004-05-20 | Auth for Flight Prod | 2004-05-20 | Dwg approved; OK to fab | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
123 | 5 | LAT-DS-00074 | 3 | LAT-DS-01906 | Dwg | PF | M2.5 X 9.96 LG Insert | 4 | Signed-Off | 2004-05-20 | Auth for Flight Prod | 2004-05-20 | Dwg approved; OK to fab | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
124 | 5 | LAT-DS-00074 | 4 | LAT-DS-01919 | Dwg | PF | 3mm Insert | 5 | Signed-Off | 2004-05-20 | Auth for Flight Prod | 2004-05-20 | Dwg approved; OK to fab | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
125 | 5 | LAT-DS-00074 | 5 | Hysol EA-934NA | Dwg | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
126 | 4 | LAT-DS-00050 | 2 | LAT-DS-00075 | Dwg | SA | Structural Closeout Wall Assy | 4 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
127 | 5 | LAT-DS-00075 | 1 | LAT-DS-00801 | Dwg | PF | Structural Closeout Wall | 8 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-05-07 | 0 | Yes | 0 | 0 | 0 | SLAC | 2004-03-31 | 43146 | 40 | 36 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
128 | 6 | LAT-DS-00801 | 1 | LAT-DS-02609 | Dwg | PF | Struc Closeout Wall M55J Detail -A | 2 | Signed-Off | 2004-03-29 | Auth for Flight Prod | 0 | 0 | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
129 | 6 | LAT-DS-00801 | 2 | LAT-DS-02610 | Dwg | PF | Struc Closeout Wall M55J Detail -B | 3 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-05-07 | 0 | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
130 | 6 | LAT-DS-00801 | 3 | Allcomp 3D Carbon-Carbon |  | MT | Tray Closeouts | 0 | GSFC Pending | 0 | OK to Procure Mat'l | 0 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
131 | 6 | LAT-DS-00801 | 4 | Hysol EA 9394 |  | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2004-03-16 | 47130 | 25 ea. 50 ml | N/A | N/A | 2003-06-16 | 0 | 0 | 0 | 0 | 0
132 | 6 | LAT-DS-00801 | 5 | MIL-G-9954 |  | MT | Glass Beads .005"-.007" | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
133 | 5 | LAT-DS-00801 | 2 | LAT-DS-01905 | Dwg | PF | M4 X 8.86 LG Insert | 4 | Signed-Off | 2004-05-20 | Auth for Flight Prod | 2004-05-20 | Dwg approved; OK to fab | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
134 | 5 | LAT-DS-00801 | 3 | LAT-DS-01906 | Dwg | PF | M2.5 X 9.96 LG Insert | 4 | Signed-Off | 2004-05-20 | Auth for Flight Prod | 2004-05-20 | Dwg approved; OK to fab | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
135 | 5 | LAT-DS-00801 | 4 | LAT-DS-01919 | Dwg | PF | 3mm Insert | 5 | Signed-Off | 2004-05-20 | Auth for Flight Prod | 2004-05-20 | Dwg approved; OK to fab | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
136 | 5 | LAT-DS-00801 | 5 | LAT-DS-02206 | Dwg | PF | M4 X 13.12 LG Insert | 4 | Signed-Off | 2004-05-20 | Auth for Flight Prod | 2004-05-20 | Dwg approved; OK to fab | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
137 | 5 | LAT-DS-00075 | 6 | Hysol EA-934NA |  | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
138 | 4 | LAT-DS-00050 | 3 | LAT-DS-02723 | Dwg | SA | Corner BRKT Flex Assy LH | 4 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-05-07 | 0 | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
139 | 5 | LAT-DS-02723 | 1 | LAT-DS-01803 | Dwg | PF | Corner Bracket LH | 6 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-05-07 | 0 | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
140 | 5 | LAT-DS-02723 | 2 | LAT-DS-00422 | Dwg | PF | 3-Blade Corner Flexure | 7 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-05-07 | 0 | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
141 | 5 | LAT-DS-02723 | 3 | NAS 1352-N06-10 |  | PP | 6-32 UNC x 5/8 IN SHCS, A286 St Steel | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
142 | 5 | LAT-DS-02723 | 4 | LAT-DS-03083 | Dwg | PF | Dowel Pin | 2 | Signed-Off | 2004-03-08 | Auth for Flight Prod | 0 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
143 | 5 | LAT-DS-02723 | 5 | LAT-DS-03041 | Dwg | PF | Pin Retainer | 2 | Signed-Off | 2004-03-08 | Auth for Flight Prod | 0 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 | 5 | LAT-DS-02723 | 6 | Solithane 113/300 |  | MT | Thread Lock | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
145 | 4 | LAT-DS-00050 | 4 | LAT-DS-02922 | Dwg | SA | Corner BRKT Flex Assy. RH | 4 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-05-07 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
146 | 5 | LAT-DS-02922 | 1 | LAT-DS-01921 | Dwg | PF | Corner Bracket RH | 6 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-05-07 | 0 | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
147 | 5 | LAT-DS-02922 | 2 | LAT-DS-00422 | Dwg | PF | 3-Blade Corner Flexure | 7 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-05-07 | 0 | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
148 | 5 | LAT-DS-02922 | 3 | NAS 1352-N06-10 |  | PP | 6-32 UNC x 5/8 IN SHCS, A286 St Steel | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
149 | 5 | LAT-DS-02922 | 4 | LAT-DS-03083 | Dwg | PF | Dowel Pin | 2 | Signed-Off | 2004-03-08 | Auth for Flight Prod | 0 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
150 | 5 | LAT-DS-02922 | 5 | LAT-DS-03041 | Dwg | PF | Pin Retainer | 2 | Signed-Off | 2004-03-08 | Auth for Flight Prod | 0 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
151 | 5 | LAT-DS-02922 | 6 | Solithane 113/300 |  | MT | Thread Lock | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
152 | 4 | LAT-DS-00050 | 5 | LAT-DS-03504 |  | PF | Bottom Tray Honeycomb Core | 1 | Signed-Off | 2004-04-07 | Auth for Flight Prod | 2004-05-04 | 0 | Yes | 0 | 0 | 0 | SLAC | [8 empty] | ? | 0 | 0
153 | 4 | LAT-DS-00050 | 6 | LAT-DS-01903 | Dwg | PF | Bottom Tray Face Sheet Top | 2 | Signed-Off | 2004-05-10 | Auth for Flight Prod | 2004-05-18 | OK for fab; coupons from Plyform to B. Rodini | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
154 | 4 | LAT-DS-00050 | 7 | LAT-DS-01904 | Dwg | PF | Bottom Tray Face Sheet Bottom | 2 | Signed-Off | 2004-05-10 | Auth for Flight Prod | 2004-05-18 | OK for fab; coupons from Plyform to B. Rodini | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
155 | 4 | LAT-DS-00050 | 8 | LAT-DS-00192 | Dwg | PF | Bias Circuit Assembly | 8 | Signed-Off | 2004-04-06 | Auth for Flight Prod | 2004-05-07 | 0 | Yes | 0 | 0 | 0 | 0 | 2004-03-30 | 48422 | 800 & 50 | 648 | 0.24 | 3/26/04 (42) | 2004-03-26 | 66503 | TBD | 0 | 0
156 | 4 | LAT-DS-00050 | 9 | LAT-DS-03488 | Dwg | PF | Closeout Corner Pin | 1 | Signed-Off | 2004-05-14 | Auth for Flight Prod | 2004-05-18 | Dwg released; OK to fab or procure part | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
157 | 4 | LAT-DS-00050 | 10 | LAT-DS-00417 | Dwg | PF | 3-Blade Narrow Span Side Flexure | 6 | Signed-Off | 2004-03-08 | Auth for Flight Prod | 0 | 0 | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
158 | 4 | LAT-DS-00050 | 11 | LAT-DS-02786 | Dwg | PF | 3-Blade Wide Span Side Flexure | 3 | Signed-Off | 2004-03-08 | Auth for Flight Prod | 0 | 0 | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
159 | 4 | LAT-DS-00050 | 12 | GSFC NA 0069-040018 |  | MP | M4x0.7x16 LG SHCS, A-286 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 2004-06-09 | Bolt spec changed to GSFC part | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
160 | 4 | LAT-DS-00050 | 13 | Hysol EA-934NA |  | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
161 | 4 | LAT-DS-00050 | 14 | Redux 312 UL |  | MT | Film Adhesive (core to face sheet) | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
162 | 4 | LAT-DS-00050 | 15 | Hysol M-9-N |  | MT | Epoxy Ink White | 0 | GSFC Pending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
163 | 4 | LAT-DS-00050 | 16 | 3M 2216 B/A Grey |  | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 2004-05-03 | 0 | 0 | 0 | 0 | 0 | INFN/Plyform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
164 | 4 | LAT-DS-00050 | 17 | AEROGLAZE Z306 |  | MT | Black Polyurethane Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 8 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
165 | 4 | LAT-DS-00050 | 18 | AEROGLAZE 9924 |  | MT | Primer for Z 306 Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 8 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
166 | 4 | LAT-DS-00050 | 19 | AEROGLAZE 9958 |  | MT | Thinner for Z 306 Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 4 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
167 | 4 | LAT-DS-00050 | 20 | DIN 912-A2 M2.5 |  | MP | M2.5x0.45x5 LG SHCS, 18-8 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 2004-05-31 | Bolt spec'd and OK to procure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
168 | 4 | LAT-DS-00050 | 21 | LAT-DS-03960 | Dwg | SA | Grounding Lug Assembly | 2 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
169 | 4 | LAT-DS-00050 | 22 | Nusil CV-2646 |  | MT | Conductive Silicone Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 42374 & 44912 | 1ea. 500gm & 2ea. 500gm | N/A | N/A | 2003-06-16 | 0 | 0 | 0 | 0 | 0
170 | 3 | LAT-DS-00051 | 2 | LAT-DS-00898 | Dwg | SA | Short TMCM Assembly | 10 | Signed Off | 2004-06-23 | Auth for Flight Prod | 2004-07-26 | 0 | Yes | 0 | 0 | 0 | SLAC | 2004-03-31 | 48017 | 578 | 576 | 0 | 0 | 0 | 0 | 0 | 0 | 0
171 | 3 | LAT-DS-00051 | 3 | LAT-DS-00594 | Dwg | SA | Ladder Assembly | 2 | Signed Off | 2002-09-05 | 0 | 2004-05-25 | Fab'ing to obsolete drawing; revision underway | 0 | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
172 | 3 | LAT-DS-00051 | 5 | LAT-DS-02112 | Dwg | PF | TMCM Mounting Pin | 2 | Signed-Off | 2004-05-18 | Auth for Flight Prod | 2004-05-20 | Dwg approved; OK to fab | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
173 | 3 | LAT-DS-00051 | 6 | Nusil CV-1142 | Dwg | MT | Non-Slumping RTV Silicone | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 42374 | 7 ea. 6 oz. Tubes | N/A | N/A | 2003-06-16 | 0 | 0 | 0 | 0 | 0
174 | 3 | LAT-DS-00051 | 7 | Nusil CV-2646 | Dwg | MT | Conductive Silicone Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 42374 & 44912 | 1ea. 500gm & 2ea. 500gm | N/A | N/A | 2003-06-16 | 0 | 0 | 0 | 0 | 0
175 | 3 | LAT-DS-00051 | 8 | 3M 2216 B/A Grey | Dwg | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 2004-05-03 | 0 | 0 | 0 | 0 | 0 | INFN/Plyform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
176 | 3 | LAT-DS-00051 | 9 | Nusil CV-2502 | Dwg | MT | Thixotropic Silicone Encapsulant | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 42374 | 1 ea. 500 gram | N/A | N/A | 2003-06-16 | 2004-10-20 | N/A | 0 | 0 | 0
177 | 3 | LAT-DS-00051 | 10 | Al 99%, Si 1% | Dwg | MT | Bond Wire 25 micron diam | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
178 | 3 | LAT-DS-00051 | 11 | Hysol M-9-N | Dwg | MT | Epoxy Ink White | 0 | GSFC Pending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
179 | Top Tray Assembly | bar: 2 to 25
180 | 2 | LAT-DS-00722 |  | LAT-DS-00764 | Dwg | SA | Top Tray Assy with Payload | 4 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
181 | 3 | LAT-DS-00764 | 1 | LAT-DS-00207 | Dwg | SA | Top Tray Mechanical Assembly | 6 | Signed-Off | 2002-06-10 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
182 | 4 | LAT-DS-00207 | 1 | LAT-DS-00356 | Dwg | SA | MCM Closeout Wall Assembly | 5 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
183 | 5 | LAT-DS-00356 | 1 | LAT-DS-00197 | Dwg | PF | MCM Closeout Wall | 5 | Signed-Off | 2004-05-20 | Auth for Flight Prod | 2004-05-18 | Dwg mod'd to fix TMCM hole; OK to fab part | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
184 | 5 | LAT-DS-00356 | 2 | LAT-DS-03539 | Dwg | PF | M2.5 x 7.5 LG Insert | 2 | Signed-Off | 2004-05-20 | Auth for Flight Prod | 2004-05-20 | Dwg approved; OK to fab | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
185 | 5 | LAT-DS-00356 | 3 | LAT-DS-00592 | Dwg | PF | M4 x 5.75 LG Insert | 3 | Signed-Off | 2004-05-20 | Auth for Flight Prod | 2004-05-20 | Dwg approved; OK to fab | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186 | 5 | LAT-DS-00356 | 4 | LAT-DS-03538 | Dwg | PF | 3mm Insert | 2 | Signed-Off | 2004-05-20 | Auth for Flight Prod | 2004-05-20 | Dwg approved; OK to fab | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
187 | 5 | LAT-DS-00356 | 5 | Hysol EA-934NA |  | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
188 | 5 | LAT-DS-00356 | 6 | AEROGLAZE Z306 |  | MT | Black Polyurethane Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 8 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
189 | 5 | LAT-DS-00356 | 7 | AEROGLAZE 9924 |  | MT | Primer for Z 306 Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 8 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
190 | 5 | LAT-DS-00356 | 8 | AEROGLAZE 9958 |  | MT | Thinner for Z 306 Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 4 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
191 | 4 | LAT-DS-00207 | 2 | LAT-DS-00357 | Dwg | SA | Structural Closeout Wall Assy | 5 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
192 | 5 | LAT-DS-00357 | 1 | LAT-DS-00196 | Dwg | PF | STRL Closeout Wall | 4 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-05-07 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
193 | 5 | LAT-DS-00357 | 2 | LAT-DS-00592 | Dwg | PF | M4 x 5.75 LG Insert | 3 | Signed-Off | 2004-05-20 | Auth for Flight Prod | 2004-05-20 | Dwg approved; OK to fab | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
194 | 5 | LAT-DS-00357 | 3 | LAT-DS-03539 | Dwg | PF | M2.5 x 7.5 LG Insert | 2 | Signed-Off | 2004-05-20 | Auth for Flight Prod | 2004-05-20 | Dwg approved; OK to fab | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
195 | 5 | LAT-DS-00357 | 4 | LAT-DS-03538 | Dwg | PF | 3mm Insert | 2 | Signed-Off | 2004-05-20 | Auth for Flight Prod | 2004-05-20 | Dwg approved; OK to fab | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
196 | 5 | LAT-DS-00357 | 5 | Hysol EA-934NA |  | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
197 | 5 | LAT-DS-00357 | 6 | AEROGLAZE Z306 |  | MT | Black Polyurethane Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 8 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
198 | 5 | LAT-DS-00357 | 7 | AEROGLAZE 9924 |  | MT | Primer for Z 306 Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 8 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
199 | 5 | LAT-DS-00357 | 8 | AEROGLAZE 9958 |  | MT | Thinner for Z 306 Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 4 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
200 | 4 | LAT-DS-00207 | 3 | LAT-DS-00198 | Dwg | PF | Top Tray Bottom Face Sheet | 4 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-05-18 | OK for fab; coupons from Plyform to B. Rodini | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201 | 4 | LAT-DS-00207 | 4 | LAT-DS-00199 | Dwg | PF | Top Tray Top Face Sheet | 4 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-05-18 | OK for fab; coupons from Plyform to B. Rodini | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
202 | 4 | LAT-DS-00207 | 5 | PAMG-XR1-1.0-3/8-0007-P-5056 |  | PP | 5056 Alum Honeycomb 1.0 pcf x 3/8" cell | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | [8 empty] | ? | 0 | 0
203 | 4 | LAT-DS-00207 | 6 | LAT-DS-00791 | Dwg | PF | 3% Converter | 3 | Signed Off | 2004-02-09 | Auth for Flight Prod | 2004-05-07 | 0 | 0 | 0 | 0 | 0 | ? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | 4 | LAT-DS-00207 | 7 | LAT-DS-00192 | Dwg | PF | Bias Circuit Assembly | 8 | Signed-Off | 2004-04-06 | Auth for Flight Prod | 2004-05-07 | 0 | Yes | 0 | 0 | 0 | 0 | 2004-03-30 | 48422 | 800 & 50 | 648 | 0.24 | 3/26/04 (42) | 2004-03-26 | 66503 | TBD | 0 | 0
205 | 4 | LAT-DS-00207 | 9 | LAT-DS-02608 | Dwg | PF | Grounding Tube | 2 | Signed-Off | 2004-03-16 | Auth for Flight Prod | 0 | 0 | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
206 | 4 | LAT-DS-00207 | 10 | Redux 312 UL |  | MT | Film Adhesive (core to face sheet) | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
207 | 4 | LAT-DS-00207 | 11 | Hysol EA-934NA |  | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
208 | 4 | LAT-DS-00207 | 12 | Hysol M-9-N |  | MT | Epoxy Ink White | 0 | GSFC Pending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
209 | 4 | LAT-DS-00207 | 13 | 3M 2216 B/A Grey |  | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 2004-05-03 | 0 | 0 | 0 | 0 | 0 | INFN/Plyform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
210 | 4 | LAT-DS-00207 | 14 | AEROGLAZE Z306 |  | MT | Black Polyurethane Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 8 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
211 | 4 | LAT-DS-00207 | 15 | AEROGLAZE 9924 |  | MT | Primer for Z 306 Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 8 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
212 | 4 | LAT-DS-00207 | 16 | AEROGLAZE 9958 |  | MT | Thinner for Z 306 Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 4 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
213 | 4 | LAT-DS-00207 | 17 | Nusil CV-2646 |  | MT | Conductive Silicone Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 38062 | 42374 & 44912 | 1ea. 500gm & 2ea. 500gm | N/A | N/A | 37788 | 0 | 0 | 0 | 0 | 0
214 | 3 | LAT-DS-00764 | 2 | LAT-DS-00594 | Dwg | SA | Ladder Assembly | 2 | Signed Off | 2002-09-05 | 0 | 2004-05-25 | Fab'ing to obsolete drawing; revision underway | 0 | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
215 | 3 | LAT-DS-00764 | 3 | LAT-DS-00898 | Dwg | SA | Short TMCM Assembly | 10 | Signed Off | 2004-06-23 | Auth for Flight Prod | 2004-07-26 | 0 | Yes | 0 | 0 | 0 | SLAC | 2004-03-31 | 48017 | 578 | 576 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 3 | LAT-DS-00764 | 5 | LAT-DS-02112 | Dwg | PF | TMCM Mounting Pin | 2 | Signed-Off | 2004-05-18 | Auth for Flight Prod | 2004-05-20 | Dwg approved; OK to fab | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
217 | 3 | LAT-DS-00764 | 6 | Nusil CV-1142 | Dwg | MT | Non-Slumping RTV Silicone | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 42374 | 7 ea. 6 oz. Tubes | N/A | N/A | 2003-06-16 | 0 | 0 | 0 | 0 | 0
218 | 3 | LAT-DS-00764 | 7 | Nusil CV-2646 | Dwg | MT | Conductive Silicone Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 42374 & 44912 | 1ea. 500gm & 2ea. 500gm | N/A | N/A | 2003-06-16 | 0 | 0 | 0 | 0 | 0
219 | 3 | LAT-DS-00764 | 8 | 3M 2216 B/A Grey | Dwg | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 2004-05-03 | 0 | 0 | 0 | 0 | 0 | INFN/Plyform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220 | 3 | LAT-DS-00764 | 9 | Nusil CV-2502 | Dwg | MT | Thixotropic Silicone Encapsulant | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 42374 | 1 ea. 500 gram | N/A | N/A | 2003-06-16 | 2004-10-20 | N/A | 0 | 0 | 0
221 | 3 | LAT-DS-00764 | 10 | Al 99%, Si 1% | Dwg | MT | Bond Wire 25 micron diam | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 3 | LAT-DS-00764 | 11 | Hysol M-9-N | Dwg | MT | Epoxy Ink White | 0 | GSFC Pending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
223 | Mid-Tray Regular Converter Ass'y | bar: 2 to 25
224 | 2 | LAT-DS-00722 |  | LAT-DS-00180 | Dwg | SA | Mid Tray Reg Convert Ass'y w/Payload | 4 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
225 | 3 | LAT-DS-00180 | 1 | LAT-DS-00148 | Dwg | SA | Reg. Converter Mech Tray Ass'y | 5 | In-Work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
226 | 4 | LAT-DS-00148 | 1 | LAT-DS-00139 | Dwg | SA | MCM Closeout Wall Assy | 6 | Offline | 0 | 0 | 2004-09-07 | New rev in works to complete dwg | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 | 5 | LAT-DS-00139 | 1 | LAT-DS-00092 | Dwg | PF | MCM Closeout Wall | 7 | Offline | 0 | 0 | 2004-09-07 | New rev in works to complete dwg | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | 5 | LAT-DS-00139 | 2 | LAT-DS-00094 | Dwg | PF | Closeout Frame Insert | 3 | Signed-Off | 2004-01-30 | Auth for Flight Prod | 2004-09-07 | Mat'l call-out S/B 7075-T6 | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | 5 | LAT-DS-00139 | 3 | LAT-DS-00718 | Dwg | PF | 3mm Insert | 3 | Signed Off | 2004-01-26 | Auth for Flight Prod | 2004-09-07 | Mat'l call-out S/B 7075-T6 | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | 5 | LAT-DS-00356 | 4 | Hysol EA-934NA |  | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | 5 | LAT-DS-00356 | 5 | AEROGLAZE Z306 |  | MT | Black Polyurethane Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 8 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
232 | 5 | LAT-DS-00356 | 6 | AEROGLAZE 9924 |  | MT | Primer for Z 306 Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 8 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
233 | 5 | LAT-DS-00356 | 7 | AEROGLAZE 9958 |  | MT | Thinner for Z 306 Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 4 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
234 | 4 | LAT-DS-00148 | 2 | LAT-DS-00140 | Dwg | SA | STRL Closeout Wall Assy | 4 | Offline | 0 | 0 | 2004-09-07 | New rev in works to complete dwg | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
235 | 5 | LAT-DS-00140 | 1 | LAT-DS-00093 | Dwg | PF | STRL Closeout Wall | 6 | Offline | 0 | 0 | 2004-09-07 | New rev in works to complete dwg | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
236 | 5 | LAT-DS-00140 | 2 | LAT-DS-00094 | Dwg | PF | Closeout Frame Insert | 3 | Signed-Off | 2004-01-30 | Auth for Flight Prod | 2004-09-07 | Mat'l call-out S/B 7075-T6 | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
237 | 5 | LAT-DS-00139 | 3 | LAT-DS-00718 | Dwg | PF | 3mm Insert | 3 | Signed Off | 2004-01-26 | Auth for Flight Prod | 2004-09-07 | Mat'l call-out S/B 7075-T6 | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
238 | 5 | LAT-DS-00356 | 4 | Hysol EA-934NA |  | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
239 | 5 | LAT-DS-00356 | 5 | AEROGLAZE Z306 |  | MT | Black Polyurethane Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 8 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
240 | 5 | LAT-DS-00356 | 6 | AEROGLAZE 9924 |  | MT | Primer for Z 306 Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 8 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
241 | 5 | LAT-DS-00356 | 7 | AEROGLAZE 9958 |  | MT | Thinner for Z 306 Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 4 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
242 | 4 | LAT-DS-00148 | 3 | LAT-DS-00049 | Dwg | PF | Mid Tray Assy Face Sheet Top | 4 | Signed Off | 2004-02-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
243 | 4 | LAT-DS-00148 | 4 | PAMG-XR1-1.0-3/8-0007-P-5056 | Dwg | PP | 5056 Alum Honeycomb 1.0 pcf x 3/8" cell | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-04-22 | 46721 | 286 | 198 | 0.31 | Drop Ship | 2004-01-29 | N/A | ? | 0 | 0
244 | 4 | LAT-DS-00148 | 5 | LAT-DS-00596 | Dwg | PF | Mid Tray Assy Face Sheet Bottom | 3 | Signed Off | 2004-01-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
245 | 3 | LAT-DS-00148 | 6 | LAT-DS-00791 | Dwg | PF | 3% Converter | 3 | Signed Off | 2004-02-09 | Auth for Flight Prod | 2004-05-07 | 0 | 0 | 0 | 0 | 0 | ? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
246 | 4 | LAT-DS-00148 | 7 | LAT-DS-00192 | Dwg | PF | Bias Circuit Assembly | 8 | Signed-Off | 2004-04-06 | Auth for Flight Prod | 2004-05-07 | 0 | Yes | 0 | 0 | 0 | 0 | 2004-03-30 | 48422 | 800 & 50 | 648 | 0.24 | 3/26/04 (42) | 2004-03-26 | 66503 | TBD | 0 | 0
247 | 4 | LAT-DS-00148 | 8 | Redux 312 UL | Dwg | MT | Film Adhesive (core to face sheet) | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
248 | 4 | LAT-DS-00148 | 9 | Hysol EA-934NA | Dwg | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
249 | 4 | LAT-DS-00148 | 10 | Hysol M-9-N | Dwg | MT | Epoxy Ink White | 0 | GSFC Pending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
250 | 4 | LAT-DS-00148 | 11 | 3M 2216 B/A Grey | Dwg | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 2004-05-03 | 0 | 0 | 0 | 0 | 0 | INFN/Plyform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
251 | 4 | LAT-DS-00148 | 12 | AEROGLAZE Z306 | Dwg | MT | Black Polyurethane Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 8 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
252 | 4 | LAT-DS-00148 | 13 | AEROGLAZE 9924 | Dwg | MT | Primer for Z 306 Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 8 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
253 | 4 | LAT-DS-00148 | 14 | AEROGLAZE 9958 | Dwg | MT | Thinner for Z 306 Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 4 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
254 | 4 | LAT-DS-00148 | 15 | LAT-DS-02608 | Dwg | PF | Grounding Tube | 2 | Signed-Off | 2004-03-16 | Auth for Flight Prod | 0 | 0 | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
255 | 4 | LAT-DS-00148 | 16 | Nusil CV-2646 | Dwg | MT | Conductive Silicone Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 42374 & 44912 | 1ea. 500gm & 2ea. 500gm | N/A | N/A | 2003-06-16 | 0 | 0 | 0 | 0 | 0
256 | 3 | LAT-DS-00180 | 2 | LAT-DS-00594 | Dwg | SA | Ladder Assembly | 2 | Signed Off | 2002-09-05 | 0 | 2004-05-25 | Fab'ing to obsolete drawing; revision underway | 0 | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
257 | 3 | LAT-DS-00180 | 3 | LAT-DS-00898 | Dwg | SA | Short TMCM Assembly | 10 | Signed Off | 2004-06-23 | Auth for Flight Prod | 2004-07-26 | 0 | Yes | 0 | 0 | 0 | SLAC | 2004-03-31 | 48017 | 578 | 576 | 0 | 0 | 0 | 0 | 0 | 0 | 0
258 | 3 | LAT-DS-00180 | 5 | LAT-DS-02112 | Dwg | PF | TMCM Mounting Pin | 2 | Signed-Off | 2004-05-18 | Auth for Flight Prod | 2004-05-20 | Dwg approved; OK to fab | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
259 | 3 | LAT-DS-00180 | 6 | Nusil CV-1142 | Dwg | MT | Non-Slumping RTV Silicone | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 42374 | 7 ea. 6 oz. Tubes | N/A | N/A | 2003-06-16 | 0 | 0 | 0 | 0 | 0
260 | 3 | LAT-DS-00180 | 7 | Nusil CV-2646 | Dwg | MT | Conductive Silicone Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 42374 & 44912 | 1ea. 500gm & 2ea. 500gm | N/A | N/A | 2003-06-16 | 0 | 0 | 0 | 0 | 0
261 | 3 | LAT-DS-00180 | 8 | 3M 2216 B/A Grey | Dwg | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 2004-05-03 | 0 | 0 | 0 | 0 | 0 | INFN/Plyform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
262 | 3 | LAT-DS-00180 | 9 | Nusil CV-2502 | Dwg | MT | Thixotropic Silicone Encapsulant | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 42374 | 1 ea. 500 gram | N/A | N/A | 2003-06-16 | 2004-10-20 | N/A | 0 | 0 | 0
263 | 3 | LAT-DS-00180 | 10 | Al 99%, Si 1% | Dwg | MT | Bond Wire 25 micron diam | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
264 | 3 | LAT-DS-00180 | 11 | Hysol M-9-N | Dwg | MT | Epoxy Ink White | 0 | GSFC Pending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
265 | Mid Tray No Converter Ass'y | bar: 2 to 25
266 | 2 | LAT-DS-00722 |  | LAT-DS-00181 | Dwg | SA | Mid Tray No Convert Ass'y w/Payload | 4 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
267 | 3 | LAT-DS-00181 | 1 | LAT-DS-02923 | Dwg | SA | No Converter Mech Tray Ass'y | 2 | Offline | 0 | 0 | 2004-09-07 | New rev in works to complete dwg | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
268 | 4 | LAT-DS-02923 | 1 | LAT-DS-00139 | Dwg | SA | MCM Closeout Wall Assy | 6 | Offline | 0 | 0 | 2004-09-07 | New rev in works to complete dwg | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
269 | 5 | LAT-DS-00139 |  | LAT-DS-00092 | Dwg | PF | MCM Closeout Wall | 7 | Offline | 0 | 0 | 2004-09-07 | New rev in works to complete dwg | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
270 | 5 | LAT-DS-00139 |  | LAT-DS-00094 | Dwg | PF | Closeout Frame Insert | 3 | Signed-Off | 2004-01-30 | Auth for Flight Prod | 2004-09-07 | Mat'l call-out S/B 7075-T6 | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 5 | LAT-DS-00139 |  | LAT-DS-00718 | Dwg | PF | 3mm Insert | 3 | Signed Off | 2004-01-26 | Auth for Flight Prod | 2004-09-07 | Mat'l call-out S/B 7075-T6 | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
272 | 4 | LAT-DS-02923 | 2 | LAT-DS-00140 | Dwg | SA | STRL Closeout Wall Assy | 4 | Offline | 0 | 0 | 2004-09-07 | New rev in works to complete dwg | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
273 | 5 | LAT-DS-00140 |  | LAT-DS-00093 | Dwg | PF | STRL Closeout Wall | 6 | Offline | 0 | 0 | 2004-09-07 | New rev in works to complete dwg | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
274 | 5 | LAT-DS-00140 |  | LAT-DS-00094 | Dwg | PF | Closeout Frame Insert | 3 | Signed-Off | 2004-01-30 | Auth for Flight Prod | 2004-09-07 | Mat'l call-out S/B 7075-T6 | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
275 | 4 | LAT-DS-02923 | 3 | LAT-DS-00049 | Dwg | PF | Mid Tray Assy Face Sheet Top | 4 | Signed Off | 2004-02-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
276 | 4 | LAT-DS-02923 | 4 | PAMG-XR1-1.0-3/8-0007-P-5056 | Dwg | PP | 5056 Alum Honeycomb 1.0 pcf x 3/8" cell | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-04-22 | 46721 | 286 | 198 | 0.31 | Drop Ship | 2004-01-29 | N/A | ? | 0 | 0
277 | 3 | LAT-DS-02923 | 5 | LAT-DS-00596 | Dwg | PF | Mid Tray Assy Face Sheet Bottom | 3 | Signed Off | 2004-01-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
278 | 4 | LAT-DS-02923 | 6 | LAT-DS-00192 | Dwg | PF | Bias Circuit Assembly | 8 | Signed-Off | 2004-04-06 | Auth for Flight Prod | 2004-05-07 | 0 | Yes | 0 | 0 | 0 | 0 | 2004-03-30 | 48422 | 800 & 50 | 648 | 0.24 | 3/26/04 (42) | 2004-03-26 | 66503 | TBD | 0 | 0
279 | 4 | LAT-DS-02923 | 7 | LAT-DS-02608 | Dwg | PF | Grounding Tube | 2 | Signed-Off | 2004-03-16 | Auth for Flight Prod | 0 | 0 | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
280 | 4 | LAT-DS-02923 | 8 | Redux 312 UL | Dwg | MT | Film Adhesive (core to face sheet) | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
281 | 4 | LAT-DS-02923 | 9 | Hysol EA-934NA | Dwg | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 4 | LAT-DS-02923 | 10 | Hysol M-9-N | Dwg | MT | Epoxy Ink White | 0 | GSFC Pending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
283 | 4 | LAT-DS-02923 | 11 | 3M 2216 B/A Grey | Dwg | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 2004-05-03 | 0 | 0 | 0 | 0 | 0 | INFN/Plyform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
284 | 4 | LAT-DS-02923 | 12 | AEROGLAZE Z306 | Dwg | MT | Black Polyurethane Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 8 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
285 | 4 | LAT-DS-02923 | 13 | AEROGLAZE 9924 | Dwg | MT | Primer for Z 306 Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 8 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
286 | 4 | LAT-DS-02923 | 14 | AEROGLAZE 9958 | Dwg | MT | Thinner for Z 306 Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 4 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
287 | 4 | LAT-DS-02923 | 15 | Nusil CV-2646 | Dwg | MT | Conductive Silicone Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 42374 & 44912 | 1ea. 500gm & 2ea. 500gm | N/A | N/A | 2003-06-16 | 0 | 0 | 0 | 0 | 0
288 | 3 | LAT-DS-00180 | 2 | LAT-DS-00594 | Dwg | SA | Ladder Assembly | 2 | Signed Off | 2002-09-05 | 0 | 2004-05-25 | Fab'ing to obsolete drawing; revision underway | 0 | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
289 | 3 | LAT-DS-00180 | 3 | LAT-DS-00898 | Dwg | SA | Short TMCM Assembly | 10 | Signed Off | 2004-06-23 | Auth for Flight Prod | 2004-07-26 | 0 | Yes | 0 | 0 | 0 | SLAC | 2004-03-31 | 48017 | 578 | 576 | 0 | 0 | 0 | 0 | 0 | 0 | 0
290 | 3 | LAT-DS-00180 | 5 | LAT-DS-02112 | Dwg | PF | TMCM Mounting Pin | 2 | Signed-Off | 2004-05-18 | Auth for Flight Prod | 2004-05-20 | Dwg approved; OK to fab | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
291 | 3 | LAT-DS-00180 | 6 | Nusil CV-1142 | Dwg | MT | Non-Slumping RTV Silicone | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 42374 | 7 ea. 6 oz. Tubes | N/A | N/A | 2003-06-16 | 0 | 0 | 0 | 0 | 0
292 | 3 | LAT-DS-00180 | 7 | Nusil CV-2646 | Dwg | MT | Conductive Silicone Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 42374 & 44912 | 1ea. 500gm & 2ea. 500gm | N/A | N/A | 2003-06-16 | 0 | 0 | 0 | 0 | 0
293 | 3 | LAT-DS-00180 | 8 | 3M 2216 B/A Grey | Dwg | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 2004-05-03 | 0 | 0 | 0 | 0 | 0 | INFN/Plyform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
294 | 3 | LAT-DS-00180 | 9 | Nusil CV-2502 | Dwg | MT | Thixotropic Silicone Encapsulant | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 42374 | 1 ea. 500 gram | N/A | N/A | 2003-06-16 | 2004-10-20 | N/A | 0 | 0 | 0
295 | 3 | LAT-DS-00180 | 10 | Al 99%, Si 1% | Dwg | MT | Bond Wire 25 micron diam | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
296 | 3 | LAT-DS-00180 | 11 | Hysol M-9-N | Dwg | MT | Epoxy Ink White | 0 | GSFC Pending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
297 | Mid-Tray Heavy Converter Ass'y | bar: 2 to 25
298 | 2 | LAT-DS-00722 |  | LAT-DS-00747 | Dwg | SA | Mid Tray Hvy Convert Ass'y w/Payload | 3 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
299 | 3 | LAT-DS-00747 | 1 | LAT-DS-00647 | Dwg | SA | Heavy Converter Mech Tray Ass'y | 4 | Offline | 0 | 0 | 2004-09-07 | New rev in works to complete dwg | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
300 | 4 | LAT-DS-00747 | 1 | LAT-DS-00139 | Dwg | SA | MCM Closeout Wall Assy | 6 | Offline | 0 | 0 | 2004-09-07 | New rev in works to complete dwg | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
301 | 5 | LAT-DS-00139 |  | LAT-DS-00092 | Dwg | PF | MCM Closeout Wall | 7 | Offline | 0 | 0 | 2004-09-07 | New rev in works to complete dwg | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
302 | 5 | LAT-DS-00139 |  | LAT-DS-00094 | Dwg | PF | Closeout Frame Insert | 3 | Signed-Off | 2004-01-30 | Auth for Flight Prod | 2004-09-07 | Mat'l call-out S/B 7075-T6 | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
303 | 5 | LAT-DS-00139 |  | LAT-DS-00718 | Dwg | PF | 3mm Insert | 3 | Signed Off | 2004-01-26 | Auth for Flight Prod | 2004-09-07 | Mat'l call-out S/B 7075-T6 | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
304 | 4 | LAT-DS-00747 | 2 | LAT-DS-00140 | Dwg | SA | STRL Closeout Wall Assy | 4 | Offline | 0 | 0 | 2004-09-07 | New rev in works to complete dwg | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
305 | 5 | LAT-DS-00140 |  | LAT-DS-00093 | Dwg | PF | STRL Closeout Wall | 6 | Offline | 0 | 0 | 2004-09-07 | New rev in works to complete dwg | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
306 | 5 | LAT-DS-00140 |  | LAT-DS-00094 | Dwg | PF | Closeout Frame Insert | 3 | Signed-Off | 2004-01-30 | Auth for Flight Prod | 2004-09-07 | Mat'l call-out S/B 7075-T6 | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
307 | 4 | LAT-DS-00747 | 3 | PAMG-XR1-3.0-3/8-002-P-5056 | Dwg | PP | 5056 Alum Honeycomb 3.0 pcf x 3/8" cell | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 46721 | 88 | 0 | 0 | Drop Ship | 2004-01-29 | N/A | ? | 0 | 0
308 | 4 | LAT-DS-00747 | 4 | LAT-DS-00617 | Dwg | PF | Heavy Convert Tray Face Sheet Top | 4 | Signed Off | 2004-02-09 | Auth for Flight Prod | 0 | 0 | 0 | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
309 | 4 | LAT-DS-00747 | 5 | LAT-DS-00618 | Dwg | PF | Heavy Convert Tray Face Sheet Bottom | 4 | Signed Off | 2004-02-09 | Auth for Flight Prod | 0 | 0 | 0 | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
310 | 3 | LAT-DS-00747 | 6 | LAT-DS-00192 | Dwg | PF | Bias Circuit Assembly | 8 | Signed-Off | 2004-04-06 | Auth for Flight Prod | 2004-05-07 | 0 | Yes | 0 | 0 | 0 | 0 | 2004-03-30 | 48422 | 800 & 50 | 648 | 0.24 | 3/26/04 (42) | 2004-03-26 | 66503 | TBD | 0 | 0
311 | 4 | LAT-DS-00747 | 7 | LAT-DS-00792 | Dwg | PF | 18% Converter | 4 | Signed Off | 2004-01-13 | Auth for Flight Prod | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-15 | 40485 | 1280 | 1152 | 0.1 | Drop Ship | 2003-08-09 | N/A | ? | 0 | 0
312 | 4 | LAT-DS-00747 | 8 | LAT-DS-02608 | Dwg | PF | Grounding Tube | 2 | Signed-Off | 2004-03-16 | Auth for Flight Prod | 0 | 0 | Yes | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
313 | 4 | LAT-DS-00747 | 9 | Redux 312 UL | Dwg | MT | Film Adhesive (core to face sheet) | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
314 | 4 | LAT-DS-00747 | 10 | Hysol EA-934NA | Dwg | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
315 | 4 | LAT-DS-00747 | 11 | Hysol M-9-N | Dwg | MT | Epoxy Ink White | 0 | GSFC Pending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
316 | 4 | LAT-DS-00747 | 12 | 3M 2216 B/A Grey | Dwg | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 2004-05-03 | 0 | 0 | 0 | 0 | 0 | INFN/Plyform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
317 | 4 | LAT-DS-00747 | 13 | AEROGLAZE Z306 | Dwg | MT | Black Polyurethane Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 8 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
318 | 4 | LAT-DS-00747 | 14 | AEROGLAZE 9924 | Dwg | MT | Primer for Z 306 Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 8 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
319 | 4 | LAT-DS-00747 | 15 | AEROGLAZE 9958 | Dwg | MT | Thinner for Z 306 Paint | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 45276 | 4 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A | 0 | 0 | 0
320 | 4 | LAT-DS-00747 | 16 | Nusil CV-2646 | Dwg | MT | Conductive Silicone Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 42374 & 44912 | 1ea. 500gm & 2ea. 500gm | N/A | N/A | 2003-06-16 | 0 | 0 | 0 | 0 | 0
321 | 3 | LAT-DS-00747 | 2 | LAT-DS-00594 | Dwg | SA | Ladder Assembly | 2 | Signed Off | 2002-09-05 | 0 | 2004-05-25 | Fab'ing to obsolete drawing; revision underway | 0 | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
322 | 3 | LAT-DS-00747 | 3 | LAT-DS-00898 | Dwg | SA | Short TMCM Assembly | 10 | Signed Off | 2004-06-23 | Auth for Flight Prod | 2004-07-26 | 0 | Yes | 0 | 0 | 0 | SLAC | 2004-03-31 | 48017 | 578 | 576 | 0 | 0 | 0 | 0 | 0 | 0 | 0
323 | 3 | LAT-DS-00747 | 4 | LAT-DS-00899 | Dwg | SA | Tall TMCM Assembly | 9 | Signed Off | 2004-06-23 | Auth for Flight Prod | 2004-07-26 | 0 | Yes | 0 | 0 | 0 | SLAC | 2004-03-31 | 48017 | 60 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0
324 | 3 | LAT-DS-00747 | 5 | LAT-DS-02112 | Dwg | PF | TMCM Mounting Pin | 2 | Signed-Off | 2004-05-18 | Auth for Flight Prod | 2004-05-20 | Dwg approved; OK to fab | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
325 | 3 | LAT-DS-00747 | 6 | Nusil CV-1142 | Dwg | MT | Non-Slumping RTV Silicone | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 42374 | 7 ea. 6 oz. Tubes | N/A | N/A | 2003-06-16 | 0 | 0 | 0 | 0 | 0
326 | 3 | LAT-DS-00747 | 7 | Nusil CV-2646 | Dwg | MT | Conductive Silicone Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 42374 & 44912 | 1ea. 500gm & 2ea. 500gm | N/A | N/A | 2003-06-16 | 0 | 0 | 0 | 0 | 0
327 | 3 | LAT-DS-00747 | 8 | 3M 2216 B/A Grey | Dwg | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 2004-05-03 | 0 | 0 | 0 | 0 | 0 | INFN/Plyform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
328 | 3 | LAT-DS-00747 | 9 | Nusil CV-2502 | Dwg | MT | Thixotropic Silicone Encapsulant | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 42374 | 1 ea. 500 gram | N/A | N/A | 2003-06-16 | 2004-10-20 | N/A | 0 | 0 | 0
329 | 3 | LAT-DS-00747 | 10 | Al 99%, Si 1% | Dwg | MT | Bond Wire 25 micron diam | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
330 | 3 | LAT-DS-00747 | 11 | Hysol M-9-N | Dwg | MT | Epoxy Ink White | 0 | GSFC Pending | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
331
332
333
334

## 3. EEE Assy Trees
|  | 3. Tracker Electrical Assemblies and Parts Disposition | [7 empty] | Updated: | 2004-09-30 | Printed: | 2004-09-30 16:04
[10 empty] | Document Status from LAT Docs | [5 empty] | H'Ware Need Dates |  |  |  |  | H'Ware Order Status |  |  |  | Shipping Status |  |  | Disposition
# | Lvl | Next Assy | BOM # | Doc / Part # | Dwg Link | Type | Title / Description | Rev | Status | Release Date | Work Authorization | Status Date | Disposition/Comments/Date | Flt Dsn | Status Date | at SLAC | at INFN | Supplied by | Status Date | SLAC P.O. # | Quantity Ordered | Qty Needed | Spares | Rec'd at SLAC | Ship Date | Shipper # | Rec'd at INFN | Work Order # | NCR (if any)
1 |  |  |  | 1 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
2 | Flex Cable Details | bar: 2 to 25
3 | 2 | LAT-DS-00722 |  | LAT-DS-03183 | Dwg | SA | C-0 Bent Assembly | 2 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 3 | LAT-DS-03183 |  | LAT-DS-02377 | Dwg | SA | C-0 Flat Assembly | 4 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 4 | LAT-DS-02377 | 1 | LAT-DS-00584 | Dwg | PF | C-0 PWB Master Layout | 10 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 5 | LAT-DS-00584 |  | LAT-DS-00334 | Dwg | EE | C-0 Flex Cable Gerber File | 4 | Signed-Off | 2004-06-25 | Auth for Flight Prod | 2004-07-26 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 6 | LAT-DS-00334 |  | LAT-DS-02049 | Dwg | EE | Readout Flex Cable Schematic | 5 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 4 | LAT-DS-02377 | 2 | LAT-DS-03031 | Dwg | PF | Cable Stiffener | 2 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 4 | LAT-DS-02377 | 3 | IPC-4203/18OOXMX |  | MT | Acrylic Adhesive, 0.001" Thk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 4 | LAT-DS-02377 | 4 | LAT-DS-03040 | Dwg | PF | Connector Adhesive Preform | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 4 | LAT-DS-02377 | 5 | Omnetics A8486-001 |  | EE | Nano-Connector Plug, 37-Pin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 4 | LAT-DS-02377 | 6 | Cristek MCR-2051-2B1 |  | EE | Micro-D Connector Plug, 51-Pin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 4 | LAT-DS-02377 | 7 | YSI S-311-P18-09S7R6 |  | EE | Thermistor, 30K | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 4 | LAT-DS-02377 | 8 | M55342M02B100DR |  | EE | Resistor, 100 Ohm 1%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41333 | 6020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 4 | LAT-DS-02377 | 9 | M55342M02B200DR |  | EE | Resistor, 200 Ohm 1%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 4 | LAT-DS-02377 | 10 | M55342M02B39K0R |  | EE | Resistor, 39K-Ohm 5%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41333 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 4 | LAT-DS-02377 | 11 | Hysol EA 9394 |  | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2004-03-16 | 47130 | 25 ea. 50 ml | N/A | N/A | 2003-06-16 | 0 | 0 | 0 | 0 | 0
19 | 4 | LAT-DS-02377 | 12 | IPC/EIA-J-STD-006A |  | MT | SN63 PB37 Solder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 2 | LAT-DS-00722 |  | LAT-DS-03184 | Dwg | SA | C-1 Bent Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 3 | LAT-DS-03184 |  | LAT-DS-02378 | Dwg | SA | C-1 Flat Assembly | 2 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 4 | LAT-DS-02378 | 1 | LAT-DS-00723 | Dwg | PF | C-1 PWB Master Layout | 6 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 5 | LAT-DS-00723 |  | LAT-DS-00342 | Dwg | EE | C-1 Flex Cable Gerber File | 2 | Signed-Off | 2004-06-25 | Auth for Flight Prod | 2004-07-26 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 6 | LAT-DS-00334 |  | LAT-DS-02049 | Dwg | EE | Readout Flex Cable Schematic | 5 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 4 | LAT-DS-02378 | 2 | LAT-DS-03031 | Dwg | PF | Cable Stiffener | 2 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 5 | LAT-DS-03031 |  | LAT-DS-03037 | Dwg | EE | Flex Cable Stiffener Gerber File | 1 | Obsolete | 2004-05-27 | 0 | 2004-06-08 | Not used | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 4 | LAT-DS-02378 | 3 | IPC-4203/18OOXMX |  | MT | Acrylic Adhesive, 0.001" Thk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 4 | LAT-DS-02378 | 4 | LAT-DS-03040 | Dwg | PF | Connector Adhesive Preform | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 4 | LAT-DS-02378 | 5 | Omnetics A8486-001 |  | EE | Nano-Connector Plug, 37-Pin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 4 | LAT-DS-02378 | 6 | Cristek MCR-2051-2B1 |  | EE | Micro-D Connector Plug, 51-Pin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 4 | LAT-DS-02378 | 7 | YSI S-311-P18-09S7R6 |  | EE | Thermistor, 30K | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 4 | LAT-DS-02378 | 8 | M55342M02B100DR |  | EE | Resistor, 100 Ohm 1%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41333 | 6020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 4 | LAT-DS-02378 | 9 | M55342M02B200DR |  | EE | Resistor, 200 Ohm 1%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 4 | LAT-DS-02378 | 10 | M55342M02B39K0R |  | EE | Resistor, 39K-Ohm 5%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41333 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 4 | LAT-DS-02378 | 11 | Hysol EA 9394 |  | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2004-03-16 | 47130 | 25 ea. 50 ml | N/A | N/A | 2003-06-16 | 0 | 0 | 0 | 0 | 0
36 | 4 | LAT-DS-02378 | 12 | IPC/EIA-J-STD-006A |  | MT | SN63 PB37 Solder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 2 | LAT-DS-00722 |  | LAT-DS-03185 | Dwg | SA | C-2 Bent Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 3 | LAT-DS-03185 |  | LAT-DS-02379 | Dwg | SA | C-2 Flat Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 4 | LAT-DS-02379 | 1 | LAT-DS-00724 | Dwg | PF | C-2 PWB Master Layout | 6 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 5 | LAT-DS-00724 |  | LAT-DS-00336 | Dwg | EE | C-2 Flex Cable Gerber File | 2 | Signed-Off | 2004-06-25 | Auth for Flight Prod | 2004-07-26 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 6 | LAT-DS-00334 |  | LAT-DS-02049 | Dwg | EE | Readout Flex Cable Schematic | 5 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 4 | LAT-DS-02379 | 2 | LAT-DS-03031 | Dwg | PF | Cable Stiffener | 2 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 4 | LAT-DS-02379 | 3 | IPC-4203/18OOXMX |  | MT | Acrylic Adhesive, 0.001" Thk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 4 | LAT-DS-02379 | 4 | LAT-DS-03040 | Dwg | PF | Connector Adhesive Preform | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 4 | LAT-DS-02379 | 5 | Omnetics A8486-001 |  | EE | Nano-Connector Plug, 37-Pin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 4 | LAT-DS-02379 | 6 | Cristek MCR-2051-2B1 |  | EE | Micro-D Connector Plug, 51-Pin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 4 | LAT-DS-02379 | 7 | YSI S-311-P18-09S7R6 |  | EE | Thermistor, 30K | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 4 | LAT-DS-02379 | 8 | M55342M02B100DR |  | EE | Resistor, 100 Ohm 1%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41333 | 6020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 4 | LAT-DS-02379 | 9 | M55342M02B200DR |  | EE | Resistor, 200 Ohm 1%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 4 | LAT-DS-02379 | 10 | M55342M02B39K0R |  | EE | Resistor, 39K-Ohm 5%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41333 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 4 | LAT-DS-02379 | 11 | Hysol EA 9394 |  | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2004-03-16 | 47130 | 25 ea. 50 ml | N/A | N/A | 2003-06-16 | 0 | 0 | 0 | 0 | 0
53 | 4 | LAT-DS-02379 | 12 | IPC/EIA-J-STD-006A |  | MT | SN63 PB37 Solder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 2 | LAT-DS-00722 |  | LAT-DS-03186 | Dwg | SA | C-3 Bent Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | 3 | LAT-DS-03186 |  | LAT-DS-02380 | Dwg | SA | C-3 Flat Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 4 | LAT-DS-02380 | 1 | LAT-DS-00725 | Dwg | PF | C-3 PWB Master Layout | 6 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 5 | LAT-DS-00725 |  | LAT-DS-00337 | Dwg | EE | C-3 Flex Cable Gerber File | 2 | Signed-Off | 2004-06-25 | Auth for Flight Prod | 2004-07-26 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 6 | LAT-DS-00334 |  | LAT-DS-02049 | Dwg | EE | Readout Flex Cable Schematic | 5 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | 4 | LAT-DS-02380 | 2 | LAT-DS-03031 | Dwg | PF | Cable Stiffener | 2 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 5 | LAT-DS-03031 |  | LAT-DS-03037 | Dwg | EE | Flex Cable Stiffener Gerber File | 1 | Obsolete | 2004-05-27 | 0 | 2004-06-08 | Not used | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 4 | LAT-DS-02380 | 3 | IPC-4203/18OOXMX |  | MT | Acrylic Adhesive, 0.001" Thk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 4 | LAT-DS-02380 | 4 | LAT-DS-03040 | Dwg | PF | Connector Adhesive Preform | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 4 | LAT-DS-02380 | 5 | Omnetics A8486-001 |  | EE | Nano-Connector Plug, 37-Pin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 4 | LAT-DS-02380 | 6 | Cristek MCR-2051-2B1 |  | EE | Micro-D Connector Plug, 51-Pin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | 4 | LAT-DS-02380 | 7 | YSI S-311-P18-09S7R6 |  | EE | Thermistor, 30K | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | 4 | LAT-DS-02380 | 8 | M55342M02B100DR |  | EE | Resistor, 100 Ohm 1%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41333 | 6020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | 4 | LAT-DS-02380 | 9 | M55342M02B200DR |  | EE | Resistor, 200 Ohm 1%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | 4 | LAT-DS-02380 | 10 | M55342M02B39K0R |  | EE | Resistor, 39K-Ohm 5%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41333 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | 4 | LAT-DS-02380 | 11 | Hysol EA 9394 |  | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2004-03-16 | 47130 | 25 ea. 50 ml | N/A | N/A | 2003-06-16 | 0 | 0 | 0 | 0 | 0
70 | 4 | LAT-DS-02380 | 12 | IPC/EIA-J-STD-006A |  | MT | SN63 PB37 Solder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | 2 | LAT-DS-00722 |  | LAT-DS-03187 | Dwg | SA | C-4 Bent Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 3 | LAT-DS-03187 |  | LAT-DS-02381 | Dwg | SA | C-4 Flat Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | 4 | LAT-DS-02381 | 1 | LAT-DS-00726 | Dwg | PF | C-4 PWB Master Layout | 6 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 | 5 | LAT-DS-00726 |  | LAT-DS-00338 | Dwg | EE | C-4 Flex Cable Gerber File | 2 | Signed-Off | 2004-06-25 | Auth for Flight Prod | 2004-07-26 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 | 6 | LAT-DS-00334 |  | LAT-DS-02049 | Dwg | EE | Readout Flex Cable Schematic | 5 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | 4 | LAT-DS-02381 | 2 | LAT-DS-03031 | Dwg | PF | Cable Stiffener | 2 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | 5 | LAT-DS-03031 |  | LAT-DS-03037 | Dwg | EE | Flex Cable Stiffener Gerber File | 1 | Obsolete | 2004-05-27 | 0 | 2004-06-08 | Not used | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | 4 | LAT-DS-02381 | 3 | IPC-4203/18OOXMX |  | MT | Acrylic Adhesive, 0.001" Thk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | 4 | LAT-DS-02381 | 4 | LAT-DS-03040 | Dwg | PF | Connector Adhesive Preform | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | 4 | LAT-DS-02381 | 5 | Omnetics A8486-001 |  | EE | Nano-Connector Plug, 37-Pin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | 4 | LAT-DS-02381 | 6 | Cristek MCR-2051-2B1 |  | EE | Micro-D Connector Plug, 51-Pin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | 4 | LAT-DS-02381 | 7 | YSI S-311-P18-09S7R6 |  | EE | Thermistor, 30K | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | 4 | LAT-DS-02381 | 8 | M55342M02B100DR |  | EE | Resistor, 100 Ohm 1%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41333 | 6020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | 4 | LAT-DS-02381 | 9 | M55342M02B200DR |  | EE | Resistor, 200 Ohm 1%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | 4 | LAT-DS-02381 | 10 | M55342M02B39K0R |  | EE | Resistor, 39K-Ohm 5%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41333 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | 4 | LAT-DS-02381 | 11 | Hysol EA 9394 |  | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2004-03-16 | 47130 | 25 ea. 50 ml | N/A | N/A | 2003-06-16 | 0 | 0 | 0 | 0 | 0
87 | 4 | LAT-DS-02381 | 12 | IPC/EIA-J-STD-006A |  | MT | SN63 PB37 Solder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | 2 | LAT-DS-00722 |  | LAT-DS-03188 | Dwg | SA | C-5 Bent Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | 3 | LAT-DS-03188 |  | LAT-DS-02382 | Dwg | SA | C-5 Flat Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | 4 | LAT-DS-02382 | 1 | LAT-DS-00727 | Dwg | PF | C-5 PWB Master Layout | 6 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | 5 | LAT-DS-00727 |  | LAT-DS-00339 | Dwg | EE | C-5 Flex Cable Gerber File | 2 | Signed-Off | 2004-06-25 | Auth for Flight Prod | 2004-07-26 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | 6 | LAT-DS-00334 |  | LAT-DS-02049 | Dwg | EE | Readout Flex Cable Schematic | 5 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | 4 | LAT-DS-02382 | 2 | LAT-DS-03031 | Dwg | PF | Cable Stiffener | 2 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | 5 | LAT-DS-03031 |  | LAT-DS-03037 | Dwg | EE | Flex Cable Stiffener Gerber File | 1 | Obsolete | 2004-05-27 | 0 | 2004-06-08 | Not used | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | 4 | LAT-DS-02382 | 3 | IPC-4203/18OOXMX |  | MT | Acrylic Adhesive, 0.001" Thk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | 4 | LAT-DS-02382 | 4 | LAT-DS-03040 | Dwg | PF | Connector Adhesive Preform | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | 4 | LAT-DS-02382 | 5 | Omnetics A8486-001 |  | EE | Nano-Connector Plug, 37-Pin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | 4 | LAT-DS-02382 | 6 | Cristek MCR-2051-2B1 |  | EE | Micro-D Connector Plug, 51-Pin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | 4 | LAT-DS-02382 | 7 | YSI S-311-P18-09S7R6 |  | EE | Thermistor, 30K | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | 4 | LAT-DS-02382 | 8 | M55342M02B100DR |  | EE | Resistor, 100 Ohm 1%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41333 | 6020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | 4 | LAT-DS-02382 | 9 | M55342M02B200DR |  | EE | Resistor, 200 Ohm 1%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | 4 | LAT-DS-02382 | 10 | M55342M02B39K0R |  | EE | Resistor, 39K-Ohm 5%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41333 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | 4 | LAT-DS-02382 | 11 | Hysol EA 9394 |  | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2004-03-16 | 47130 | 25 ea. 50 ml | N/A | N/A | 2003-06-16 | 0 | 0 | 0 | 0 | 0
104 | 4 | LAT-DS-02382 | 12 | IPC/EIA-J-STD-006A |  | MT | SN63 PB37 Solder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 | 2 | LAT-DS-00722 |  | LAT-DS-03189 | Dwg | SA | C-6 Bent Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 | 3 | LAT-DS-03189 |  | LAT-DS-02383 | Dwg | SA | C-6 Flat Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 | 4 | LAT-DS-02383 | 1 | LAT-DS-00728 | Dwg | PF | C-6 PWB Master Layout | 6 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 | 5 | LAT-DS-00728 |  | LAT-DS-00340 | Dwg | EE | C-6 Flex Cable Gerber File | 2 | Signed-Off | 2004-06-25 | Auth for Flight Prod | 2004-07-26 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
109 | 6 | LAT-DS-00334 |  | LAT-DS-02049 | Dwg | EE | Readout Flex Cable Schematic | 5 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | 4 | LAT-DS-02383 | 2 | LAT-DS-03031 | Dwg | PF | Cable Stiffener | 2 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 | 5 | LAT-DS-03031 |  | LAT-DS-03037 | Dwg | EE | Flex Cable Stiffener Gerber File | 1 | Obsolete | 2004-05-27 | 0 | 2004-06-08 | Not used | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
112 | 4 | LAT-DS-02383 | 3 | IPC-4203/18OOXMX |  | MT | Acrylic Adhesive, 0.001" Thk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
113 | 4 | LAT-DS-02383 | 4 | LAT-DS-03040 | Dwg | PF | Connector Adhesive Preform | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
114 | 4 | LAT-DS-02383 | 5 | Omnetics A8486-001 |  | EE | Nano-Connector Plug, 37-Pin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
115 | 4 | LAT-DS-02383 | 6 | Cristek MCR-2051-2B1 |  | EE | Micro-D Connector Plug, 51-Pin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
116 | 4 | LAT-DS-02383 | 7 | YSI S-311-P18-09S7R6 |  | EE | Thermistor, 30K | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 | 4 | LAT-DS-02383 | 8 | M55342M02B100DR |  | EE | Resistor, 100 Ohm 1%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41333 | 6020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
118 | 4 | LAT-DS-02383 | 9 | M55342M02B200DR |  | EE | Resistor, 200 Ohm 1%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
119 | 4 | LAT-DS-02383 | 10 | M55342M02B39K0R |  | EE | Resistor, 39K-Ohm 5%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41333 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | 4 | LAT-DS-02383 | 11 | Hysol EA 9394 |  | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2004-03-16 | 47130 | 25 ea. 50 ml | N/A | N/A | 2003-06-16 | 0 | 0 | 0 | 0 | 0
121 | 4 | LAT-DS-02383 | 12 | IPC/EIA-J-STD-006A |  | MT | SN63 PB37 Solder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
122 | 2 | LAT-DS-00722 |  | LAT-DS-03190 | Dwg | SA | C-7 Bent Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
123 | 3 | LAT-DS-03190 |  | LAT-DS-02384 | Dwg | SA | C-7 Flat Assembly | 2 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
124 | 4 | LAT-DS-02384 | 1 | LAT-DS-00729 | Dwg | PF | C-7 PWB Master Layout | 6 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
125 | 5 | LAT-DS-00729 |  | LAT-DS-00341 | Dwg | EE | C-7 Flex Cable Gerber File | 2 | Signed-Off | 2004-06-25 | Auth for Flight Prod | 2004-07-26 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
126 | 6 | LAT-DS-00334 |  | LAT-DS-02049 | Dwg | EE | Readout Flex Cable Schematic | 5 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
127 | 4 | LAT-DS-02384 | 2 | LAT-DS-03031 | Dwg | PF | Cable Stiffener | 2 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
128 | 5 | LAT-DS-03031 |  | LAT-DS-03037 | Dwg | EE | Flex Cable Stiffener Gerber File | 1 | Obsolete | 2004-05-27 | 0 | 2004-06-08 | Not used | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
129 | 4 | LAT-DS-02384 | 3 | IPC-4203/18OOXMX |  | MT | Acrylic Adhesive, 0.001" Thk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
130 | 4 | LAT-DS-02384 | 4 | LAT-DS-03040 | Dwg | PF | Connector Adhesive Preform | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
131 | 4 | LAT-DS-02384 | 5 | Omnetics A8486-001 |  | EE | Nano-Connector Plug, 37-Pin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
132 | 4 | LAT-DS-02384 | 6 | Cristek MCR-2051-2B1 |  | EE | Micro-D Connector Plug, 51-Pin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
133 | 4 | LAT-DS-02384 | 7 | YSI S-311-P18-09S7R6 |  | EE | Thermistor, 30K | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
134 | 4 | LAT-DS-02384 | 8 | M55342M02B100DR |  | EE | Resistor, 100 Ohm 1%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41333 | 6020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
135 | 4 | LAT-DS-02384 | 9 | M55342M02B200DR |  | EE | Resistor, 200 Ohm 1%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
136 | 4 | LAT-DS-02384 | 10 | M55342M02B39K0R |  | EE | Resistor, 39K-Ohm 5%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41333 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
137 | 4 | LAT-DS-02384 | 11 | Hysol EA 9394 |  | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2004-03-16 | 47130 | 25 ea. 50 ml | N/A | N/A | 2003-06-16 | 0 | 0 | 0 | 0 | 0
138 | 4 | LAT-DS-02384 | 12 | IPC/EIA-J-STD-006A |  | MT | SN63 PB37 Solder | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
139 | Ladder Assembly | bar: 2 to 25
140 | 3 |  |  | LAT-DS-00594 | Dwg | SA | Ladder Assembly | 2 | Signed Off | 2002-09-05 | Auth for Flight Prod | 2004-05-25 | Fab'ing to obsolete drawing; revision underway | 0 | 0 | 0 | 0 | INFN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
141 | 4 | LAT-DS-00594 | 1 | LAT-DS-00026 | Dwg | PF | GLAST 2000 SSD | 2 | Signed-Off | 2002-09-17 | Auth for Flight Prod | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
142 | 4 | LAT-DS-00594 | 2 | 3M 2216 B/A Grey |  | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 2004-05-03 | 0 | 0 | 0 | 0 | 0 | INFN/Plyform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
143 | 4 | LAT-DS-00594 | 3 | Al 99%, Si 1% |  | MT | Bond Wire 25 micron diam | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 | 4 | LAT-DS-00594 | 4 | Nusil CV-1142 |  | MT | Non-Slumping RTV Silicone | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-16 | 42374 | 7 ea. 6 oz. Tubes | N/A | N/A | 2003-06-16 | 0 | 0 | 0 | 0 | 0
145 | 4 | LAT-DS-00594 | 5 | NuSil CV-2500 |  | MT | Silicone Encapsulant | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
146 | Bias Circuit Assembly | bar: 2 to 25
147 | 3 | LAT-DS-00148 |  | LAT-DS-00192 | Dwg | PF | Bias Circuit Assembly | 8 | Signed-Off | 2004-04-06 | Auth for Flight Prod | 2004-05-07 | 0 | Yes | 0 | 0 | 0 | 0 | 2004-03-30 | 48422 | 800 & 50 | 648 | 0.24 | 3/26/04 (42) | 2004-03-26 | 66503 | TBD | 0 | 0
148 | 4 | LAT-DS-00192 |  | LAT-DS-00277 | Dwg | PF | Bias Plane Board | 6 | Signed-Off | 2004-02-26 | Auth for Flight Prod | 0 | 0 | Yes | N/A | N/A | N/A | SLAC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
149 | TMCM Assemblies | bar: 2 to 25
150 | 3 | LAT-DS-00051 | 3 | LAT-DS-00898 | Dwg | SA | Short TMCM Assembly | 10 | Signed Off | 2004-06-23 | Auth for Flight Prod | 2004-07-26 | 0 | Yes | 0 | 0 | 0 | SLAC | 2004-03-31 | 48017 | 578 | 576 | 0 | 0 | 0 | 0 | 0 | 0 | 0
151 | 4 | LAT-DS-00898 | 1 | LAT-DS-00077 | Dwg | PF | Short MCM PWB | 10 | Signed-Off | 2004-03-16 | Auth for Flight Prod | 2004-05-07 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-31 | 42710 | 770 | 576 | 0.26 | N/A | N/A | N/A | N/A | 0 | 0
152 | 5 | LAT-DS-00077 |  | LAT-DS-00133 | Dwg | EE | Short MCM PWB Gerber | 4 | Signed-Off | 2004-01-26 | Auth for Flight Prod | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
153 | 5 | LAT-DS-00077 |  | LAT-DS-00130 | Dwg | SA | TMCM Schematic | 2 | Signed Off | 2003-09-12 | Auth for Flight Prod | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
154 | 4 | LAT-DS-00898 | 2 | LAT-DS-00370 | Dwg | PF | Pitch Adapter | 7 | Signed Off | 2004-05-27 | Auth for Flight Prod | 2004-06-08 | New rev released to improve production yield | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
155 | 5 | LAT-DS-00370 |  | LAT-DS-01641 | Dwg | EE | Pitch Adapter Gerber | 2 | Signed-Off | 2004-06-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
156 | 4 | LAT-DS-00898 | 3 | LAT-DS-00389 | Dwg | EE | GTFE IC | 2 | Signed-Off | 2003-01-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
157 | 5 | LAT-DS-00389 |  | LAT-DS-00811 | Dwg | EE | GTFE IC Schematic | 1 | Signed-Off | 2003-03-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
158 | 4 | LAT-DS-00898 | 4 | Omnetics A8485-001 |  | EE | Connector Receptacle, 37 pin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 40836 | 1682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
159 | 4 | LAT-DS-00898 | 5 | LAT-DS-00893 | Dwg | EE | GTRC IC | 2 | Signed-Off | 2003-03-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
160 | 5 | LAT-DS-00893 |  | LAT-DS-00813 | Dwg | EE | GTRC IC VHDL | 7 | Signed-Off | 2003-11-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
161 | 4 | LAT-DS-00898 | 6 | CDR01BX332 BKSR TM |  | EE | CAP, 3.3NF, 100V, AVNET | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41710 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
162 | 4 | LAT-DS-00898 | 7 | CWR09CC475KBB/TR |  | EE | CAP 4.7uF, 4V VISHAY SPRAGUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 42197 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
163 | 4 | LAT-DS-00898 | 8 | 1210B563K251YHTM |  | EE | CAP 56NF, 250V, NOVACAP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 470946 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
164 | 4 | LAT-DS-00898 | 9 | SMDC014-2 |  | EE | POLYSWITCH 0.3 AMP, TYCO/RAYCHEM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41429 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
165 | 4 | LAT-DS-00898 | 10 | H0505CPX000 |  | EE | RES, 0 OHMS, 5%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41333 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
166 | 4 | LAT-DS-00898 | 11 | M55342M02B12K0R |  | EE | RES, 12K 5%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41333 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
167 | 4 | LAT-DS-00898 | 12 | M55342M02B39K0R |  | EE | Resistor, 39K-Ohm 5%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41333 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
168 | 4 | LAT-DS-00898 | 13 | M55342M02B100DR |  | EE | Resistor, 100 Ohm 1%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41333 | 6020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
169 | 4 | LAT-DS-00898 | 14 | TELEDYNE #7261685-1 |  | MT | HYSOL FP4451, DIE ENCAPSULANT DAM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Teledyne | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
170 | 4 | LAT-DS-00898 | 15 | D55342M07B270KR |  | EE | RES, 270K 5%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41333 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
171 | 4 | LAT-DS-00898 | 16 | M55342M02B680KR |  | EE | RES, 680K 5%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41333 | 32600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
172 | 4 | LAT-DS-00898 | 17 | CWR09CC685KBB/TR |  | EE | CAP, 6.8UF, 4V, VISHAY SPRAGUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 42197 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
173 | 4 | LAT-DS-00898 | 18 | NAS723CE100-120 |  | PP | M1X0.25 X 0.120" LG FLAT HD CS, SST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
174 | 4 | LAT-DS-00898 | 19 | Al 99%, Si 1% |  | MT | Bond Wire 25 micron diam | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
175 | 4 | LAT-DS-00898 | 20 | TELEDYNE #7261679-1 |  | MT | SCOTCHWELD 1838 B/A, EPOXY, GREEN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Teledyne | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
176 | 4 | LAT-DS-00898 | 21 | TELEDYNE #7261693-1 |  | MT | HYSOL FP4450, DIE ENCAPSULANT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Teledyne | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
177 | 4 | LAT-DS-00898 | 22 | TELEDYNE #7258290 |  | MT | EPO-TEK H20E, DIE ATTACH, EPOXY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Teledyne | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
178 | 4 | LAT-DS-00898 | 23 | TELEDYNE #7506502 |  | MT | SOLDER WIRE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Teledyne | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
179 | 4 | LAT-DS-00898 | 25 | TELEDYNE #7506598 |  | MT | SN62, SOLDER PASTE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Teledyne | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
180 | 4 | LAT-DS-00898 | 26 | OMNETICS A8597-001 |  | EE | CONNECTOR SAVER, 37 PIN | 0 | 0 | 0 | 0 | 0 | EGSE, not flight | 0 | 0 | 0 | 0 | SLAC | 0 | 40836 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
181 | 4 | LAT-DS-00898 | 27 | TELEDYNE #7261633 & TELEDYNE #7261638 |  | MT | HUMISEAL 1A2O, CONFORMAL COATING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Teledyne | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
182 | 4 | LAT-DS-00898 | 28 | LAT-DS-00543 | Dwg | EE | TMCM STORAGE BASE | 2 | Signed-Off | 2004-04-04 | Auth for Flight Prod | 2004-07-22 | MGSE, not flight | 0 | 0 | 0 | 0 | SLAC | 0 | 38857 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
183 | 4 | LAT-DS-00898 | 29 | LAT-DS-00544 | Dwg | EE | TMCM STORAGE COVER | 2 | Signed-Off | 2004-04-04 | Auth for Flight Prod | 2004-07-22 | MGSE, not flight | 0 | 0 | 0 | 0 | SLAC | 0 | 38857 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
184 | 4 | LAT-DS-00898 | 30 | BN7.16C40SHC/912 |  | PP | M1.6 X 0.45 X 4 MM SHCS ALLOY STL 12.9 | 0 | 0 | 0 | 0 | 0 | MGSE, not flight | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
185 | 3 | LAT-DS-00747 |  | LAT-DS-00899 | Dwg | SA | Tall TMCM Assembly | 9 | Signed Off | 2004-06-23 | Auth for Flight Prod | 2004-07-26 | 0 | Yes | 0 | 0 | 0 | SLAC | 2004-03-31 | 48017 | 60 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186 | 4 | LAT-DS-00899 | 1 | LAT-DS-00368 | Dwg | PF | Tall MCM PWB | 8 | Signed-Off | 2004-03-16 | Auth for Flight Prod | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 2004-03-31 | 42710 | 85 | 72 | 0.16 | N/A | N/A | N/A | N/A | 0 | 0
187 | 5 | LAT-DS-00899 |  | LAT-DS-01984 | Dwg | PF | Tall MCM PWB Gerber Files | 4 | Signed Off | 2004-01-24 | Auth for Flight Prod | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
188 | 5 | LAT-DS-00899 |  | LAT-DS-00130 | Dwg | SA | TMCM Schematic | 2 | Signed Off | 2003-09-12 | Auth for Flight Prod | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
189 | 4 | LAT-DS-00899 | 2 | LAT-DS-00370 | Dwg | PF | Pitch Adapter | 7 | Signed Off | 2004-05-27 | Auth for Flight Prod | 2004-06-08 | New rev released to improve production yield | Yes | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
190 | 4 | LAT-DS-00899 | 3 | LAT-DS-00389 | Dwg | EE | GTFE IC | 2 | Signed-Off | 2003-01-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
191 | 4 | LAT-DS-00899 | 4 | Omnetics A8485-001 |  | EE | Connector Receptacle, 37 pin | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 40836 | 1682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
192 | 4 | LAT-DS-00899 | 5 | LAT-DS-00893 | Dwg | EE | GTRC IC | 2 | Signed-Off | 2003-03-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
193 | 4 | LAT-DS-00899 | 6 | CDR01BX332 BKSR TM |  | EE | CAP, 3.3NF, 100V, AVNET | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41710 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
194 | 4 | LAT-DS-00899 | 7 | CWR09CC475KBB/TR |  | EE | CAP 4.7uF, 4V VISHAY SPRAGUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 42197 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
195 | 4 | LAT-DS-00899 | 8 | 1210B563K251YHTM |  | EE | CAP 56NF, 250V, NOVACAP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 470946 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
196 | 4 | LAT-DS-00899 | 9 | SMDC014-2 |  | EE | POLYSWITCH 0.3 AMP, TYCO/RAYCHEM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41429 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
197 | 4 | LAT-DS-00899 | 10 | H0505CPX000 |  | EE | RES, 0 OHMS, 5%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41333 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
198 | 4 | LAT-DS-00899 | 11 | M55342M02B12K0R |  | EE | RES, 12K 5%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41333 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
199 | 4 | LAT-DS-00899 | 12 | M55342M02B39K0R |  | EE | Resistor, 39K-Ohm 5%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41333 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200 | 4 | LAT-DS-00899 | 13 | M55342M02B100DR |  | EE | Resistor, 100 Ohm 1%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41333 | 6020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201 | 4 | LAT-DS-00899 | 14 | TELEDYNE #7261685-1 |  | MT | HYSOL FP4451, DIE ENCAPSULANT DAM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Teledyne | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
202 | 4 | LAT-DS-00899 | 15 | D55342M07B270KR |  | EE | RES, 270K 5%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41333 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
203 | 4 | LAT-DS-00899 | 16 | M55342M02B680KR |  | EE | RES, 680K 5%, SOTA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 41333 | 32600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | 4 | LAT-DS-00899 | 17 | CWR09CC685KBB/TR |  | EE | CAP, 6.8UF, 4V, VISHAY SPRAGUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 42197 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
205 | 4 | LAT-DS-00899 | 18 | NAS723CE100-120 |  | PP | M1X0.25 X 0.120" LG FLAT HD CS, SST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
206 | 4 | LAT-DS-00899 | 19 | Al 99%, Si 1% |  | MT | Bond Wire 25 micron diam | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
207 | 4 | LAT-DS-00899 | 20 | TELEDYNE #7261679-1 |  | MT | SCOTCHWELD 1838 B/A, EPOXY, GREEN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Teledyne | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
208 | 4 | LAT-DS-00899 | 21 | TELEDYNE #7261693-1 |  | MT | HYSOL FP4450, DIE ENCAPSULANT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Teledyne | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
209 | 4 | LAT-DS-00899 | 22 | TELEDYNE #7258290 |  | MT | EPO-TEK H20E, DIE ATTACH, EPOXY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Teledyne | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
210 | 4 | LAT-DS-00899 | 23 | TELEDYNE #7506502 |  | MT | SOLDER WIRE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Teledyne | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
211 | 4 | LAT-DS-00899 | 25 | TELEDYNE #7506598 |  | MT | SN62, SOLDER PASTE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Teledyne | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212 | 4 | LAT-DS-00899 | 26 | OMNETICS A8597-001 |  | EE | CONNECTOR SAVER, 37 PIN | 0 | 0 | 0 | 0 | 0 | EGSE, not flight | 0 | 0 | 0 | 0 | SLAC | 0 | 40836 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
213 | 4 | LAT-DS-00899 | 27 | TELEDYNE #7261633 & TELEDYNE #7261638 |  | MT | HUMISEAL 1A2O, CONFORMAL COATING | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Teledyne | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
214 | 4 | LAT-DS-00899 | 28 | LAT-DS-00543 | Dwg | EE | TMCM STORAGE BASE | 2 | Signed-Off | 2004-04-04 | Auth for Flight Prod | 2004-07-22 | MGSE, not flight | 0 | 0 | 0 | 0 | SLAC | 0 | 38857 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
215 | 4 | LAT-DS-00899 | 29 | LAT-DS-00544 | Dwg | EE | TMCM STORAGE COVER | 2 | Signed-Off | 2004-04-04 | Auth for Flight Prod | 2004-07-22 | MGSE, not flight | 0 | 0 | 0 | 0 | SLAC | 0 | 38857 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 4 | LAT-DS-00899 | 30 | BN7.16C40SHC/912 |  | PP | M1.6 X 0.45 X 4 MM SHCS ALLOY STL 12.9 | 0 | 0 | 0 | 0 | 0 | MGSE, not flight | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 4. Mech GSE Parts Tree
|  | 2. Tracker Mechanical Ground Support Equipment | [7 empty] | Updated: | 2004-09-30 | Printed: | 2004-09-30 16:04
[10 empty] | Document Status from LAT Docs | [5 empty] | H'Ware Need Dates |  |  |  |  | H'Ware Order Status |  |  |  | Shipping Status |  |  | Disposition
# | Lvl | Next Assy | BOM # | Doc / Part # | Dwg Link | Type | Title / Description | Rev | Status | Release Date | Work Authorization | Status Date | Disposition/Comments/Date | Flt Dsn | Status Date | at SLAC | at INFN | Supplied by | Status Date | SLAC P.O. # | Quantity Ordered | Qty Needed | Spares | Rec'd at SLAC | Ship Date | Shipper # | Rec'd at INFN | Work Order # | NCR (if any)
1 |  |  |  | 1 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
2 | TKR Ground Configuration Assembly
3 |  |  |  | LAT-DS-04435 | Dwg | SA | TKR Ground Configuration Ass'y | 1 | Signed-Off | 2004-09-29 | Auth for Flight Prod | 2004-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | LAT-DS-04435 | 1 | LAT-DS-04434 | Dwg | SA | Base Plate + Tracker Ass'y | 1 | Signed-Off | 2004-09-15 | Auth for Flight Prod | 2004-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 |  | LAT-DS-04434 | 1 | LAT-DS-00722 | Dwg | SA | Tracker Module Assembly | 2 | Signed-Off | 2004-09-29 | Auth for Flight Prod | 2004-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | LAT-DS-04434 | 2 | LAT-DS-03673 | Dwg | PF | Tower Base Plate Assembly | 2 | Signed-Off | 2004-07-22 | Auth for Flight Prod | 2004-09-07 | Dwg released | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | LAT-DS-03673 | 1 | LAT-DS-00681 | Dwg | PF | Tower Base Plate | 10 | Signed-Off | 2004-07-26 | Auth for Flight Prod | 2004-09-07 | Dwg released | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | LAT-DS-03673 | 2 | MC 8481A34 | Dwg | MP | 0.5" Tooling Ball, 0.25" Shank | 0 | 0 | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 |  | LAT-DS-03673 | 3 | 1084-12CN300 | Dwg | MP | Heli-Coil M12x1.75x30 LG, 300 SS | 0 | 0 | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 470946 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | LAT-DS-03673 | 4 | LAT-DS-03551 | Dwg | PF | Square Nut, Grid | 3 | Signed-Off | 2004-07-26 | Auth for Flight Prod | 2004-09-07 | Updated rev into parts list | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 |  | LAT-DS-03673 | 5 | MS51029-105 | Dwg | MP | 4-40 UNC-2Ax.37" lg CRES flat pt SHSS | 0 | 0 | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 |  | LAT-DS-03673 | 6 | LAT-DS-02794 | Dwg | PF | Tracker Interface Bushing | 3 | Signed-Off | 2004-05-18 | Auth for Flight Prod | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 |  | LAT-DS-03673 | 7 | 3M 2216 B/A Grey | Dwg | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 2004-05-03 | 0 | 0 | 0 | 0 | 0 | INFN/Plyform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 2 | LAT-DS-04434 | 3 | LAT-DS-03965 | Dwg | SA | Reflector Ball Nest Assembly | 1 | Signed-Off | 2002-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 3 | LAT-DS-03965 | 1 | LAT-DS-03966 | Dwg | PF | Reflector Ball Nest | 1 | Signed-Off | 2002-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 3 | LAT-DS-03965 | 2 | LAT-DS-03967 | Dwg | PF | Nest Magnet | 1 | Signed-Off | 2002-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 3 | LAT-DS-03965 | 3 | MC 98394A437 | Dwg | MP | 20 Diam x 1 Int Retain Ring, PH15-7 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 3 | LAT-DS-03965 | 4 | Hysol EA-934NA | Dwg | MT | Structural Adhesive | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 3 | LAT-DS-03965 | 5 | ISO 7380-A2 M4 | Dwg | MP | M4x0.7x12 LG But Hd CS, 18-8 St Steel, Self-Locking | 0 | 0 | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 |  | LAT-DS-04435 | 2 | LAT-DS-02358 | Dwg | PF | Cable Holding Plate | 2 | Signed-Off | 2004-06-21 | Auth for Flight Prod | 2004-06-24 | OK for fab | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 |  | LAT-DS-04435 | 3 | AMS 5732H M12 SHCS | Dwg | MT | M12x1.75x24 Lg SHCS, AMS 5732H A-286 St Steel | 0 | GSFC Approved | 0 | OK to Procure Mat'l | 2004-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 |  | LAT-DS-04435 | 4 | LAT-DS-03825 | Dwg | PF | Connector Mount | 1 | Signed-Off | 2004-06-21 | Auth for Flight Prod | 2004-06-24 | OK for fab | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 |  | LAT-DS-04435 | 5 | DIN 912-A2 M4 | Dwg | MP | M4x0.7x12 LG SHCS, 18-8 St Steel, Self-Lock | 0 | 0 | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 |  | LAT-DS-04435 | 6 | LAT-DS-04730 | Dwg | PF | Connector Mount Cap | 1 | Signed-Off | 2004-09-24 | Auth for Flight Prod | 2004-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 |  | LAT-DS-04435 | 7 | Cristek M SAV-G-1B | Dwg | EE | Micro-D 51 Pin Connector Saver | 0 | 0 | 0 | OK to Procure Mat'l | 2004-09-30 | 0 | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30
31 | TKR Shipping Configuration Assembly
32 |  |  |  | LAT-DS-04009 | Dwg | SA | TKR Shipping Configuration Ass'y | 1 | Signed-Off | 2004-09-20 | Auth for Flight Prod | 2004-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 |  | LAT-DS-04009 | 1 | LAT-DS-04435 | Dwg | SA | TKR Ground Configuration Ass'y | 1 | Signed-Off | 2004-09-29 | Auth for Flight Prod | 2004-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 |  | LAT-DS-04009 | 2 | LAT-DS-03947 | Dwg | PF | Bottom Cover Plate | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 |  | LAT-DS-04009 | 3 | LAT-DS-03945 | Dwg | PF | Left-Hand Corner Post | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 |  | LAT-DS-04009 | 4 | LAT-DS-03946 | Dwg | PF | Right-Hand Corner Post | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 |  | LAT-DS-04009 | 5 | LAT-DS-03943 | Dwg | PF | X-Side Container Wall | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 |  | LAT-DS-04009 | 6 | LAT-DS-03944 | Dwg | PF | Y-Side Container Wall | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 |  | LAT-DS-04009 | 7 | LAT-DS-03948 | Dwg | PF | Top Cover Plate | 2 | Signed-Off | 2004-08-18 | Auth for Flight Prod | 2004-09-07 | Update released w/Datalogger holes | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 |  | LAT-DS-04009 | 8 | DIN 912-A2 M5x12 | Dwg | MP | M5x0.8x12 LG SHCS, 18-8 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 |  | LAT-DS-04009 | 9 | CLM-34314-SHR | Dwg | PP | M10x1.5x26lg Hoist Ring, Alloy Steel | 0 | 0 | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 |  | LAT-DS-04009 | 10 | DIN 912-A2 M10 | Dwg | MP | M10x1.5x25 LG SHCS, 18-8 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 |  | LAT-DS-04009 | 11 | MC 3112T13 | Dwg | PP | M10x1.5 Eye Nut Steel Zinc Plated | 0 | 0 | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 |  | LAT-DS-04009 | 12 | Madge Tech Ultrashock-EB | Dwg | PP | Shock, Temp, Pressure, and Humidity Data Logger | 0 | GSFC Pending | 0 | OK to Procure Mat'l | 2004-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 |  | LAT-DS-04009 | 13 | DIN 125 M10 | Dwg | PP | M10 Flat Washer x 20OD, 18-8 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 |  | LAT-DS-04009 | 14 | DIN 127B M10 | Dwg | PP | M10 Lock Washer x 2 Thk, 18-8 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 |  | LAT-DS-04009 | 15 | CL 92871A078 | Dwg | PP | Spacer, 10 ODx4.3IDx10Lg, 18-8 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 2004-09-07 | Added to parts list | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 |  | LAT-DS-04009 | 16 | DIN 912-A2 M4x20 | Dwg | MP | M4x0.7x12 LG SHCS, 18-8 St Steel, Self-Lock | 0 | 0 | 0 | OK to Procure Mat'l | 2004-09-07 | Added to parts list | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 |  | LAT-DS-04009 | 17 | DIN 125 M5 | Dwg | PP | M5 Flat Washer x 10OD, 18-8 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 |  | LAT-DS-04009 | 18 | DIN 125 M4 | Dwg | PP | M4 Flat Washer x 9OD, 18-8 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 |  | LAT-DS-04009 | 19 | LAT-DS-04586 | Dwg | PF | Inner Ship Container Sidewall Shim | 1 | Signed-Off | 2004-09-20 | Auth for Flight Prod | 2004-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 |  | LAT-DS-04009 | 20 | 3M 70-0060-4256-1 | Dwg | MT | Adhesive Transfer Tape 966 Clear, 1" W x 0.002" Thk | 0 | GSFC Pending | 0 | OK to Procure Mat'l | 2004-09-07 | 0 | 0 | 0 | 0 | 0 | INFN/Plyform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 |  | LAT-DS-04009 | 21 | MIL-D-3464E | Dwg | PP | 12 Units Silica Gel Dessicant in Tyvek Bag | 0 | GSFC Pending | 0 | OK to Procure Mat'l | 2004-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 |  | LAT-DS-04009 | 22 | Kapton Tape | Dwg | MT | Kapton Tape w/Acrylic Adhesive, 1" W x 0.002" Thk | MT | GSFC Pending | 0 | OK to Procure Mat'l | 2004-09-07 | Added to parts list | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 |  | LAT-DS-04009 | 23 | LAT-DS-04010 | Dwg | PF | Outer Shipping Container SCD | 1 | Signed-Off | 2004-08-17 | Auth for Flight Prod | 2004-09-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 |  | LAT-DS-04009 | 24 | MIL-PRF-81705D Type III | Dwg | MT | Static Shield Sheet, 0.003" Nom Thk | 0 | GSFC Pending | 0 | OK to Procure Mat'l | 2004-09-07 | Added to parts list | 0 | 0 | 0 | 0 | SLAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 |  | LAT-DS-04009 | 25 | ANSI/ESD 554/511.31 | Dwg | MT | Anti-Static Tape, 0.002" Nom Thk | 0 | GSFC Pending | 0 | OK to Procure Mat'l | 2004-09-07 | Added to parts list | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58
59 |  |  |  | LAT-DS-03949 | Dwg | SA | Inner Shipping Container Assembly | 1 | Signed-Off | 2004-09-20 | Auth for Flight Prod | 2004-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 |  | LAT-DS-03949 | 1 | LAT-DS-03826 | Dwg | SA | Cable Holding Plate Assembly | 2 | Signed-Off | 2004-09-29 | Auth for Flight Prod | 2004-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 |  | LAT-DS-03826 | 1 | LAT-DS-02358 | Dwg | PF | Cable Holding Plate | 2 | Signed-Off | 2004-06-21 | Auth for Flight Prod | 2004-06-24 | OK for fab | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 |  | LAT-DS-03826 | 2 | LAT-DS-03825 | Dwg | PF | Connector Mount | 1 | Signed-Off | 2004-06-21 | Auth for Flight Prod | 2004-06-24 | OK for fab | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 |  | LAT-DS-03826 | 3 | DIN 912-A2 M4 | Dwg | MP | M4x0.7x12 LG SHCS, 18-8 St Steel, Self-Lock | 0 | 0 | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 |  | LAT-DS-03826 | 4 | DIN 914/ISO 4027 M3 | Dwg | MP | M3x0.5x4 LG SHSS Cone End, 18-8 St Steel, Self-Lock | 0 | 0 | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 |  | LAT-DS-03949 | 2 | LAT-DS-03947 | Dwg | PF | Bottom Cover Plate | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 |  | LAT-DS-03949 | 3 | LAT-DS-03945 | Dwg | PF | Left-Hand Corner Post | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 |  | LAT-DS-03949 | 4 | LAT-DS-03946 | Dwg | PF | Right-Hand Corner Post | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 |  | LAT-DS-03949 | 5 | LAT-DS-03943 | Dwg | PF | X-Side Container Wall | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 |  | LAT-DS-03949 | 6 | LAT-DS-03944 | Dwg | PF | Y-Side Container Wall | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 |  | LAT-DS-03949 | 7 | LAT-DS-03948 | Dwg | PF | Top Cover Plate | 2 | Signed-Off | 2004-08-18 | Auth for Flight Prod | 2004-09-07 | Update released w/Datalogger holes | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 |  | LAT-DS-03949 | 8 | DIN 912-A2 M5 | Dwg | MP | M5x0.8x12 LG SHCS, 18-8 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 |  | LAT-DS-03949 | 9 | DIN 125 M5 | Dwg | PP | M5 Flat Washer x 10OD, 18-8 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 |  | LAT-DS-03949 | 10 | CLM-34314-SHR | Dwg | PP | M10x1.5x26lg Hoist Ring, Alloy Steel | 0 | 0 | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 |  | LAT-DS-03949 | 11 | MC 3112T13 | Dwg | PP | M10x1.5 Eye Nut Steel Zinc Plated | 0 | 0 | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 |  | LAT-DS-03949 | 12 | DIN 912-A2 M10 | Dwg | MP | M10x1.5x25 LG SHCS, 18-8 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 |  | LAT-DS-03949 | 13 | DIN 125 M10 | Dwg | PP | M10 Flat Washer x 20OD, 18-8 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 |  | LAT-DS-03949 | 14 | DIN 127B M10 | Dwg | PP | M10 Lock Washer x 2 Thk, 18-8 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 |  | LAT-DS-03949 | 15 | LAT-DS-04225 | Dwg | PF | Inr Ship Container Proof Test Plate | 1 | Obsolete | 0 | 0 | 2004-09-30 | Not used | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79
80 | TKR Thermal-Vacuum Test Configuration Assembly
81 |  |  |  | LAT-DS-04007 | Dwg | SA | TKR T-Vac Test Configuration Ass'y | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 |  | LAT-DS-04007 |  | LAT-DS-04434 | Dwg | SA | Base Plate + Tracker Ass'y | 1 | Signed-Off | 2004-09-15 | Auth for Flight Prod | 2004-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83
84 | TKR Lifting Fixture Assembly
85 |  | LAT-DS-04008 | 2 | LAT-DS-03618 | Dwg | SA | Tower Lifting Fixture Assembly | 1 | Signed-Off | 2004-07-23 | Auth for Flight Prod | 2004-07-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 |  | LAT-DS-03618 | 1 | LAT-DS-03619 | Dwg | PF | Lifting Plate | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 |  | LAT-DS-03618 | 2 | MC 92290A242 | Dwg | MP | M5x0.8x20 Lg SHCS, 316 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 2004-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 |  | LAT-DS-03618 | 3 | LAT-DS-03620 | Dwg | PF | Flexure | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 |  | LAT-DS-03618 | 4 | MC 90965A170 | Dwg | MP | M6x12 OD Flat Washer, 316 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 2004-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 |  | LAT-DS-03618 | 5 | MC 3155T13 | Dwg | MP | M12 Eye Nut, Forged 316 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 2004-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 |  | LAT-DS-03618 | 6 | MC 90278A328 | Dwg | MP | 5x10 Lg SH Shoulder Scr, 18-8 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 2004-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 |  | LAT-DS-03618 | 7 | MC 3174T11 | Dwg | MP | M8 Eye Nut, Forged 316 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 2004-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 |  | LAT-DS-03618 | 8 | MC 92290A624 | Dwg | MP | M12x1.75 x 40 Lg SHCS, 316 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 2004-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 |  | LAT-DS-03618 | 9 | LAT-DS-04128 | Dwg | PF | Weight Rod | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 |  | LAT-DS-03618 | 10 | LAT-DS-04127 | Dwg | PF | Weight | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 |  | LAT-DS-03618 | 11 | MC 94150A345 | Dwg | MP | M6x1 Hex Nut, 316 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 2004-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 |  | LAT-DS-03618 | 12 | MC 92290A442 | Dwg | MP | M8x1.25 x 40 Lg SHCS, 316 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 2004-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 |  | LAT-DS-03618 | 13 | MC 90965A160 | Dwg | MP | M5x10 OD Flat Washer, 316 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 2004-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 |  | LAT-DS-03618 | 14 | MC 90965A190 | Dwg | MP | M8x16 OD Flat Washer, 316 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 2004-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 |  | LAT-DS-03618 | 15 | MC 92148A200 | Dwg | MP | M8x2 Thk Lock Washer, 316 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 2004-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 |  | LAT-DS-03618 | 16 | MC 90965A210 | Dwg | MP | M12x24 OD Flat Washer, 316 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 2004-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 |  | LAT-DS-03618 | 17 | MC 92153A436 | Dwg | MP | M12x2.5 Thk Lock Washer, 316 St Steel | 0 | 0 | 0 | OK to Procure Mat'l | 2004-07-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 |  | LAT-DS-03618 | 18 | LAT-DS-03892 | Dwg | PF | Proof Test Cross Bar | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104
105
106

## 5. Parts List
4. Tracker Parts List |  |  | 0 |  | Updated: | 2004-09-30 | Printed: | 2004-09-30 16:04
[5 empty] | Document Status from LAT Docs | [5 empty] | H'Ware Need Dates |  |  |  |  | H'Ware Order Status |  |  |  | Shipping Status |  |  | Disposition
Doc/Part # | T | Title / Description | Rev | Status | Release Date | Work Authorization | Status Date | Disposition/Comments/Date | OK for Flight | Status Date | at SLAC | at INFN | Supplied by | Status Date | SLAC P.O. # | Quantity Ordered | Qty Needed | Spares | Rec'd at SLAC | Ship Date | Shipper # | Rec'd at INFN | Work Order # | NCR (if any)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
1084-12CN300 | MP | Heli-Coil M12x1.75x30 LG, 300 SS |  |  |  | OK to Procure Mat'l | [6 empty] | SLAC |  | 470946 | 7000
1210B563K251YHTM | EE | CAP 56NF, 250V, NOVACAP | [10 empty] | SLAC |  | 470946 | 7000
3M 2216 B/A Grey | MT | Structural Adhesive |  | GSFC Approved |  | OK to Procure Mat'l | 2004-05-03 | [5 empty] | INFN/Plyform
3M 70-0060-4256-1 | MT | Adhesive Transfer Tape 966 Clear, 1" W x 0.002" Thk |  | GSFC Pending |  | OK to Procure Mat'l | 2004-09-07 | [5 empty] | INFN/Plyform
A 286 CRES | PP | A 286 CRES |  | GSFC Approved |  | OK to Procure Mat'l
AEROGLAZE 9924 | MT | Primer for Z 306 Paint |  | GSFC Approved |  | OK to Procure Mat'l | [6 empty] | SLAC | 2004-03-16 | 45276 | 8 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A
AEROGLAZE 9958 | MT | Thinner for Z 306 Paint |  | GSFC Approved |  | OK to Procure Mat'l | [6 empty] | SLAC | 2004-03-16 | 45276 | 4 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A
AEROGLAZE Z306 | MT | Black Polyurethane Paint |  | GSFC Approved |  | OK to Procure Mat'l | [6 empty] | SLAC | 2004-03-16 | 45276 | 8 Pints | N/A | N/A | Drop Ship | 2003-10-20 | N/A
Al 99%, Si 1% | MT | Bond Wire 25 micron diam |  | GSFC Approved |  | OK to Procure Mat'l
Allcomp 3D Carbon-Carbon | MT | Tray Closeouts |  | GSFC Pending |  | OK to Procure Mat'l |  |  | Yes
AMS 5732H | MT | AMS 5732H CRES A 286 |  | GSFC Approved |  | OK to Procure Mat'l
AMS 5732H M12 SHCS | MT | M12x1.75x24 Lg SHCS, AMS 5732H A-286 St Steel |  | GSFC Approved |  | OK to Procure Mat'l | 2004-09-30
AMS 5735 | PP | CRES A 286 MJ2.5 x 0.45 x 8mm 120 Deg. Flush Head Torx-Plus |  | GSFC Approved |  | OK to Procure Mat'l
AMS-T-9046/9047 | MT | 6Al4V Titanium |  | GSFC Approved |  | OK to Procure Mat'l
ANSI/ESD 554/511.31 | MT | Anti-Static Tape, 0.002" Nom Thk |  | GSFC Pending |  | OK to Procure Mat'l | 2004-09-07 | Added to parts list
ASTM A240 | PP | CRES 316 Stainless Steel |  | GSFC Approved |  | OK to Procure Mat'l
ASTM A276 | PP | CRES 316 Stainless Steel |  | GSFC Approved |  | OK to Procure Mat'l
BN7.16C40SHC/912 | PP | M1.6 X 0.45 X 4 MM SHCS ALLOY STL 12.9 | [5 empty] | MGSE, not flight |  |  |  |  | SLAC
Brady B-457 | MT | Labels for I.D. of parts |  | GSFC Approved |  | OK to Procure Mat'l | [6 empty] | SLAC
CAB-O-SIL | MT | Thickening agent |  | GSFC Approved |  | OK to Procure Mat'l
CDR01BX332 BKSR TM | EE | CAP, 3.3NF, 100V, AVNET | [10 empty] | SLAC |  | 41710 | 90000
Chomerics Cho-Foil CCJ | MT | Aluminum Tape (EMI) |  | GSFC Approved |  | OK to Procure Mat'l | [6 empty] | SLAC | 2004-04-22 | 42654 | 10 Rolls | ? | ? | 2004-06-26
CLM-34314-SHR | PP | M10x1.5x26lg Hoist Ring, Alloy Steel |  |  |  | OK to Procure Mat'l
CL 92871A078 | PP | Spacer, 10 ODx4.3IDx10Lg, 18-8 St Steel |  |  |  | OK to Procure Mat'l | 2004-09-07 | Added to parts list
Cristek MCR-2051-2B1 | EE | Micro-D Connector Plug, 51-Pin | [10 empty] | SLAC
Cristek M SAV-G-1B | EE | Micro-D 51 Pin Connector Saver |  |  |  | OK to Procure Mat'l | 2004-09-30 | [5 empty] | SLAC
CWR09CC475KBB/TR | EE | CAP 4.7uF, 4V VISHAY SPRAGUE | [10 empty] | SLAC |  | 42197 | 5500
CWR09CC685KBB/TR | EE | CAP, 6.8UF, 4V, VISHAY SPRAGUE | [10 empty] | SLAC |  | 42197 | 1800
Cytec BR-127 | MT | Corrosion Inhibiting Primer |  | GSFC Approved |  | OK to Procure Mat'l | 2004-05-04 | INFN to check if they have this material |  |  |  |  | SLAC | 2004-04-22 | Credit Card | 1 Gallon | ? | ? | Drop Ship | 2004-10-13 | N/A | ?
D55342M07B270KR | EE | RES, 270K 5%, SOTA | [10 empty] | SLAC |  | 41333 | 3600
DIN 125 M4 | PP | M4 Flat Washer x 9OD, 18-8 St Steel |  |  |  | OK to Procure Mat'l
DIN 125 M5 | PP | M5 Flat Washer x 10OD, 18-8 St Steel |  |  |  | OK to Procure Mat'l
DIN 125 M2.5 | PP | M2.5 Flat Washer x 6OD, 316 St Steel |  |  |  | OK to Procure Mat'l
DIN 125 M10 | PP | M10 Flat Washer x 20OD, 18-8 St Steel |  |  |  | OK to Procure Mat'l
DIN 127B M10 | PP | M10 Lock Washer x 2 Thk, 18-8 St Steel |  |  |  | OK to Procure Mat'l
DIN 912-A2 M10 | MP | M10x1.5x25 LG SHCS, 18-8 St Steel |  |  |  | OK to Procure Mat'l
DIN 912-A2 M2.5 | MP | M2.5x0.45x5 LG SHCS, 18-8 St Steel |  |  |  | OK to Procure Mat'l | 2004-05-31 | Bolt spec'd and OK to procure
DIN 912-A2 M4 | MP | M4x0.7x12 LG SHCS, 18-8 St Steel, Self-Lock |  |  |  | OK to Procure Mat'l
DIN 912-A2 M4x20 | MP | M4x0.7x12 LG SHCS, 18-8 St Steel, Self-Lock |  |  |  | OK to Procure Mat'l | 2004-09-07 | Added to parts list
DIN 912-A2 M5 | MP | M5x0.8x12 LG SHCS, 18-8 St Steel |  |  |  | OK to Procure Mat'l
DIN 912-A2 M5x12 | MP | M5x0.8x12 LG SHCS, 18-8 St Steel |  |  |  | OK to Procure Mat'l
DIN 912-A4 M4 | MP | M4x0.7x25 LG SHCS, 316 St Steel |  |  |  | OK to Procure Mat'l
DIN 912-A4 M4x8 | MP | M4x0.7x8 LG SHCS, 316 St Steel |  |  |  | OK to Procure Mat'l
DIN 914/ISO 4027 M3 | MP | M3x0.5x4 LG SHSS Cone End, 18-8 St Steel, Self-Lock |  |  |  | OK to Procure Mat'l
Epo-Tek E4110-LV | MT | Epo-Tek EP110-LV (now E4110-LV) |  | GSFC Approved |  | OK to Procure Mat'l
Epoxi-Patch Kit 0151 | MT | Adhesive |  | GSFC Approved |  | OK to Procure Mat'l
FM-73M | MT | Film Adhesive |  | GSFC Approved |  | OK to Procure Mat'l
GSFC NA 0069-040018 | MP | M4x0.7x16 LG SHCS, A-286 St Steel |  |  |  | OK to Procure Mat'l | 2004-06-09 | Bolt spec changed to GSFC part
H0505CPX000 | EE | RES, 0 OHMS, 5%, SOTA | [10 empty] | SLAC |  | 41333 | 3600
Hysol 10-105 | MT | Epoxy Ink White |  | GSFC Approved |  | OK to Procure Mat'l
Hysol EA 9323 | MT | Structural Adhesive |  | GSFC Approved |  | OK to Procure Mat'l
Hysol EA 9394 | MT | Structural Adhesive |  | GSFC Approved |  | OK to Procure Mat'l | [7 empty] | 2004-03-16 | 47130 | 25 ea. 50 ml | N/A | N/A | 2003-06-16
Hysol EA9309.2NA |  | Structural Adhesive |  | GSFC Pending | [8 empty] | INFN/Plyform
Hysol EA-934NA | MT | Structural Adhesive |  | GSFC Approved |  | OK to Procure Mat'l
Hysol M-0-N/CAT B-3 | MT | Epoxy Ink Black or White |  | GSFC Approved |  | OK to Procure Mat'l
Hysol M-9-N | MT | Epoxy Ink White |  | GSFC Pending
IPC/EIA-J-STD-006A | MT | SN63 PB37 Solder
IPC-4203/18OOXMX | MT | Acrylic Adhesive, 0.001" Thk
ISO 7380-A2 M2 | MP | M2x0.4x6 LG But Hd CS, 316 St Steel |  |  |  | OK to Procure Mat'l
ISO 7380-A2 M2.5 | MP | M2.5x0.45x2.5 LG But Hd CS, 316 St Steel |  |  |  | OK to Procure Mat'l
ISO 7380-A2 M4 | MP | M4x0.7x12 LG But Hd CS, 18-8 St Steel, Self-Locking |  |  |  | OK to Procure Mat'l
Kapton Tape | MT | Kapton Tape w/Acrylic Adhesive, 1" W x 0.002" Thk | MT | GSFC Pending |  | OK to Procure Mat'l | 2004-09-07 | Added to parts list
K-1750 | PP | Converter Alloy Tungsten |  | GSFC Approved |  | OK to Procure Mat'l
LAT-DS-00026 | PF | GLAST 2000 SSD | 2 | Signed-Off | 2002-09-17 | Auth for Flight Prod | [6 empty] | SLAC
LAT-DS-00049 | PF | Mid Tray Assy Face Sheet Top | 4 | Signed Off | 2004-02-03 | [7 empty] | INFN
LAT-DS-00050 | SA | Bottom Tray Mech. Assy | 2 | Signed-Off | 2004-06-10 | Auth for Flight Prod | 2004-07-22 |  | Yes
LAT-DS-00051 | SA | Bottom Tray Assembly w/ Payload | 2 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 |  | Yes
LAT-DS-00074 | SA | MCM Closeout Wall Assy | 4 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-07-22 |  | Yes |  |  |  | SLAC
LAT-DS-00075 | SA | Structural Closeout Wall Assy | 4 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-07-22 |  | Yes |  |  |  | SLAC
LAT-DS-00077 | PF | Short MCM PWB | 10 | Signed-Off | 2004-03-16 | Auth for Flight Prod | 2004-05-07 | [5 empty] | SLAC | 2004-03-31 | 42710 | 770 | 576 | 26% | N/A | N/A | N/A | N/A
LAT-DS-00092 | PF | MCM Closeout Wall | 7 | Offline |  |  | 2004-09-07 | New rev in works to complete dwg
LAT-DS-00093 | PF | STRL Closeout Wall | 6 | Offline |  |  | 2004-09-07 | New rev in works to complete dwg
LAT-DS-00094 | PF | Closeout Frame Insert | 3 | Signed-Off | 2004-01-30 | Auth for Flight Prod | 2004-09-07 | Mat'l call-out S/B 7075-T6 | Yes |  |  |  | INFN
LAT-DS-00130 | SA | TMCM Schematic | 2 | Signed Off | 2003-09-12 | Auth for Flight Prod | [6 empty] | SLAC
LAT-DS-00133 | EE | Short MCM PWB Gerber | 4 | Signed-Off | 2004-01-26 | Auth for Flight Prod | [6 empty] | SLAC
LAT-DS-00139 | SA | MCM Closeout Wall Assy | 6 | Offline |  |  | 2004-09-07 | New rev in works to complete dwg
LAT-DS-00140 | SA | STRL Closeout Wall Assy | 4 | Offline |  |  | 2004-09-07 | New rev in works to complete dwg
LAT-DS-00148 | SA | Reg. Converter Mech Tray Ass'y | 5 | In-Work
LAT-DS-00180 | SA | Mid Tray Reg Convert Ass'y w/Payload | 4 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 |  | Yes
LAT-DS-00181 | SA | Mid Tray No Convert Ass'y w/Payload | 4 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 |  | Yes
LAT-DS-00192 | PF | Bias Circuit Assembly | 8 | Signed-Off | 2004-04-06 | Auth for Flight Prod | 2004-05-07 |  | Yes |  |  |  |  | 2004-03-30 | 48422 | 800 & 50 | 648 | 24% | 3/26/04 (42) | 2004-03-26 | 66503 | TBD
LAT-DS-00196 | PF | STRL Closeout Wall | 4 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-05-07 |  | Yes
LAT-DS-00197 | PF | MCM Closeout Wall | 5 | Signed-Off | 2004-05-20 | Auth for Flight Prod | 2004-05-18 | Dwg mod'd to fix TMCM hole; OK to fab part | Yes
LAT-DS-00198 | PF | Top Tray Bottom Face Sheet | 4 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-05-18 | OK for fab; coupons from Plyform to B. Rodini | Yes
LAT-DS-00199 | PF | Top Tray Top Face Sheet | 4 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-05-18 | OK for fab; coupons from Plyform to B. Rodini | Yes
LAT-DS-00207 | SA | Top Tray Mechanical Assembly | 6 | Signed-Off | 2002-06-10 | Auth for Flight Prod | 2004-07-22 |  | Yes
LAT-DS-00277 | PF | Bias Plane Board | 6 | Signed-Off | 2004-02-26 | Auth for Flight Prod |  |  | Yes | N/A | N/A | N/A | SLAC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAT-DS-00303 | PF | Sidewall -X Fabrication | 6 | Signed-Off | 2004-07-20 | Auth for Flight Prod | 2004-09-30 |  | Yes |  |  |  | INFN
LAT-DS-00304 | PF | Sidewall +X Fabrication | 6 | Signed-Off | 2004-07-20 | Auth for Flight Prod | 2004-09-30 |  | Yes |  |  |  | INFN
LAT-DS-00305 | PF | Sidewall -Y Fabrication | 6 | Signed-Off | 2004-07-20 | Auth for Flight Prod | 2004-09-30 |  | Yes |  |  |  | INFN
LAT-DS-00306 | PF | Sidewall +Y Fabrication | 6 | Signed-Off | 2004-07-20 | Auth for Flight Prod | 2004-09-30 |  | Yes |  |  |  | INFN
LAT-DS-00334 | EE | C-0 Flex Cable Gerber File | 4 | Signed-Off | 2004-06-25 | Auth for Flight Prod | 2004-07-26 |  | Yes
LAT-DS-00336 | EE | C-2 Flex Cable Gerber File | 2 | Signed-Off | 2004-06-25 | Auth for Flight Prod | 2004-07-26 |  | Yes
LAT-DS-00337 | EE | C-3 Flex Cable Gerber File | 2 | Signed-Off | 2004-06-25 | Auth for Flight Prod | 2004-07-26 |  | Yes
LAT-DS-00338 | EE | C-4 Flex Cable Gerber File | 2 | Signed-Off | 2004-06-25 | Auth for Flight Prod | 2004-07-26 |  | Yes
LAT-DS-00339 | EE | C-5 Flex Cable Gerber File | 2 | Signed-Off | 2004-06-25 | Auth for Flight Prod | 2004-07-26 |  | Yes
LAT-DS-00340 | EE | C-6 Flex Cable Gerber File | 2 | Signed-Off | 2004-06-25 | Auth for Flight Prod | 2004-07-26 |  | Yes
LAT-DS-00341 | EE | C-7 Flex Cable Gerber File | 2 | Signed-Off | 2004-06-25 | Auth for Flight Prod | 2004-07-26 |  | Yes
LAT-DS-00342 | EE | C-1 Flex Cable Gerber File | 2 | Signed-Off | 2004-06-25 | Auth for Flight Prod | 2004-07-26 |  | Yes
LAT-DS-00356 | SA | MCM Closeout Wall Assembly | 5 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-07-22 |  | Yes |  |  |  | SLAC
LAT-DS-00357 | SA | Structural Closeout Wall Assy | 5 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-07-22 |  | Yes |  |  |  | SLAC
LAT-DS-00368 | PF | Tall MCM PWB | 8 | Signed-Off | 2004-03-16 | [7 empty] | SLAC | 2004-03-31 | 42710 | 85 | 72 | 16% | N/A | N/A | N/A | N/A
LAT-DS-00370 | PF | Pitch Adapter | 7 | Signed Off | 2004-05-27 | Auth for Flight Prod | 2004-06-08 | New rev released to improve production yield | Yes |  |  |  | SLAC
LAT-DS-00389 | EE | GTFE IC | 2 | Signed-Off | 2003-01-24 | [7 empty] | SLAC
LAT-DS-00417 | PF | 3-Blade Narrow Span Side Flexure | 6 | Signed-Off | 2004-03-08 | Auth for Flight Prod |  |  | Yes |  |  |  | SLAC
LAT-DS-00422 | PF | 3-Blade Corner Flexure | 7 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-05-07 |  | Yes |  |  |  | SLAC
LAT-DS-00543 | EE | TMCM STORAGE BASE | 2 | Signed-Off | 2004-04-04 | Auth for Flight Prod | 2004-07-22 | MGSE, not flight |  |  |  |  | SLAC |  | 38857 | 850
LAT-DS-00544 | EE | TMCM STORAGE COVER | 2 | Signed-Off | 2004-04-04 | Auth for Flight Prod | 2004-07-22 | MGSE, not flight |  |  |  |  | SLAC |  | 38857 | 850
LAT-DS-00584 | PF | C-0 PWB Master Layout | 10 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes |  |  |  | SLAC
LAT-DS-00592 | PF | M4 x 5.75 LG Insert | 3 | Signed-Off | 2004-05-20 | Auth for Flight Prod | 2004-05-20 | Dwg approved; OK to fab | Yes |  |  |  | SLAC
LAT-DS-00594 | SA | Ladder Assembly | 2 | Signed Off | 2002-09-05 |  | 2004-05-25 | Fab'ing to obsolete drawing; revision underway |  |  |  |  | INFN
LAT-DS-00596 | PF | Mid Tray Assy Face Sheet Bottom | 3 | Signed Off | 2004-01-26 | [7 empty] | INFN
LAT-DS-00617 | PF | Heavy Convert Tray Face Sheet Top | 4 | Signed Off | 2004-02-09 | Auth for Flight Prod | [6 empty] | INFN
LAT-DS-00618 | PF | Heavy Convert Tray Face Sheet Bottom | 4 | Signed Off | 2004-02-09 | Auth for Flight Prod | [6 empty] | INFN
LAT-DS-00647 | SA | Heavy Converter Mech Tray Ass'y | 4 | Offline |  |  | 2004-09-07 | New rev in works to complete dwg
LAT-DS-00681 | PF | Tower Base Plate | 10 | Signed-Off | 2004-07-26 | Auth for Flight Prod | 2004-09-07 | Dwg released | Yes
LAT-DS-00718 | PF | 3mm Insert | 3 | Signed Off | 2004-01-26 | Auth for Flight Prod | 2004-09-07 | Mat'l call-out S/B 7075-T6 | Yes |  |  |  | INFN
LAT-DS-00722 | SA | Tracker Module Assembly | 2 | Signed-Off | 2004-09-29 | Auth for Flight Prod | 2004-09-30
LAT-DS-00723 | PF | C-1 PWB Master Layout | 6 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes |  |  |  | SLAC
LAT-DS-00724 | PF | C-2 PWB Master Layout | 6 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes |  |  |  | SLAC
LAT-DS-00725 | PF | C-3 PWB Master Layout | 6 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes |  |  |  | SLAC
LAT-DS-00726 | PF | C-4 PWB Master Layout | 6 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes |  |  |  | SLAC
LAT-DS-00727 | PF | C-5 PWB Master Layout | 6 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes |  |  |  | SLAC
LAT-DS-00728 | PF | C-6 PWB Master Layout | 6 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes |  |  |  | SLAC
LAT-DS-00729 | PF | C-7 PWB Master Layout | 6 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes |  |  |  | SLAC
LAT-DS-00747 | SA | Mid Tray Hvy Convert Ass'y w/Payload | 3 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 |  | Yes |  |  |  | INFN
LAT-DS-00764 | SA | Top Tray Assy with Payload | 4 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 |  | Yes |  |  |  | INFN
LAT-DS-00791 | PF | 3% Converter | 3 | Signed Off | 2004-02-09 | Auth for Flight Prod | 2004-05-07 | [5 empty] | ?
LAT-DS-00792 | PF | 18% Converter | 4 | Signed Off | 2004-01-13 | Auth for Flight Prod | [6 empty] | SLAC | 2004-03-15 | 40485 | 1280 | 1152 | 10% | Drop Ship | 2003-08-09 | N/A | ?
LAT-DS-00800 | PF | MCM Closeout Wall | 8 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-05-07 |  | Yes |  |  |  | SLAC | 2004-03-31 | 43146 | 40 | 36 | 10%
LAT-DS-00801 | PF | Structural Closeout Wall | 8 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-05-07 |  | Yes |  |  |  | SLAC | 2004-03-31 | 43146 | 40 | 36 | 10%
LAT-DS-00811 | EE | GTFE IC Schematic | 1 | Signed-Off | 2003-03-03 | [7 empty] | SLAC
LAT-DS-00813 | EE | GTRC IC VHDL | 7 | Signed-Off | 2003-11-05 | [7 empty] | SLAC
LAT-DS-00893 | EE | GTRC IC | 2 | Signed-Off | 2003-03-23 | [7 empty] | SLAC
LAT-DS-00898 | SA | Short TMCM Assembly | 10 | Signed Off | 2004-06-23 | Auth for Flight Prod | 2004-07-26 |  | Yes |  |  |  | SLAC | 2004-03-31 | 48017 | 578 | 576
LAT-DS-00899 | SA | Tall TMCM Assembly | 9 | Signed Off | 2004-06-23 | Auth for Flight Prod | 2004-07-26 |  | Yes |  |  |  | SLAC | 2004-03-31 | 48017 | 60 | 72
LAT-DS-00909 | PF | Sidewall Washer 2.5mm | 2 | Signed-Off | 2004-05-04 | Auth for Flight Prod | 2004-05-07 |  | Yes |  |  |  | SLAC | 2004-03-31 | 45155 | 600
LAT-DS-01271 | SA | Sidewall +X Assembly | 3 | Signed-Off | 2004-05-11 | Auth for Flight Prod | 2004-09-30 |  | Yes |  |  |  | INFN
LAT-DS-01272 | SA | Sidewall -X Assembly | 3 | Signed-Off | 2004-05-11 | Auth for Flight Prod | 2004-09-30 |  | Yes |  |  |  | INFN
LAT-DS-01273 | SA | Sidewall +Y Assembly | 4 | Signed-Off | 2004-09-15 | Auth for Flight Prod | 2004-09-30 | Updated to include paint masking | Yes |  |  |  | INFN
LAT-DS-01274 | SA | Sidewall -Y Assembly | 4 | Signed-Off | 2004-09-15 | Auth for Flight Prod | 2004-09-30 | Updated to include paint masking | Yes |  |  |  | INFN
LAT-DS-01627 | SA | TKR Outline Drawing | 1 | Obsolete |  |  | 2004-09-30 | No longer to be used. |  | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAT-DS-01641 | EE | Pitch Adapter Gerber | 2 | Signed-Off | 2004-06-13 | [7 empty] | SLAC
LAT-DS-01803 | PF | Corner Bracket LH | 6 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-05-07 |  | Yes |  |  |  | SLAC
LAT-DS-01804 | SA | Heat Strap Assembly | 3 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-23 |  | Yes
LAT-DS-01903 | PF | Bottom Tray Face Sheet Top | 2 | Signed-Off | 2004-05-10 | Auth for Flight Prod | 2004-05-18 | OK for fab; coupons from Plyform to B. Rodini | Yes |  |  |  | INFN
LAT-DS-01904 | PF | Bottom Tray Face Sheet Bottom | 2 | Signed-Off | 2004-05-10 | Auth for Flight Prod | 2004-05-18 | OK for fab; coupons from Plyform to B. Rodini | Yes |  |  |  | INFN
LAT-DS-01905 | PF | M4 X 8.86 LG Insert | 4 | Signed-Off | 2004-05-20 | Auth for Flight Prod | 2004-05-20 | Dwg approved; OK to fab | Yes |  |  |  | INFN
LAT-DS-01906 | PF | M2.5 X 9.96 LG Insert | 4 | Signed-Off | 2004-05-20 | Auth for Flight Prod | 2004-05-20 | Dwg approved; OK to fab | Yes |  |  |  | INFN
LAT-DS-01907 | PF | M2.5 X 0.45 X 14.1 LG Insert | 1 | Obsolete | [8 empty] | INFN
LAT-DS-01919 | PF | 3mm Insert | 5 | Signed-Off | 2004-05-20 | Auth for Flight Prod | 2004-05-20 | Dwg approved; OK to fab | Yes
LAT-DS-01921 | PF | Corner Bracket RH | 6 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-05-07 |  | Yes |  |  |  | SLAC
LAT-DS-01984 | PF | Tall MCM PWB Gerber Files | 4 | Signed Off | 2004-01-24 | [7 empty] | SLAC
LAT-DS-02049 | EE | Readout Flex Cable Schematic | 5 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released |  |  |  |  | SLAC
LAT-DS-02090 | PF | Heat Strap Tie Down Strap | 3 | Signed-Off | 2004-07-26 | Auth for Flight Prod | 2004-09-07 |  | Yes
LAT-DS-02112 | PF | TMCM Mounting Pin | 2 | Signed-Off | 2004-05-18 | Auth for Flight Prod | 2004-05-20 | Dwg approved; OK to fab | Yes
LAT-DS-02203 | PF | Sidewall Washer 4mm | 2 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-05-07 |  | Yes |  |  |  | SLAC | 2004-03-31 | 45155 | 500
LAT-DS-02206 | PF | M4 X 13.12 LG Insert | 4 | Signed-Off | 2004-05-20 | Auth for Flight Prod | 2004-05-20 | Dwg approved; OK to fab | Yes
LAT-DS-02346 | SA | Packing Assembly | 1 | In-Work
LAT-DS-02358 | PF | Cable Holding Plate | 2 | Signed-Off | 2004-06-21 | Auth for Flight Prod | 2004-06-24 | OK for fab
LAT-DS-02377 | SA | C-0 Flat Assembly | 4 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes |  |  |  | SLAC
LAT-DS-02378 | SA | C-1 Flat Assembly | 2 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes |  |  |  | SLAC
LAT-DS-02379 | SA | C-2 Flat Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes |  |  |  | SLAC
LAT-DS-02380 | SA | C-3 Flat Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes |  |  |  | SLAC
LAT-DS-02381 | SA | C-4 Flat Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes |  |  |  | SLAC
LAT-DS-02382 | SA | C-5 Flat Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes |  |  |  | SLAC
LAT-DS-02383 | SA | C-6 Flat Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes |  |  |  | SLAC
LAT-DS-02384 | SA | C-7 Flat Assembly | 2 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes |  |  |  | SLAC
LAT-DS-02608 | PF | Grounding Tube | 2 | Signed-Off | 2004-03-16 | Auth for Flight Prod |  |  | Yes |  |  |  | INFN
LAT-DS-02609 | PF | Struc Closeout Wall M55J Detail -A | 2 | Signed-Off | 2004-03-29 | Auth for Flight Prod |  |  | Yes |  |  |  | SLAC
LAT-DS-02610 | PF | Struc Closeout Wall M55J Detail -B | 3 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-05-07 |  | Yes |  |  |  | SLAC
LAT-DS-02616 | PF | MCM Closeout Wall M55J Detail-A | 2 | Signed-Off | 2004-03-29 | Auth for Flight Prod |  |  | Yes |  |  |  | SLAC
LAT-DS-02617 | PF | MCM Closeout Wall M55J Detail-B | 2 | Signed-Off | 2004-03-29 | Auth for Flight Prod |  |  | Yes |  |  |  | SLAC
LAT-DS-02723 | SA | Corner BRKT Flex Assy LH | 4 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-05-07 |  | Yes |  |  |  | SLAC
LAT-DS-02786 | PF | 3-Blade Wide Span Side Flexure | 3 | Signed-Off | 2004-03-08 | Auth for Flight Prod |  |  | Yes |  |  |  | SLAC
LAT-DS-02787 | PF | Inner Eccentric Cone | 3 | Signed-Off | 2004-06-02 | Auth for Flight Prod | 2004-06-15 | Dwg released; OK to fab | Yes |  |  |  | SLAC
LAT-DS-02788 | PF | Outer Eccentric Cone | 4 | Signed-Off | 2004-06-02 | Auth for Flight Prod | 2004-06-15 | Dwg released; OK to fab | Yes |  |  |  | SLAC
LAT-DS-02789 | PF | Hex Bushing | 3 | Signed-Off | 2004-06-02 | Auth for Flight Prod | 2004-06-15 | Dwg released; OK to fab | Yes |  |  |  | SLAC
LAT-DS-02790 | PF | TBD | 1 | Obsolete |  |  | 2004-09-30 | Not used
LAT-DS-02791 | PF | Shoulder Stud | 5 | Signed-Off | 2004-07-21 | Auth for Flight Prod | 2004-07-22 | Mods incorporated to improve Nylok fit | Yes |  |  |  | SLAC
LAT-DS-02792 | PF | TBD | 1 | Obsolete |  |  | 2004-09-30 | Not used |  |  |  |  | SLAC
LAT-DS-02793 | PF | TBD | 1 | Obsolete |  |  | 2004-09-30 | Not used |  |  |  |  | SLAC
LAT-DS-02794 | PF | Tracker Interface Bushing | 3 | Signed-Off | 2004-05-18 | Auth for Flight Prod
LAT-DS-02922 | SA | Corner BRKT Flex Assy. RH | 4 | Signed-Off | 2004-05-06 | Auth for Flight Prod | 2004-05-07 |  | Yes
LAT-DS-02923 | SA | No Converter Mech Tray Ass'y | 2 | Offline |  |  | 2004-09-07 | New rev in works to complete dwg
LAT-DS-03031 | PF | Cable Stiffener | 2 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes |  |  |  | SLAC
LAT-DS-03037 | EE | Flex Cable Stiffener Gerber File | 1 | Obsolete | 2004-05-27 |  | 2004-06-08 | Not used
LAT-DS-03039 | PF | Stiffener Adhesive Preform | 1 | Obsolete |  |  | 2004-05-03 | Not used
LAT-DS-03040 | PF | Connector Adhesive Preform | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes
LAT-DS-03041 | PF | Pin Retainer | 2 | Signed-Off | 2004-03-08 | Auth for Flight Prod |  |  | Yes
LAT-DS-03083 | PF | Dowel Pin | 2 | Signed-Off | 2004-03-08 | Auth for Flight Prod |  |  | Yes
LAT-DS-03183 | SA | C-0 Bent Assembly | 2 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes |  |  |  | SLAC
LAT-DS-03184 | SA | C-1 Bent Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes |  |  |  | SLAC
LAT-DS-03185 | SA | C-2 Bent Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes |  |  |  | SLAC
LAT-DS-03186 | SA | C-3 Bent Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes |  |  |  | SLAC
LAT-DS-03187 | SA | C-4 Bent Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes |  |  |  | SLAC
LAT-DS-03188 | SA | C-5 Bent Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes |  |  |  | SLAC
LAT-DS-03189 | SA | C-6 Bent Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes |  |  |  | SLAC
LAT-DS-03190 | SA | C-7 Bent Assembly | 1 | Signed-Off | 2004-05-27 | Auth for Flight Prod | 2004-05-31 | Flex Cable Mech and Elec drawings released | Yes |  |  |  | SLAC
LAT-DS-03309 | PF | Upper Cable Restraint | 1 | Obsolete |  |  | 2004-09-30 | Not used
LAT-DS-03488 | PF | Closeout Corner Pin | 1 | Signed-Off | 2004-05-14 | Auth for Flight Prod | 2004-05-18 | Dwg released; OK to fab or procure part | Yes
LAT-DS-03504 | PF | Bottom Tray Honeycomb Core | 1 | Signed-Off | 2004-04-07 | Auth for Flight Prod | 2004-05-04 |  | Yes |  |  |  | SLAC | 2004-03-16 | 46721 | 24 | 18 | 25% | Drop Ship | 2004-01-29 | N/A | ?
LAT-DS-03505 | PF | Interface Parts Auxiliary Ass'y | 2 | Signed-Off | 2004-06-02 | Auth for Flight Prod | 2004-06-15 | Dwg released; OK to fab | Yes
LAT-DS-03506 | PF | Installation Shims | 2 | Signed-Off | 2004-06-02 | Auth for Flight Prod | 2004-06-15 | Dwg released; OK to fab | Yes |  |  |  | SLAC
LAT-DS-03509 | PF | Grid Simulator Plate | 1 | Obsolete |  |  | 2004-09-30 | Not used |  |  |  |  | SLAC
LAT-DS-03538 | PF | 3mm Insert | 2 | Signed-Off | 2004-05-20 | Auth for Flight Prod | 2004-05-20 | Dwg approved; OK to fab | Yes |  |  |  | INFN
LAT-DS-03539 | PF | M2.5 x 7.5 LG Insert | 2 | Signed-Off | 2004-05-20 | Auth for Flight Prod | 2004-05-20 | Dwg approved; OK to fab | Yes |  |  |  | INFN
LAT-DS-03544 | PF | Tray Vibration Fixture | 1 | In-Work |  |  | 2004-05-16 | MGSE, not flight
LAT-DS-03551 | PF | Square Nut, Grid | 3 | Signed-Off | 2004-07-26 | Auth for Flight Prod | 2004-09-07 | Updated rev into parts list | Yes
LAT-DS-03618 | SA | Tower Lifting Fixture Assembly | 1 | Signed-Off | 2004-07-23 | Auth for Flight Prod | 2004-07-23
LAT-DS-03619 | PF | Lifting Plate | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-23
LAT-DS-03620 | PF | Flexure | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-23
LAT-DS-03673 | PF | Tower Base Plate Assembly | 2 | Signed-Off | 2004-07-22 | Auth for Flight Prod | 2004-09-07 | Dwg released | Yes
LAT-DS-03681 | PF | Heat Strap Inner | 2 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-23 |  | Yes
LAT-DS-03682 | PF | Heat Strap Outer | 2 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-23 |  | Yes
LAT-DS-03738 | PF | Tray Service Box | 1 | In-Work |  |  | 2004-05-16 | MGSE, not flight
LAT-DS-03825 | PF | Connector Mount | 1 | Signed-Off | 2004-06-21 | Auth for Flight Prod | 2004-06-24 | OK for fab
LAT-DS-03826 | SA | Cable Holding Plate Assembly | 2 | Signed-Off | 2004-09-29 | Auth for Flight Prod | 2004-09-30
LAT-DS-03892 | PF | Proof Test Cross Bar | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-23
LAT-DS-03925 | PT | M5 x 0.8 Hex Nut | 1 | Signed-Off | 2004-06-02 | Auth for Flight Prod | 2004-06-15 | Dwg released; OK to fab | Yes
LAT-DS-03943 | PF | X-Side Container Wall | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22
LAT-DS-03944 | PF | Y-Side Container Wall | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22
LAT-DS-03945 | PF | Left-Hand Corner Post | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22
LAT-DS-03946 | PF | Right-Hand Corner Post | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22
LAT-DS-03947 | PF | Bottom Cover Plate | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22
LAT-DS-03948 | PF | Top Cover Plate | 2 | Signed-Off | 2004-08-18 | Auth for Flight Prod | 2004-09-07 | Update released w/Datalogger holes | Yes
LAT-DS-03949 | SA | Inner Shipping Container Assembly | 1 | Signed-Off | 2004-09-20 | Auth for Flight Prod | 2004-09-30
LAT-DS-03960 | SA | Grounding Lug Assembly | 2 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 |  | Yes
LAT-DS-03961 | PF | Double Corner Mount Bracket | 1 | Signed-Off | 2004-07-21 | Auth for Flight Prod | 2004-07-22 |  | Yes
LAT-DS-03962 | PF | Left-Hand Corner Mount Bracket | 1 | Signed-Off | 2004-07-21 | Auth for Flight Prod | 2004-07-22 |  | Yes
LAT-DS-03963 | PF | Right-Hand Corner Mount Bracket | 1 | Signed-Off | 2004-07-21 | Auth for Flight Prod | 2004-07-22 |  | Yes
LAT-DS-03964 | PF | Single Corner Mount Bracket | 1 | Signed-Off | 2004-07-21 | Auth for Flight Prod | 2004-07-22 |  | Yes
LAT-DS-03965 | SA | Reflector Ball Nest Assembly | 1 | Signed-Off | 2002-07-15 | Auth for Flight Prod | 2004-07-22 |  | Yes
LAT-DS-03966 | PF | Reflector Ball Nest | 1 | Signed-Off | 2002-07-15 | Auth for Flight Prod | 2004-07-22 |  | Yes
LAT-DS-03967 | PF | Nest Magnet | 1 | Signed-Off | 2002-07-15 | Auth for Flight Prod | 2004-07-22 |  | Yes
LAT-DS-03968 | SA | Top Tray Auxiliary Assembly | 1 | Signed-Off | 2004-09-29 | Auth for Flight Prod | 2004-09-30 |  | Yes
LAT-DS-03998 | PF | Cable Retaining Clip | 1 | Signed-Off | 2004-07-21 | Auth for Flight Prod | 2004-07-22 |  | Yes
LAT-DS-03999 | PF | OBSOLETE | 1 | Obsolete |  |  | 2004-09-30 | Not used
LAT-DS-04006 | SA | TKR Vibe Test Configuration Ass'y | 1 | Obsolete |  |  | 2004-09-30 | Not used
LAT-DS-04007 | SA | TKR T-Vac Test Configuration Ass'y | 1
LAT-DS-04008 | SA | TKR Lifting Configuration Ass'y | 1 | Obsolete |  |  | 2004-09-30 | Not used
LAT-DS-04009 | SA | TKR Shipping Configuration Ass'y | 1 | Signed-Off | 2004-09-20 | Auth for Flight Prod | 2004-09-30
LAT-DS-04010 | PF | Outer Shipping Container SCD | 1 | Signed-Off | 2004-08-17 | Auth for Flight Prod | 2004-09-07
LAT-DS-04127 | PF | Weight | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22
LAT-DS-04128 | PF | Weight Rod | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22
LAT-DS-04199 | PF | M4 x 8 lg 100 deg Flat Hd Cap Scr | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 |  | Yes
LAT-DS-04200 | PF | M4 x 6 lg 100 deg Flat Hd Cap Scr | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 |  | Yes
LAT-DS-04201 | PF | M2.5 x 8 lg 100 deg Flat Hd Cap Scr | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 |  | Yes
LAT-DS-04202 | PF | M2.5 x 8 lg 120 deg Flat Hd Cap Scr | 1 | Signed-Off | 2004-07-15 | Auth for Flight Prod | 2004-07-22 |  | Yes
LAT-DS-04225 | PF | Inr Ship Container Proof Test Plate | 1 | Obsolete |  |  | 2004-09-30 | Not used
LAT-DS-04434 | SA | Base Plate + Tracker Ass'y | 1 | Signed-Off | 2004-09-15 | Auth for Flight Prod | 2004-09-30
LAT-DS-04435 | SA | TKR Ground Configuration Ass'y | 1 | Signed-Off | 2004-09-29 | Auth for Flight Prod | 2004-09-30
LAT-DS-04438 | SA | TKR Survey Configuration Ass'y | 1 | Obsolete |  |  | 2004-09-30 | Not used
LAT-DS-04586 | PF | Inner Ship Container Sidewall Shim | 1 | Signed-Off | 2004-09-20 | Auth for Flight Prod | 2004-09-30
LAT-DS-04730 | PF | Connector Mount Cap | 1 | Signed-Off | 2004-09-24 | Auth for Flight Prod | 2004-09-30
Lexan 500 | MT | encapsulant dam |  | GSFC Approved |  | OK to Procure Mat'l |  | No longer to be used.
Loctite 401 | MT | Cyanoacrylate Adhesive |  | GSFC Pending |  |  | 2004-06-15 | Not yet approved; planned for heat straps only
Madge Tech Ultrashock-EB | PP | Shock, Temp, Pressure, and Humidity Data Logger |  | GSFC Pending |  | OK to Procure Mat'l | 2004-09-30
M55342M02B100DR | EE | Resistor, 100 Ohm 1%, SOTA | [10 empty] | SLAC |  | 41333 | 6020
M55342M02B12K0R | EE | RES, 12K 5%, SOTA | [10 empty] | SLAC |  | 41333 | 1800
M55342M02B200DR | EE | Resistor, 200 Ohm 1%, SOTA | [10 empty] | SLAC
M55342M02B39K0R | EE | Resistor, 39K-Ohm 5%, SOTA | [10 empty] | SLAC |  | 41333 | 22000
M55342M02B680KR | EE | RES, 680K 5%, SOTA | [10 empty] | SLAC |  | 41333 | 32600
M55J/CE3 | MT | Carbon Fiber Composite, Resin Content 31+/- 2% |  | GSFC Approved |  | OK to Procure Mat'l | [6 empty] | SLAC
MC 3112T13 | PP | M10x1.5 Eye Nut Steel Zinc Plated |  |  |  | OK to Procure Mat'l
MC 3155T13 | MP | M12 Eye Nut, Forged 316 St Steel |  |  |  | OK to Procure Mat'l | 2004-07-22
MC 3174T11 | MP | M8 Eye Nut, Forged 316 St Steel |  |  |  | OK to Procure Mat'l | 2004-07-22
MC 8481A34 | MP | 0.5" Tooling Ball, 0.25" Shank |  |  |  | OK to Procure Mat'l
MC 90278A328 | MP | 5x10 Lg SH Shoulder Scr, 18-8 St Steel |  |  |  | OK to Procure Mat'l | 2004-07-22
MC 90965A160 | MP | M5x10 OD Flat Washer, 316 St Steel |  |  |  | OK to Procure Mat'l | 2004-07-22
MC 90965A170 | MP | M6x12 OD Flat Washer, 316 St Steel |  |  |  | OK to Procure Mat'l | 2004-07-22
MC 90965A190 | MP | M8x16 OD Flat Washer, 316 St Steel |  |  |  | OK to Procure Mat'l | 2004-07-22
MC 90965A210 | MP | M12x24 OD Flat Washer, 316 St Steel |  |  |  | OK to Procure Mat'l | 2004-07-22
MC 92148A200 | MP | M8x2 Thk Lock Washer, 316 St Steel |  |  |  | OK to Procure Mat'l | 2004-07-22
MC 92153A436 | MP | M12x2.5 Thk Lock Washer, 316 St Steel |  |  |  | OK to Procure Mat'l | 2004-07-22
MC 92290A242 | MP | M5x0.8x20 Lg SHCS, 316 St Steel |  |  |  | OK to Procure Mat'l | 2004-07-22
MC 92290A442 | MP | M8x1.25 x 40 Lg SHCS, 316 St Steel |  |  |  | OK to Procure Mat'l | 2004-07-22
MC 92290A624 | MP | M12x1.75 x 40 Lg SHCS, 316 St Steel |  |  |  | OK to Procure Mat'l | 2004-07-22
MC 94150A345 | MP | M6x1 Hex Nut, 316 St Steel |  |  |  | OK to Procure Mat'l | 2004-07-22
MC 98394A437 | MP | 20 Diam x 1 Int Retain Ring, PH15-7 St Steel |  |  |  | OK to Procure Mat'l
MIL-D-3464E | PP | 12 Units Silica Gel Dessicant in Tyvek Bag |  | GSFC Pending |  | OK to Procure Mat'l | 2004-09-30
MIL-G-9954 | MT | Glass Beads .005"-.007" |  | GSFC Approved |  | OK to Procure Mat'l | [6 empty] | SLAC
MIL-G-9954 | MT | Glass Beads .005"-.007" |  | GSFC Approved |  | OK to Procure Mat'l | [6 empty] | SLAC
MIL-PRF-81705D Type III | MT | Static Shield Sheet, 0.003" Nom Thk |  | GSFC Pending |  | OK to Procure Mat'l | 2004-09-07 | Added to parts list |  |  |  |  | SLAC
MS51029-105 | MP | 4-40 UNC-2Ax.37" lg CRES flat pt SHSS |  |  |  | OK to Procure Mat'l
NAS 1352-N06-10 | PP | 6-32 UNC x 5/8 IN SHCS, A286 St Steel |  | GSFC Approved |  | OK to Procure Mat'l | [6 empty] | SLAC
NAS 1352-N04LB-6 | PP | 4-40 UNC x 3/8 IN SHCS, A286 St Steel, Self-Locking |  | GSFC Approved |  | OK to Procure Mat'l | 2004-09-07 | [5 empty] | SLAC
NAS723CE100-120 | PP | M1X0.25 X 0.120" LG FLAT HD CS, SST | [10 empty] | SLAC
NuSil CV-1142 | MT | Non-Slumping RTV Silicone |  | GSFC Approved |  | OK to Procure Mat'l | [6 empty] | SLAC | 2004-03-16 | 42374 | 7 ea. 6 oz. Tubes | N/A | N/A | 2003-06-16
NuSil CV15-2500 | MT | Silicone Encapsulant |  | GSFC Approved |  | OK to Procure Mat'l | [6 empty] | SLAC | 2004-03-16 | 42374 | 2 ea. 500 grams | N/A | N/A | 2003-06-16
NuSil CV-2500 | MT | Silicone Encapsulant |  | GSFC Approved |  | OK to Procure Mat'l
NuSil CV-2502 | MT | Thixotropic Silicone Encapsulant |  | GSFC Approved |  | OK to Procure Mat'l | [6 empty] | SLAC | 2004-03-16 | 42374 | 1 ea. 500 gram | N/A | N/A | 2003-06-16 | 2004-10-20 | N/A
NuSil CV-2646 | MT | Conductive Silicone Adhesive |  | GSFC Approved |  | OK to Procure Mat'l | [6 empty] | SLAC | 2004-03-16 | 42374 & 44912 | 1ea. 500gm & 2ea. 500gm | N/A | N/A | 2003-06-16
Omnetics A8485-001 | EE | Connector Receptacle, 37 pin | [10 empty] | SLAC |  | 40836 | 1682
Omnetics A8486-001 | EE | Nano-Connector Plug, 37-Pin | [10 empty] | SLAC
OMNETICS A8597-001 | EE | CONNECTOR SAVER, 37 PIN | [5 empty] | EGSE, not flight |  |  |  |  | SLAC |  | 40836 | 1600
PAMG-XR1-1.0-3/8-0007-P-5056 | PP | 5056 Alum Honeycomb 1.0 pcf x 3/8" cell |  | GSFC Approved |  | OK to Procure Mat'l | [6 empty] | SLAC | 2004-04-22 | 46721 | 286 | 198 | 31% | Drop Ship | 2004-01-29 | N/A | ?
PAMG-XR1-3.0-3/8-002-P-5056 | PP | 5056 Alum Honeycomb 3.0 pcf x 3/8" cell |  | GSFC Approved |  | OK to Procure Mat'l | [6 empty] | SLAC | 2004-03-16 | 46721 | 88 |  |  | Drop Ship | 2004-01-29 | N/A | ?
Redux 312 UL | MT | Film Adhesive (core to face sheet) |  | GSFC Approved |  | OK to Procure Mat'l
S.S. 302 MJ2.5 100 Degree | PP | Side Wall Fastener |  | GSFC Approved |  | OK to Procure Mat'l | [6 empty] | SLAC
SMDC014-2 | EE | POLYSWITCH 0.3 AMP, TYCO/RAYCHEM | [10 empty] | SLAC |  | 41429 | 10000
Solithane 113/300 | MT | Thread Lock |  | GSFC Approved |  | OK to Procure Mat'l | [6 empty] | SLAC
TELEDYNE #7258290 | MT | EPO-TEK H20E, DIE ATTACH, EPOXY | [10 empty] | Teledyne
TELEDYNE #7261633 & TELEDYNE #7261638 | MT | HUMISEAL 1A2O, CONFORMAL COATING | [10 empty] | Teledyne
TELEDYNE #7261679-1 | MT | SCOTCHWELD 1838 B/A, EPOXY, GREEN | [10 empty] | Teledyne
TELEDYNE #7261685-1 | MT | HYSOL FP4451, DIE ENCAPSULANT DAM | [10 empty] | Teledyne
TELEDYNE #7261693-1 | MT | HYSOL FP4450, DIE ENCAPSULANT | [10 empty] | Teledyne
TELEDYNE #7506502 | MT | SOLDER WIRE | [10 empty] | Teledyne
TELEDYNE #7506598 | MT | SN62, SOLDER PASTE | [10 empty] | Teledyne
YSI S-311-P18-09S7R6 | EE | Thermistor, 30K | [10 empty] | SLAC