## MSRR
RFA # | Subject | Originator | Response | Closure Date
1 | Requirements Traceability & Verification Matrix | Al Lieberman | MSRR RFA 1 Response Mod.doc | 2001-01-11
2 | Engineering Test Unit and Flight Data System Simulator | Mary Esfandiari | MSRR RFA 2 Response.doc | 2001-01-11
3 | LAT IOC & GBM IOC SW and Data to SSC | Mary Esfandiari | MSRR RFA 3 Response.doc | 2001-01-11
4 | Different Instrument Data Streams to SSC | Mary Esfandiari | MSRR RFA 4 Response Mod.doc | 2001-03-28
5 | Define a SC and Instrument Jitter Spec | Tim Gruner | MSRR RFA 5 Response.doc | 2001-01-11
6 | Revisit Requirement for Deorbit Propulsion System | Tim Gruner Dennis Dillman | MSRR RFA 6 Response.doc | 2001-01-11
7 | Fault Tolerance and Reliability Requirements | Tim Gruner | MSRR RFA 7 Response.doc | 2001-01-11
8 | System Level Mass Breakdown | Tim Gruner Alan Posey | MSRR RFA 8 Response.doc | 2001-01-11
9 | Review Requirements Stated as Design Solutions and Revise | Tim Gruner Alan Posey Paul Guy | MSRR RFA 9 Response.doc | 2001-01-11
10 | Analysis Software Configuration Control | Nick White | MSRR RFA 10 Response.doc | 2001-01-11
11 | Lack of TDRSS Coverage during a Burst | Nick White | MSRR RFA 11 Response.doc | 2001-01-11
12 | Common Higher-Level Analysis Software Environment | Nick White | MSRR RFA 12 Response.doc | 2001-01-11
13 | Requirement for Data Latency to Guest Observer | Nick White | MSRR RFA 13 Response.doc | 2001-01-11
14 | Role of the HEASARC | Nick White Mary Esfandiari | MSRR RFA 14 Response.doc | 2001-01-11
15 | Make GBM Localization a Requirement | Nick White | MSRR RFA 15 Response.doc | 2001-01-11
16 | Add GBM Requirements for All-Sky Monitor Data Analysis and TOO Alerts | Nick White | MSRR RFA 16 Response.doc | 2001-01-11
17 | Data Format Standards for Level 1 and Above | Nick White | MSRR RFA 17 Response.doc | 2001-01-11
18 | Science Community Expectations | Nick White | MSRR RFA 18 Response.doc | 2001-01-11
19 | Joint Analysis and Coordinated Observations | Nick White | MSRR RFA 19 Response.doc | 2001-01-11
20 | Detailed System Level Contamination Control Plan | Alan Posey | MSRR RFA 20 Response.doc | 2001-01-11
21 | Calibration of Both Instruments Over Predicted Temperature Extremes | Alan Posey | MSRR RFA 21 Response.doc | 2001-01-11
22 | Develop Preliminary Mechanical Environmental Specifications | Alan Posey | MSRR RFA 22 Response.doc | 2001-01-11
|  |  | Total RFAs | 22
|  |  | # Closed | 22

## LAT PDR
RFA # | Subject | Originator | Assignee | Response | Date Submitted to Systems | Project Office Review Status | Date Submitted to Code 300 | Closure Status | Closure Date
1 | Minimum Science Mission Requirements and Descope Plan | Steve Scott |  | LAT PDR RFA 1 Response.doc |  | PM Approved 2/19/04 | 2004-02-20 | SS approved via email 3/4/04 | 2004-03-04
2 | Requirements Verification Traceability Matrix | Steve Scott |  | LAT PDR RFA 2 Response.doc |  |  |  | Closed | 2003-04-17
3 | LAT Risk List | Steve Scott |  | LAT PDR RFA 3 Response.doc |  |  |  | Closed | 2003-04-17
4 | Regularly Monitored LAT Technical Budgets | Steve Scott |  | LAT PDR RFA 4 Response.doc |  |  |  | Closed | 2003-04-17
5 | Cross Subsystem Trade Studies | Steve Scott |  | LAT PDR RFA 5 Response.doc |  |  |  | Closed | 2003-04-17
6 | Spacecraft Requirements and Constraints | Steve Scott |  | LAT PDR RFA 6 Response.doc |  |  |  | Closed | 2003-04-17
7 | Status and Tracking Plan of Technical Drawings | Steve Scott | Horn | LAT PDR RFA 7 Response.doc |  | PM Approved 4/4/04 | 2004-04-08 | SS approved via email 4/8/04 | 2004-04-08
8 | Subsystem and System Peer Review RFAs | Steve Scott |  | LAT PDR RFA 8 Response.doc |  |  |  | Closed | 2003-04-17
9 | Design and Fabrication of Cables and Harnesses | Steve Scott |  | LAT PDR RFA 9 Response.doc |  |  |  | Closed | 2003-04-17
10 | Transition of LAT CM and Problem Reporting & Corrective Action processes | Steve Scott |  | LAT PDR RFA 10 Response.doc |  |  |  | Closed | 2003-04-17
11 | Descriptions of LAT CPT, LPT, & Aliveness Test | Steve Scott |  | LAT PDR RFA 11 Response.doc |  |  |  | Closed | 2003-04-17
12 | Description of Alignment Requirements and Tests | Steve Scott |  | LAT PDR RFA 12 Response.doc |  |  |  | Closed | 2003-04-17
13 | Time Accuracy Requirements | Steve Scott |  | LAT PDR RFA 13 Response.doc |  |  |  | Closed | 2003-04-17
14 | Levels of Redundancy |  |  | LAT PDR RFA 14 Response.doc |  |  |  | Closed | 2003-04-17
15 | Logistics Support Plan and Expected Spares | Steve Scott | Horn | LAT PDR RFA 15 Response RevA.doc | 2004-07-02 | PM Approved 8/2/04 | 2004-08-06 | SS approved via email 8/8/04 | 2004-08-08
LAT-TD-04167-01 LAT Subsystem Spares Summary.doc
16 | Formal Qualification Test of FSW prior to Delivery to I&T | Steve Scott |  | LAT PDR RFA 16 Response.doc |  |  |  | Closed | 2003-04-17
17 | Describe the Metrology Program | Steve Scott |  | LAT PDR RFA 17 Response.doc |  |  |  | Closed | 2003-04-17
18 | Conduct Software Peer Reviews | Steve Scott |  | LAT PDR RFA 18 Response.doc |  |  |  | Closed | 2003-04-17
19 | GLAST LAT Software Requirements | Steve Scott |  | LAT PDR RFA 19 Response.doc |  |  |  | Closed | 2003-04-17
20 | NASA IV&V Involvement with LAT | Steve Scott | Dubois/Haller | LAT PDR RFA 20 Response.doc |  | PM Approved 1/7/04 | 2004-01-15 | SS approved via email 3/4/04 | 2004-03-04
21 | EGSE Verification and Validation | Steve Scott |  | LAT PDR RFA 21 Response.doc |  |  |  | Closed | 2003-04-17
22 | Software Maintenance Approach | Steve Scott |  | LAT PDR RFA 22 Response.doc |  |  |  | Closed | 2003-04-17
23 | Cabling and Harnessing Peer Review | Steve Scott |  | LAT PDR RFA 23 Response.doc |  |  |  | Closed | 2003-04-17
24 | EMI/EMC Acceptance Testing | Cliff Jackson | Haller | LAT PDR RFA 24 Response.doc |  | PM Approved 2/19/04 | 2004-02-20 | CJ approved via email 2/23/04 | 2004-02-23
25 | Reevaluate Operational and Survival Temperature Limits | Cliff Jackson |  | LAT PDR RFA 25 Response.doc |  |  |  | Closed | 2003-04-17
26 | Systems Engineering Management Plan Implementation | Cliff Jackson |  | LAT PDR RFA 26 Response.doc |  |  |  | Closed | 2003-04-17
27 | Pursue a System Solution to Radiator Repackaging | Hewitt/McCarthy |  | LAT PDR RFA 27 Response.doc |  |  |  | Closed | 2003-04-17
28 | Factor Long Thermal /Time Constant into TV/TB Planning | Hewitt/McCarthy |  | LAT PDR RFA 28 Response.doc |  |  |  | Closed | 2003-04-17
29 | Fabrication of Radiators to Original Schedule | Hewitt/McCarthy |  | LAT PDR RFA 29 Response.doc |  |  |  | Closed | 2003-04-17
30 | Consider Second Sourcing of TCS Components | Hewitt/McCarthy |  | LAT PDR RFA 30 Response.doc |  |  |  | Closed | 2003-04-17
31 | TCS Qualification and Acceptance Testing | Hewitt/McCarthy | Nordby | LAT PDR RFA 31 Response.doc |  | PM Approved 1/7/04 | 2004-01-15 | TM Approved via email 1/22/04 | 2004-04-26
DH concur from TM 4/26/04
32 | Individual Box Temperature Requirements | Hewitt/McCarthy | Nordby | LAT PDR RFA 32 Response.doc |  | PM Approved 1/7/04 | 2004-01-15 | TM Approved via email 1/22/04 | 2004-04-26
DH concur from TM 4/26/04
33 | Delta PDR for Mechanical/Thermal | Hewitt/McCarthy |  | LAT PDR RFA 33 Response.doc |  |  |  | Closed | 2003-04-17
34 | Alternative Radiator Thermal Coatings | Hewitt/McCarthy |  | LAT PDR RFA 34 Response.doc |  |  |  | Closed | 2003-04-17
35 | Workmanship TV Test of the Flight Grid with Heat Pipes | Hewitt/McCarthy |  | LAT PDR RFA 35 Response.doc |  |  |  | Closed | 2003-04-17
36 | LAT Survival Heater Control | Hewitt/McCarthy |  | LAT PDR RFA 36 Response.doc |  |  |  | Closed | 2003-04-17
37 | Thermal Interface Materials | Hewitt/McCarthy |  | LAT PDR RFA 37 Response.doc |  |  |  | Closed | 2003-04-17
38 | Blanket Equivalent Sink Temperatures | Hewitt/McCarthy |  | LAT PDR RFA 38 Response.doc |  |  |  | Closed | 2003-04-17
39 | Thermal Control System Risks and Risk Mitigation List | Hewitt/McCarthy | Nordby | LAT PDR RFA 39 Response.doc |  | PM Approved 1/7/04 | 2004-01-15 | TM Approved via email 1/22/04 | 2004-04-26
DH concur from TM 4/26/04
40 | Reevaluate Worst Case Hot/Cold Cases | Hewitt/McCarthy |  | LAT PDR RFA 40 Response.doc |  |  |  | Closed | 2003-04-17
41 | Freeze/Thaw of VCHP/CCHP Ammonia | Hewitt/McCarthy |  | LAT PDR RFA 41 Response.doc |  |  |  | Closed | 2003-04-17
42 | Sensitivity of Tracker Tray Temperature | Hewitt/McCarthy |  | LAT PDR RFA 42 Response.doc |  |  |  | Closed | 2003-04-17
43 | Impact of Replacing a Tracker Tower | Jim Ryan |  | LAT PDR RFA 43 Response.doc |  |  |  | Closed | 2003-04-17
44 | Allowables Testing for Composite Joints | Jim Ryan | Nordby | LAT PDR RFA 44 Response RevB.doc | 2004-07-02 | PM Approved 8/2/04 | 2004-08-06 | JR approved via email 8/9/04 | 2004-08-09
45 | Fastener Procurement | Jim Ryan | Nordby | LAT PDR RFA 45 Response.doc |  | PM Approved 5/19/04 | 2004-05-19 | JR approved via email 5/20/04 | 2004-05-20
46 | Incorporate Positive Sheer Restraint | Jim Ryan | Nordby | LAT PDR RFA 46 Response.doc | 2004-05-03 | PM Approved 8/28/04 | 2004-08-30 | JR approved via email 9/1/04 | 2004-09-01
47 | Sine Test Philosophy | Jim Ryan | Nordby | LAT PDR RFA 47 Response RevB.doc | 2004-07-02 | PM Approved 8/2/04 RevB updated per JR comment | 8/6/2004 8/24/2004 | JR approved via email with comment 8/31/04 | 2004-08-31
48 | Strength Qualification Plan for the LAT | Jim Ryan | Nordby | LAT PDR RFA 48 Response RevC.doc | 7/2/2004 8/17/2004 8/25/2004 | PM Approved 8/28/04 | 2004-08-30 | JR approved via email 9/1/04 | 2004-09-01
49 | Overall Flow Diagram to the PCB or Component Level | Dave Betz | Horn | LAT PDR RFA 49 Response.doc |  | PM Approved 1/7/04 | 2004-01-15 | Mark Goans approved via email 5/20/04 | 2004-05-20
50 | Polyswitch Qualification | Fred Huegel |  | LAT PDR RFA 50 Response.doc |  |  |  | Closed | 2003-04-17
51 | Tantalum Capacitor Testing and Derating | Fred Huegel |  | LAT PDR RFA 51 Response.doc |  |  |  | Closed | 2003-04-17
52 | Power Supply Development Schedule and Budget | Fred Huegel |  | LAT PDR RFA 52 Response.doc |  |  |  | Closed | 2003-04-17
53 | Use of Optocouplers | Fred Huegel |  | LAT PDR RFA 53 Response.doc |  |  |  | Closed | 2003-04-17
54 | RAD750 Backup Options | Fred Huegel |  | LAT PDR RFA 54 Response.doc |  |  |  | Closed | 2003-04-17
55 | Burn-in and Screening of the Flight ASICs | Fred Huegel |  | LAT PDR RFA 55 Response.doc |  |  |  | Closed | 2003-04-17
56 | Discrepancies in the ACD Flight ASIC Schedules | Fred Huegel |  | LAT PDR RFA 56 Response.doc |  |  |  | Closed | 2003-04-17
57 | Additional Resources in the FSW Development | Fred Huegel |  | LAT PDR RFA 57 Response.doc |  |  |  | Closed | 2003-04-17
[8 empty] | Total RFAs | 57
[8 empty] | # Closed | 57

## GBM PDR
RFA # | Subject | Originator | Assignee | Due Date | Response | Date Submitted to Systems | Project Office Review Status | Date Submitted to Code 300 | Closure Status | Closure Date
1 | Unanticipated Interface Issues after SC Vendor Selection | Jean Oliver |  |  | GBM PDR RFA 1 Response.doc |  | Approved |  | Closed | 2003-09-05
2 | Review of Parts List for Flight Acceptability | Bruce Meinhold |  |  | GBM PDR RFA 2 Response.doc |  | Approved |  | Closed | 2003-09-05
3 | Verify Capability of High Voltage Cable | Bruce Meinhold |  |  | GBM PDR RFA 3 Response.doc |  | Approved |  | Closed | 2003-09-05
4 | Verify Acceptability of Actel FPGA Devices | Bruce Meinhold | SwRI / DJO | 12/15/03? | GBM PDR RFA 4 Response RevA.doc |  | PM Approved 9/15/04 | 2004-09-15 | BM approved via email 10/5/04 | 2004-10-05
5 | Provide Preliminary for All GBM Subsystems | Bruce Meinhold |  |  | GBM PDR RFA 5 Response.doc |  | Approved |  | Closed | 2003-09-05
6 | Blanket ESD Requirements | Tom McCarthy |  |  | GBM PDR RFA 6 Response.doc |  | Approved |  | Closed | 2003-09-05
7 | PMT Storage Temperature | Tom McCarthy |  |  | GBM PDR RFA 7 Response.doc |  | Approved |  | Closed | 2003-09-05
8 | Heater Power Margins and Contingency | Tom McCarthy | DJO | GBM CDR | GBM PDR RFA 8 Response RevA.doc |  | Addressed at CDR |  | TM approved via email 7/13/04 | 2004-07-13
9 | Thermal Tolerance of both DPU Boards Powered On | Tom McCarthy |  |  | GBM PDR RFA 9 Response.doc |  | Approved |  | Closed | 2003-09-05
10 | Environmental Test Matrix for all Test/Analysis on GBM | Mark Goans |  |  | GBM PDR RFA 10 Response.doc |  | Approved |  | Closed | 2003-09-05
11 | Command and Telemetry System | Ron Zellar |  |  | GBM PDR RFA 11 Response.doc |  | Approved |  | Closed | 2003-09-05
12 | Magnetic Field Rate of Change | Joseph Bolek | Dr. Lichti | 2003-12-15 | GBM PDR RFA 12 Response RevA.doc |  | PM Approved 2/19/04 | 2004-02-20 | JB comment received 3/5/04 Rev A approved via email 3/15/04 | 2004-03-15
13 | Verification of Orbit Parameters in Thermal Analysis | Joseph Bolek |  |  | GBM PDR RFA 13 Response.doc |  | Approved |  | Closed | 2003-09-05
14 | Deleted | David Betz |  |  | Deleted |  | Approved |  | Deleted | 2003-09-05
15 | Test with Flight Cables or Test Cables Built to Flight | Fred Huegel |  |  | GBM PDR RFA 15 Response.doc |  | Approved |  | Closed | 2003-09-05
16 | GBM vs. SC Selection of Electrical Connections | Fred Huegel |  |  | GBM PDR RFA 16 Response.doc |  | Approved |  | Closed | 2003-09-05
17 | Detector Signal Interface to the Redundant DPUs | Fred Huegel |  |  | GBM PDR RFA 17 Response.doc |  | Approved |  | Closed | 2003-09-05
18 | SC Provided Over Current Protection | Fred Huegel |  |  | GBM PDR RFA 18 Response.doc |  | Approved |  | Closed | 2003-09-05
19 | High Voltage Cable Fabrication | Fred Huegel |  |  | GBM PDR RFA 19 Response.doc |  | Approved |  | Closed | 2003-09-05
20 | Interface Level FMEA | David Betz |  |  | GBM PDR RFA 20 Response.doc |  | Approved |  | Closed | 2003-09-05
21 | Sine Sweep to 50 Hz and Delta II MECO | Jim Ryan |  |  | GBM PDR RFA 21 Response.doc |  | Approved |  | Closed | 2003-09-05
22 | Generate Strength Qualification Plans for GBM | Jim Ryan |  |  | GBM PDR RFA 22 Response.doc |  | Approved |  | Closed | 2003-09-05
23 | GBM Detector Thermal Analysis | Tom McCarthy | DJO | GBM CDR | GBM PDR RFA 23 Response RevA.doc |  | Addressed at CDR |  | TM approved via email 7/13/04 | 2004-07-13
24 | Independent Verification of Software Algorithms | Ron Zellar |  |  | GBM PDR RFA 24 Response.doc |  | Approved |  | Closed | 2003-09-05
25 | Consider Supplementing Software Staff | Ron Zellar |  |  | GBM PDR RFA 25 Response.doc |  | Approved |  | Closed | 2003-09-05
26 | Create an Algorithm Description Document | Ron Zellar |  |  | GBM PDR RFA 26 Response.doc |  | Approved |  | Closed | 2003-09-05
27 | Ensure Build 3 Delivery Prior to GBM Environmental Test | David Betz |  |  | GBM PDR RFA 27 Response.doc |  | Approved |  | Closed | 2003-09-05
[9 empty] | Total RFAs | 27
[9 empty] | # Closed | 27

## LAT dPDR
RFA # | Subject | Originator | Assignee | Response | Date Submitted to Systems | Project Office Review Status | Date Submitted to Code 300 | Closure Status | Closure Date
1 | Energy Balance of Arithmetic Nodes | Tom McCarthy |  | LAT dPDR RFA 1 Response.doc |  |  |  | Closed | 2003-04-17
2 | Qualification Levels Based on Acceptance Levels | Tom McCarthy |  | LAT dPDR RFA 2 Response.doc |  |  |  | Closed | 2003-04-17
3 | Consider Single Point Failures of TCS Elements | Tom McCarthy |  | LAT dPDR RFA 3 Response.doc |  |  |  | Closed | 2003-04-17
4 | Consider the Use of TOTS | Tom McCarthy |  | LAT dPDR RFA 4 Response.doc |  |  |  | Closed | 2003-04-17
5 | Use Qual Levels in Electronics Box Worst Case Thermal Analysis | Tom McCarthy |  | LAT dPDR RFA 5 Response.doc |  |  |  | Closed | 2003-04-17
6 | IR Camera Test to Assess Workmanship | Tom McCarthy |  | LAT dPDR RFA 6 Response.doc |  |  |  | Closed | 2003-04-17
7 | Thermal Engineer Coverage During TV/TB Testing | Tom McCarthy | Bloom | LAT dPDR RFA 7 Response.doc |  | PM Approved 3/17/04 | 2004-03-22 | TM approved by email 4/6/04 | 2004-04-06
8 | Heat Pipe Stress Analysis | Tom McCarthy |  | LAT dPDR RFA 8 Response.doc |  |  |  | Closed | 2003-04-17
9 | Assess Ground Cooling Requirements | Tom McCarthy |  | LAT dPDR RFA 9 Response.doc |  |  |  | Closed | 2003-04-17
10 | Interface Delta T's at Shimmed Locations | Tom McCarthy |  | LAT dPDR RFA 10 Response.doc |  |  |  | Closed | 2003-04-17
11 | Thermal Cycling of Radiator VCHP/Grid Joint | Tom McCarthy |  | LAT dPDR RFA 11 Response.doc |  |  |  | Closed | 2003-04-17
12 | Radiator Panel Venting Analysis | Tom McCarthy |  | LAT dPDR RFA 12 Response.doc |  |  |  | Closed | 2003-04-17
13 | Tracker-Grid Heat Transfer Path | Tom McCarthy |  | LAT dPDR RFA 13 Response.doc |  |  |  | Closed | 2003-04-17
14 | IR Scan of Radiators Pre & Post Testing | Dennis Hewitt |  | LAT dPDR RFA 14 Response.doc |  |  |  | Closed | 2003-04-17
15 | Radiator Panel Venting Analysis | Dennis Hewitt |  | LAT dPDR RFA 15 Response.doc |  |  |  | Closed | 2003-04-17
16 | Interface Delta T's at Shimmed Locations | Dennis Hewitt |  | LAT dPDR RFA 16 Response.doc |  |  |  | Closed | 2003-04-17
17 | Define Cleanliness Requirements | Dennis Hewitt |  | LAT dPDR RFA 17 Response.doc |  |  |  | Closed | 2003-04-17
18 | Installation of X-LAT Plate | Dennis Hewitt |  | LAT dPDR RFA 18 Response.doc |  |  |  | Closed | 2003-04-17
19 | Implement a Continuous Risk Management Approach | Mark Goans | Horn | LAT dPDR RFA 19 Response.doc |  | PM Approved 4/4/04 | 2004-04-07 | MG approved via email 5/19/04 | 2004-05-19
20 | Integrated List and Schedule of all Simulators, Emulators, and Engineering Models | Steve Scott / Dennis Hewitt | Bloom | LAT dPDR RFA 20 Response.doc |  | PM Approved 3/17/04 | 2004-03-22 | SS approved by email 3/26/04 | 2004-03-26
LAT-TD-01137-01.pdf
[8 empty] | Total RFAs | 20
[8 empty] | # Closed | 20

## SC SRR
RFA | Subject | Originator | Responsible Org. | Assignee | Due Date | Response | Reviewed | Comments | Project Office Review Status | Status from SC PDR Charts
1 | Confusion over SC-LAT ICD Final Release | Dick Horn | Spectrum | Tim Morse | 2002-12-15 | Fixed in schedules |  |  | Closed
2 | Incorrect LAT CDR Date | Al Vernacchio | Spectrum | Chris Clark | 2002-12-15 | Fixed in schedules |  | no specific record | Closed
3 | LAT Purge Requirements for Relative Humidity | Dick Horn | GPO | Bernie Graf | 2003-01-01 | Absorbed by #42 |  | Folder RFA42&3&4 | Closed
4 | LAT Requirements for Helium Sensitivity | Sharon Seipel | GPO | Bernie Graf | 2003-01-01 | Absorbed by #42 |  | Folder RFA42&3&4 | Closed
5 | Resolve "If Possible" in Requirement MSS 3.3.3.4 | Joy Bretthauer | GPO | Norman Rioux | MPDR - 1 month | CCR 433-0139 |  | Folder RFA5 | Closed
6 | Operations Concept at 2 times LAT Data Rate | Steve Ritz | GPO | Al Vernacchio | 2003-01-01 | R. Cox documented response dated 4/3/03 | Ritz Approved - email to Deily | Folder RFA6 | Closed
7 | Safing Hierarchy | Art Whipple | Spectrum | Scott Fallek | 2002-12-15 | SAI memo dated 4/1/03 | Kendall emailed on 7/9/04 | Folder RFA7 | Open | Memo in work
8 | Review Impact of Power Safe Safe Mode with Instruments | Dave Lung | Spectrum | Scott Fallek | 2002-12-15 | SAI Memo dated 2/7/03 | Fault Mgmt & Response detail @ SC PDR "Power Safe Mode" Eliminated from SC Safe Mode design | Folder RFA8 | Closed
9 | Spacecraft Fault Management Requirements | John Deily | Spectrum | Scott Fallek | 2002-12-15 | Incorporated at PDR Dry Run #1 Presentation | Deily Approved |  | Closed
10 | Observatory CG Budget | Norman Rioux | Spectrum | Jordan Evans | 2003-01-15 | Done is SAI Systems Budget Charts |  |  | Closed
11 | 30% Heater Design Control Margin | Mark Melton | Spectrum | Aaron Gilchrist | 2003-01-15 | ECR003 and ECR061 approved @ SAI | Melton Approved | Folder RFA11 | Closed
12 | Resolver with Project the Intent of CDRL 29 | Arun Guha | Spectrum | Jordan Evans | 2002-11-27 | SAI Memo dated 12/16/02 Combined 12&13 | Deily Approved | Folder RFA12&13 | Closed
13 | Include Subsystem Requirements in CDRL 29 | John Deily | Spectrum | Jordan Evans | 2002-11-27 | SAI Memo dated 12/16/02 Combined 12&13 | Deily Approved | Folder RFA12&13 | Closed
14 | Work with Instruments to Understand Actions Necessary due to Anomalous Conditions | Al Vernacchio | GPO | Erik Andrews | 2002-12-15 | Andrews' spreadsheet describes content of 1553 I/F | EA comments: "With respect to the SC recognizing the instruments are alive, it is documented in the 1553 ICD, section 4.11. It basically states that a 'reporting/non-reporting' flag will be maintained for each instrument. That the receipt of telemetry is an indication that the instrument is alive. If no telemetry is received after X (ground settable) frames, the instrument will be flagged as not-reporting. With respect to the Instruments recognizing the SC is 'alive', the 1553 ICD, Section 4.5 documents the following: "If a payload stops receiving this message (Attitude updates), then the payload should assume that the S/C is entering safemode and that payload power may be removed at any time." This RFA can be closed." | Folder RFA14 Needs Al approval | Closed | Erik Andrews developed spreadsheet describing contents of 1553 interface. GPO reviewing.
15 | Reprogramming of the Mission and ISM CSCI | Erik Andrews | Spectrum | Scott Fallek | 2002-12-15 | SAI Memo dated 2/17/03 | Andrews Approved - e-mail to Deily | Folder RFA15&16 | Closed
16 | RAM Patching and EEPROM Reprogramming | Erik Andrews | Spectrum | Scott Fallek | 2002-12-15 | SAI Memo dated 2/17/03 | Andrews Approved - e-mail to Deily | Folder RFA15&16 | Closed
17 | Boot Level Requirements | Erik Andrews | Spectrum | Nick Gaudio | 2003-01-01 | Andrews' spreadsheet describes e-mail response | Andrews Approved - e-mail to Deily | Folder RFA17 | Closed
18 | LAT Key Parameters for Safing Instrument | Joy Bretthauer | GPO | Bernie Graf | 2003-01-01 | Captured in ICDs (e-mail from T. Morse dated 2/20/03) | ICDs in signature cycle | Folder RFA18&19 | Closed
19 | GBM Key Parameters for Safing Instrument | Joy Bretthauer | GPO | Bill Browne | 2003-01-01 | Captured in ICDs (e-mail from T. Morse dated 2/20/03) | ICDs in signature cycle | Folder RFA18&19 | Closed
20 | Examine Parent Requirement & Traceability for CDH50 | Joy Bretthauer | Spectrum | Jordan Evans | 2003-01-01 | Monitored Instrument items captured in ICD for final approval Only need to monitor analogs & discretes, not 1553 | Melton Approved - E-mail to Deily | SAI recorded action on website of e-version of SRR Action - note from J. Evans- needs Joy approval | Closed
21 | Trickle Charging Requirements | Joy Bretthauer | Spectrum | Robb Pinkerton | 2003-01-15 | SAI Memo dated 1/8/03 | Gaddy & Fantano approval emails to Deily | Folder RFA21&22 | Closed
22 | Cooling of Battery on Launch Vehicle | Joy Bretthauer | Spectrum | Aaron Gilchrist | 2003-01-15 | SAI Memo dated 1/8/03 | Gaddy & Fantano approval emails to Deily | Folder RFA21&22 | Closed
23 | Requirement for Lifting of Spacecraft and Observatory | Ed Shippey | Spectrum | Scott Dow | 2003-01-15 | ECR009 approved @SAI | Deily Approved | Folder RFA23 | Closed
24 | Define Requirements for Simulators (SIIS, CTS & MTS) | Al Vernacchio | Spectrum | Roger Jellum | 2002-12-27 | No specific SAI written response | EA comments:"There are no issues/concerns with the GBM SIIS. Some Details of the LAT SIIS usage remain in work. Specifically, assessing the amount of in-line testing the SLAC team plans to perform with the SIIS. These LAT SIIS testing usage issues are being worked in the normal course of business. This RFA can be closed." |  | Open | 11/27, 12/19 Telecons. GPO reviewing meeting
25 | SIIS Design & Test Consistent with other EGSE that Touches Flight Hardware | Dick Horn | Spectrum | Roger Jellum | 2002-12-13 | No specific SAI written response | EA comments: "This RFA addresses the safety concerns that SLAC has with using the SIIS to test / interface to its instrument. In December 2002 to GPO, and on Jan 3, 2003 to SLAC/MSFC, Spectrum presented their testing and Safety approach for the SIIS. This satisfied the intent of this RFA - it can be closed." |  | Open | 11/27, 12/19 Telecons. GPO approved.
26 | Develop a Plan for ITOS Use in SC & Observatory Testing | Al Vernacchio | GPO | Erik Andrews | 2002-12-15 | No specific SAI written response | EA comments: "A series of telecons were held with Spectrum in December and January, followed by an on-site meeting in late January. The approach is/was to define the boundary between the AstroRT system being used in SC/Obs I&T and the Ops Team using ITOS. This division of labor was being defined. With the addition of Mike Rackley to the team, Erik requested that Mike oversee this action. Personally, I feel this RFA can be closed, but you may wish to check with Mike to see if there is more information you'd find useful. (I have not been actively working this since the January meeting.)" |  | Open | Meetings in work for last week of January. Closed per GPO review.
27 | Simulator Functionality to Provide Intended Purpose | Joy Bretthauer | Spectrum | Roger Jellum | MPDR | "The content is going to be in the Simulators section of our PDR package." - JE, SAI |  | Needs Joy Approval | Open | MPDR Presentation includes requirements. GPO approved.
28 | X-Band Antenna Deployment System | Minh Phan | Spectrum | Deva Ponnusamy | PDR | SAI posted note to RFA on website 4/10/02 | response out for comment | Folder RFA28 | Closed | GPO approved
29 | Component Level Acoustic Test | Art Whipple | Spectrum | Scott Fallek | 2002-01-15 | SAI Memo dated 12/10/02 | Whipple Approved - e-mail to Deily | Folder RFA29 | Closed
30 | Request for Waiver for Box Level Thermal Cycling in Vacuum | Lou Fantano | Spectrum | Scott Fallek | 2002-12-15 | SAI memo dated 12/15/02 | Kendall emailed on 7/6/04 |  | Open | Waiver provide for TAM. GPO approved.
31 | Approach for Assessing Analysis Uncertainty in Pointing Analysis | Steve Ritz | Spectrum | Scott Dow | 2002-12-04 | No specific written response | Talk to Art |  | Open | Pointing TIM held 12/10 (rescheduled from 12/4). Meeting notes and charts provided to GPO. GPO approved.
32 | Single Point Hold Down on X-Band Antenna Deployment | Minh Phan | Spectrum | Deva Ponnusamy | 2003-01-15 | SAI Memo dated 1/10/03 | Minh Phan Approved - e-mail to Deily | Folder RFA32 | Closed
33 | Verification of Jitter from SADA & Gimbal | Minh Phan | Spectrum | Igor Lazbin | 2003-01-15 | SAI posted note to RFA on website 3/10/02 | response out for comment | Folder RFA33 | Closed | GPO approved
34 | Evaluate Sine Vibration of the Solar Array at the Subsystem Level | Minh Phan | Spectrum | Scott Fallek | 2003-01-15 | SAI memo dated 3/18/03 | Minh Phan Approved - e-mail to Bretthauer (forward by Connor) | Folder RFA34 | Closed | SAI Memo sent and in GPO approved.
35 | Document Requirement for Deployed Frequencies of Solar Array and X-band Boom | Minh Phan | Spectrum | Igor Lazbin | 2002-12-15 | SAI approved ECR023 for X-band boom Solar Array freq is goal | Minh Phan Approved - e-mail to Bretthauer (forward by Connor) | Folder RFA35 | Closed | Freqs defined, ECR to CDRL29 in work. GPO approved.
36 | Verification of Harnesses via Test | Joy Bretthauer | Spectrum | Robb Pinkerton | 2003-01-15 | SAI Memo dated 1/8/03 | Deily Approved | Folder RFA36 Needs Joy approval | Closed | ECR to CDRL 29
37 | EMI Testing of the Flight Battery | Joy Bretthauer | GPO | Fred Blanchette |  |  | Melton recommend closure - flight battery installed for Obs. EMI per CDR charts | Action to GPO | Open | Response in work by Project
38 | [8 empty] | Closed @ SRR
39 | Optical Bench Testing | Joy Bretthauer | Spectrum | Scott Dow | MPDR | Response onlineAI#0086 | Deily Approved | Folder RFA39 Needs Joy Approval | Closed | Resp. posted to SA GLAST website 2/21/03
40 | Review SC MAR for Vibration Testing Requirements | Joy Bretthauer | Spectrum | Scott Fallek | 2002-12-15 | SAI Memo dated 12/10/02 | Grady approval in SAI/GPO telecon discussing Dry Run Actions - Seipel e-mail Approval | Folder RFA40 | Closed
41 | Permissible level of He in GN2 for GBM | Joy Bretthauer | GPO | Bill Browne | SC PDR | No discussion of He in GN2 | Talk to Art re: He budgets | Action to GPO | Open | Issues captured in PDR package on He exposure
42 | Permissible level of He in GN2 for LAT | Joy Bretthauer | GPO | Bernie Graf | SC PDR | He & humidity rqmt documented in ICD, no discussion of He in GN2 | Talk to Art re: He budgets | Action to GPO | Open | Issues captured in PDR package on He exposure
43 | Quantitative AO Environment | Joy Bretthauer | Spectrum | Mark Porter | 2002-12-13 | SAI E-mail to J. Edmund 12/9 | Bretthauer Approved |  | Closed
FSRR1 | Investigate Whether the EEPROM on the RAD750 must be used to Boot | Robert Klar | Spectrum | Nick Gaudio | 2003-01-15 |  |  |  |  | Memo Describes the EEPROM use on RAD750
FSRR2 | FSW27 Clarification | Robert Klar | Spectrum | Cyp Colbert | 2003-01-15 |  |  |  |  | ECR 8 Approved to Address
FSRR3 | Common Elements Between the ISM Function and the Primary FSW | Robert Klar | Spectrum | Cyp Colbert | 2003-01-15 |  |  |  |  | See SE AI#88 Response on SA Website
FSRR4 | Include the SOW in the Requirements Flowdown | Joy Bretthauer | Spectrum | Cyp Colbert | 2003-01-15 |  |  |  |  | See SE AI#89 Response on SA Website
FSRR5 | Specify Complete Set of Initial Conditions for GNC Sun Capture | Art Whipple | Spectrum | Igor Lazbin | 2003-01-15 |  |  |  |  | Response posted to website 4/18/03
FSRR6 | Clarify FSW8 | Michael Briggs | Spectrum | Jordan Evans | 2003-01-15 |  |  |  |  | Typos fixed by ECR009 to CDRL29.
FSRR7 | Def. Of Temp in GNCDR51 | Norman Rioux | Spectrum | Igor Lazbin | [5 empty] | Response posted to website 3/10/03
FSRR8 | Review Reqs for Ambiguous Language | Norman Rioux | Spectrum | Jordan Evans | [5 empty] | Resp. posted to SA GLAST website 2/21/03.
FSRR9 | Correct Typos in FSW69 | Ross Cox | Spectrum | Jordan Evans | 2003-01-15 |  |  |  |  | "IEM" was not a typo. No action required.
FSRR10 | Additional Typos in FSW Requirements | Ross Cox | Spectrum | Jordan Evans | 2003-01-15 |  |  |  |  | Various correction, see OL95.

## ACD CDR
RFA # | Subject | Originator | Assignee | Response | Closure Status | Closure Date
1 | Evaluate delivery date and completion readiness of ACD EGSE software delivery for I&T | Fred Huegel | Dave Thompson | ACD CDR RFA 1 Response.doc | Closed | 2004-02-23
2 | Review ACD reliability analysis, assumptions and define key drivers with LAT to identify resolution | Dick Horn | Mike Amato | ACD CDR RFA 2 Response.doc | Closed | 2004-02-23
3 | Demonstrate adequate venting of the tile detector assemblies and the micrometeoroid shield | Jim Ryan | Tom Johnson | ACD CDR RFA 3 Response.doc | Closed | 2004-02-23
4 | Delineate plans and procedures for preventing helium contaminatijon of the PMTs during I&T | Joseph Bolek | Mike Amato | ACD CDR RFA 4 Response.doc | Closed | 2004-02-23
5 | Provide the concept and details for grounding the micrometeoroid shield | Ted Michalek Steve Scott | Tom Johnson | ACD CDR RFA 5 Response.doc | Closed | 2004-02-23
6 | Environmental testing at the system level should be at "qualification" levels not "acceptance" levels | Jim Ryan | Mike Amato | ACD CDR RFA 6 Response.doc | Closed | 2004-02-23
7 | Identify the document that defines the roles/responsibilities of personnel with respect to CM | Jim Ryan | Tom Johnson | ACD CDR RFA 7 Response.doc | Closed | 2004-02-23
8 | Check to make sure that the thermal conduction from the BFA to the LAT grid is representative of the planned mechanical connection of the BFA to the LAT grid. | Ted Michalek | Carlton Peters | ACD CDR RFA 8 Response.doc | Closed | 2004-02-23
9 | Mechanical loading cases should consider asymmetrical thermal loading | Ted Michalek | Ken Segal | ACD CDR RFA 9 Response.doc | Closed | 2004-02-23
10 | Complete the GAFE test procedure ASAP, and provide a copy | Fred Huegel | Glenn Unger | ACD CDR RFA 10 Response.doc | Closed | 2004-02-23
11 | Ensure that the correct fabrication standard is used for the FREE printed card. | Fred Huegel | Glenn Unger | ACD CDR RFA 11 Response.doc | Closed | 2004-02-23
12 | Are two modal surveys planned (required) | Jim Ryan | Mike Amato | ACD CDR RFA 12 Response.doc | Closed | 2004-02-23
13 | Describe in detail the problem reporting and corrective action system that will be used for ACD | Steve Scott | Ron Kolecki | ACD CDR RFA 13 Response.doc | Closed | 2004-02-23
14 | Is there a logistical support plan or spares plan | Steve Scott | Mike Amato | ACD CDR RFA 14 Response.doc | Closed | 2004-02-23
15 | Evaluate changing the baseline bottom tile mount concept to one that does not rely on a slipping interface | Gary Sneiderman | Ken Segal | ACD CDR RFA 15 Response.doc | Closed | 2004-02-23
16 | Identify TDA's that will/may require the most disassembly to access or replace/repair. | Dick Horn | Ken Segal | ACD CDR RFA 16 Response.doc | Closed | 2004-02-23
17 | Provide an explanation for the discrepancy in the duration of the integration activity | Mark Goans | Tom Johnson | ACD CDR RFA 17 Response.doc | Closed | 2004-02-23
18 | Present a QA plan for the fabrication work at Fermilab of the scintillator tile assemblies | Lowell Klaisner | Tom Johnson | ACD CDR RFA 18 Response.doc | Closed | 2004-02-23
19 | Provide a risk management plan for ACD | Dennis Dillman | Mike Amato | ACD CDR RFA 19 Response.doc | Closed | 2004-02-23
[5 empty] | Total RFAs | 19
[5 empty] | # Closed | 19

## LAT Peer Reviews
RFA # | Subsystem | Request | Reason | Originator | Assignee | Response | Originator Review Status
1 | Mechanical | Verify that Grid Finite Element Model reflects the flange cutaways for the downspout heat pipes. Assess stress concentrations at these reduced flange section areas | Cutting away the lower grid flange for the downspout pipes could significantly effect grid stiffness | Ryan | Campbell | The Grid has been re-designed to incorporate the spacecraft interface wing as an integral feature of the grid. The lower flange has been extended to become the wing. This removes the discontinuities that were in the old design. Analysis for this new design has just begun. ECD: 5/12/03 | Submitted
2 | Mechanical | Provide details of tracker to grid interface. How will mounting holes be drilled? What tolerances will be obtained for shear restraints? | Eight flexures are to be mounted between the tower baseplate and grid. Obtaining tight tolerance fits for fasteners and maintaining tower alignment requirements will call for detailed planning and precise workmanship | Ryan | Nordby | A TKR module is mounted to the Grid by way of 8 flexures, They extend down through the bay cut-out in the Grid top flange, and bolt to the side of the top flange with 12 shoulder bolts—1 bolt per corner flexure and 2 bolts per mid-side flexure. These mounts provide the sole means of both TKR module alignment and structural support. On the TKR side of the interface, the holes in the flexure are established during assembly of the bottom tray. The tray close-out is assembled using a jig which accurately locates the 4 titanium corner bosses and close-out side pieces. The jig also holds these in place during curing of the structural adhesive which holds the pieces together. As part of this assembly process, the corner flexures are pinned and bonded to the titanium corner bosses). Once the tray is cured, holes are machined in the corner flexures using drill bushing that are machined into the assembly jig. Likewise, the mid-side flexures are accurately located on the close-out and bonded in place, using the jig for alignment. The result of this process is 12 flexure holes which are 25 microns oversized, located to an absolute accuracy of 12 microns (TBD) with respect to the bottom tray. During module stacking, and wall bolt-up, the perpendicularity of the sidewalls is established by the bottom tray. Thus, the overall alignment of a module is held very tightly, with little tolerance build-up, with respect to the holes in the flexures. On the Grid side of the interface, the mating hole features for mounting the flexures are counterbored holes and tapped holes for locating the shoulder bolt and carrying shear, and a for locking the bolt in place. The holes are positioned and drilled using a jig . This jig is fabricated with the bottom tray assembly jig, and the mating holes are match-drilled. This ensures that the flexure and Grid holes line up exactly, to the degree of repeatability of the hole drilling process. On the Grid side of the interface, the counterbored holes are expected to be aligned to within 25 microns (TBR) with respect to true position. The jig will be positioned in the Grid bay by two pins located on the top flange of the Grid. Vertical position and pitch/yaw attitude of the jig will be established with respect to the Grid primary datum feature (the bottom of the Grid at the corners) and not the local surface of the top flange. This eliminates the tipping error associated with the planarity tolerance of the Grid top surface. A secondary issue associated with TKR module positioning is assuring that the flexures can provide adequate range of flexing in their as-installed position. This is determined by the tolerance of position and perpendicularity of the Grid top flange sidewall with respect to the flexures on the orthogonal sidewalls. To accommodate this need, the Grid top flange sidewalls will be toleranced with respect to the same pin holes in the bay that are used to position flexure holes. This eliminates tolerance build-up which would limit the flexure range-of-travel. TKR flexures requirements are that they be positioned to within +/- 0.2 mm (TBR) of their true position. Current plans for Grid machining include machining the sidewalls to a profile tolerance of 0.25 mm (double-sided), which provides 0.15 mm of margin. | Closed
3 | Mechanical | Recommend conducting a fail safe fastener analysis for all bolted interfaces. | Analysis assures that no single bolt failure will lead to significant degradation in LAT structural performance. Where fastener patterns are not fail safe, more detailed analysis/inspections would be required. | Ryan | Nordby | Failure of structural components and structures is explicitly exempted in MSS 3.3.1.5.1, so none is planned. Stress analysis of all bolted interfaces has (or will) show positive margins for all joints and bolting hardware. Furthermore, qualification testing at the subsystem level will demonstrate that the design can endure loads and stresses associated with protoflight or qualification environments. Finally, all bolted joints will be subjected to verification testing at either the subsystem or LAT level (or both) to verify workmanship. The GLAST PO and LAT consider this adequate for mitigating the risk of fastener problems during launch. | Submitted
4 | Mechanical | Evaluate effect of overconstraint at LAT/spacecraft interface in pointing error analysis for on orbit conditions and quantify disruption that could be imposed by spacecraft onto LAT interface. | The overconstraint of the LAT/spacecraft interface can result in distortions on orbit. Pointing error analysis should be performed for these on orbit conditions, distortion f the spacecraft interface will also effect the redundant LAT interface. | Mignosa/Ryan | Nordby | This is one of many load cases planned to be analyzed in evaluating the coupling of the LAT and SC as it relates to pointing knowledge error. The LAT plans to run these analyses following completion of the CDR design load case analyses. | Close @ CDR
5 | Mechanical | Static load cases should include a 0 g or tension load in the thrust direction with lateral loads | Interface loads at the LAT/spacecraft and subsystem interfaces should include maximum axial tension load case combinations or evaluate interfaces with fully reversible loads. | Mignosa/Ryan | Nordby | Tension/negative thrust accelerations have been added to the list of LAT load cases, for completeness. Results of these load cases will be part of the CDR structural results. | Close @ CDR
6 | Mechanical | Demonstrate stress and distortions generated from all thermal cases on LAT for E-boxes and X-LAT Plate using updated interface design do not negatively impact thermal or structural margins (at this interface) | Recent changes to the E-box/X-LAT plate have not been finalized and analysis results on this issue have not been verified. (Or their impact on the design) | Fransen/Ryan | Nordby | The Peer Review structural model did not include the recent changes to the electronics box structural mounting to the CAL and X-LAT Plates. These changes have now been incorporated into the model, and interface loads presented at the CDR will include these interfaces. Furthermore, structural load cases for extreme qualification-level thermal environments have been modified to adequately bound these extremes (see also Mech RFA #24). | Close @ CDR
7 | Mechanical | Add to LAT Environmental Specification a loads recovery section for the TEMS to X-LAT interface loads. | This interface is being revised and, as currently envisioned, will not completely decouple the TEMS from the X-lat plate. Therefore, loads recovery is necessary here. | Ryan | Nordby | The LAT-SS-00778 “LAT Environmental Specification” already includes interface structural requirements at the E-Box to X-LAT interface. This is specified in the form of peak transverse misalignment that must be accommodated by either side of the interface. This will be updated as part of the CDR analysis, and peak loads at this interface will be added. | Close @ CDR
8 | Mechanical | Provide delivery date for full-up LAT FEM dynamic model (2 – weeks post CDR suggested) | Mission CLA activities need replanning based on new model delivery dates. | Seipel/Ryan | Nordby | Current plans are to deliver the LAT CDR FEA model 4 weeks after the close of the CDR, assuming there are no CDR RFA’s which impact the FEA modeling. | Close @ CDR
9 | Mechanical | Perform a continuity check of all FEM models against current baseline design (CAD models, etc.). Once subsystem models are integrated into full-up LAT model, perform standard model checks (static equilibrium, free-free, grounding, etc.) and provide descriptions. Include verification that significant modes and shapes from each subsystem are captured. Verify all model translations, whether for unit conversion or software tool. | Necessary to insure model integrity to develop flight design loads and margins. | Seipel/Ryan | Nordby | Verification of subsystem models and model integration into the LAT FEA model is planned. Results of this will be part of the CDR material. Verification tests that are being run on all subsystem models:Subsystem model evaluation Review model—units, orientation/coordinate system, size, mesh resolution Review delivery report—do the report and model agree FEA model check-runsFree-free modal analysis—check model for mechanisms Translation check—check model for inadvertent grounding Gravity check—check that inertial loads are reacted only at boundaries Temperature check—check that structure is free to expand/contract Analysis comparison runs Mass—compare model mass with subsystem estimate Center of mass—compare model center of mass with subsystem estimate Modal analysis—check against subsystem detailed model and report | Close @ CDR
10 | Mechanical | Complete design and structural analysis of S/C to LAT interface. Present margins of safety for LAT side of interface hardware | CDR Closure | Seipel/Ryan | Campell | Analysis is in work. ECD: 5/12/03
11 | Mechanical | Complete ICDs and IDDs between LAT subsystems. For specific items that can not be closed by CDR, present a closure plan w/ associated schedule and risk mitigation plan | CDR Closure | Seipel/Ryan | Nordby | The following is a list of ICD’s and IDD’s within the LAT, and their status as of the response date listed, updated status and closure plan will be provided at CDR: LAT-DS-00040-09: LAT Envelope—released (14 Apr 03) LAT-DS-00038-4: LAT Instrument Layout—first draft being checked (14 Apr 03) LAT-DS-00233-3: CAL-LAT IDD—final check prior to release (14 Apr 03) LAT-SS-00238-4: CAL-LAT Mech, Therm, Elec ICD—released LAT-DS-00309-1: ACD-LAT IDD—final check prior to release (14 Apr 03) LAT-SS-00363-4: ACD-LAT Mech, Therm, Elec ICD—released LAT-DS-00851-1: TKR-LAT IDD—first draft underway (14 Apr 03) LAT-SS-00138-5: TKR-LAT Mech, Therm ICD—released LAT-DS-01630-1: Electronics-LAT IDD—first draft underway (14 Apr 03) LAT-SS-01794-1: Elec-LAT Mech, Therm ICD—first draft underway (14 Apr 03) | Not Accepted
12 | Mechanical | 1) Address the intermetallic layer issue at the friction joint of the bimetallic joint for VCHPs. 2) What does LMC do from a manufacturing process point of view to preclude this layer from forming during the integration welding process, including temperature control during processing? 3) Do LMC CCHPs use a friction weld to cap off CCHPs? | NASA GSFC has learned 1st hand of the intermetallic layer formation at the friction joint and associatedprocess requirements | McCarthy | Morrison | Leakage through intermetallic layers is an issue in pressure vessel design. It can be aggravated by the friction-welding process since these layers can be aligned to result in leak paths. LM has instituted strict controls on material purity to preclude the formation of intermetallic layers which can lead to leakage. Temperatures are controlled during subsequent fusion welding processes to remain below approximately 200 oF. Fusion welding is automated, allowing minimum heat input to the parts. Inert gas flow provides sufficient cooling to limit temperatures during and after the welding process. This ensures that material integrity is not compromised due to overheating. LM has had no failures in these joints in over 15 years of flight experience using our material and process controls | Submitted
13 | Mechanical | 1) Add a stowed SA case for CDR 2) Add a "HP Anti - Freeze Heater" Fail On Case | Cases will make matrix of analyses more complete | McCarthy | Wang | 1) Stowed case has been run and results coordinated with Spectrum Astro. The limiting LAT component is the VCHP reservoirs; nominal timeline for heater activation is about one hour from launch. Contingency action timeline established with Spectrum at 3 hours post launch. 2) Agreed HP Anti-freeze heater failed on case has been added to analysis matrix (Data Provided) | Closed
14 | Mechanical | Define flight heater sizing methodology/philosophy | None provided | McCarthy | Wang | Heaters are sized for at least 30% margin at minimum voltage | Closed
15 | Mechanical | Evaluate the thermal margins for a move back to the YS90 tracker sidewall material from the current K13D baseline material | Risk mitigation in case K13D material allowables turn out to not meet requirements | Seipel/Ryan | Wang | Agreed, Analysis case has been added to the plan to support this potential trade study with tracker subsystem | Closed
16 | Mechanical | Raise ACD survival temperatures limit to -25C (from -40 C current limit) | The current -40 C survival limit for the ACD is driving the design of the lower scintillator tile flexures. Data shown on page 4-15 predict -19.1 C survival limit for the ACD with a 5 C uncertainty factor. Also, this predict is at the "coldest extremity" of the ACD which most likely is the "top" of the ACD (A significant distance removed from the lower scintillator tiles) | Ryan/Rodini | Wang | Lower limit of –40C has been reviewed and accepted by the ACD, the lower limit protects flight design margin and flexibility during subsystem & system test. | Closed
17 | Mechanical | Determine necessary interface information, including needed delivery date from vendor for design of acoustic testing MGSE to simulate S/C | Define outstanding interface requirements & schedule so project office can establish CDRL for spacecraft. | Seipel/Ryan | Nordby |  | In-Work
18 | Mechanical | Consider requesting a set of S/C flexures to use during dynamic testing of LAT. These flexures could (should) also be used to strength qualify the grid structure. Strength qual of full up LAT instrument is not planned. Also, recommend that tracker simulator with flexures be used to qualify the tracker interface. | S/C flexures will provide much more realistic boundary conditions & interface loads for the LAT. It will be very difficult with a rigid mount (or semi rigid mounts) to get accurate stresses (including moments) into the LAT S/C interface | Mignosa/Ryan | Nordby | SC flexures have been considered for use during LAT environmental testing, but their use has not been baselined. While the use of the SC flexures is conceptually appealing, the logistics and complications of implementing them into the LAT test planning was deemed not worth the additional cost (dollars and risk) associated with using them. The LAT is currently investigating either a fixed-base or flexing mount to STE for structural/dynamics testing. The constraint is that the mount must not load the LAT-SC interface region beyond its design and test limit loads. The option to use the SC flexures will be revisited post CDR as a mitigation to the concerns noted as part of the final selection of the STE interface approach. Regarding strength testing of the Grid, Grid bays will be proof tested one at a time, using STE to pull on all eight support points simultaneously. This fixture has not yet been designed, but it is intended to load the Grid interface in a manner consistent with the flight interface. Using flexure-like mounts is one means to accomplish this. | Not Accepted
19 | Mechanical | Conduct cross-orthogonality check of test (ASET) instrumentation with full FEM (GSET). These results should pass standard criteria (In GEVS) for all modes desired to establish correlation of LAT FEM. These results may need to be re-run as instrumentation set is modified (locations changed) | Proper pre-test analysis is required to assure instrumentation (accelerometer locations) are adequate to properly resolve desired mode shapes | Fransen/Ryan | Nordby | Pre-test analysis is planned for all LAT dynamics tests, but will not be completed until after CDR. | Closed
20 | Mechanical | For all instrumentation which flies, please update relevant mass report entries for these items | Ensure all flight mass is in budget | Seipel/Ryan | Nordby | Once instrumentation and cabling is chosen, they will be added to the mass report. Until such time, they are carried as a lien on the LAT mass reserve. Selection and baselining of the fly-away test instrumentation is planned to be complete by August, 2003 | Closed
21 | Mechanical | Consider addition of a backup test heater in the radiator survival heater system to prevent possible freezing of the ammonia during T/V testing to mitigate an operational anomaly | Test anomaly could damage flight hardware | Knudson | Wang | Need for back-up test heater has been mitigated through fail safe T/V environmental control approach. Damage would require primary, redundant anti freeze heaters and chamber environmental control systems to fail simultaneously
22 | Mechanical | Verify that a tracker hot design case that assumes a leaky MLI blanket (E* - 0.03), Germanium Black Kapton outer ACD blanket Layer and high emittance tracker side walls does not exceed current hot design case tracker thermal predictions | It was indicated that the current tracker design hot case assumes an effective MLI E* of 0.01. Typical uncertainty ranges from 0.01 –0.03, since germanium black kapton will run 40 C to 60 C in sun, this may produce a hotter tracker max predict on the sun side of the LAT. | Fantano/ McCarthy | Wang | Agree, CDR analysis case includes MLI E* -.03 | Closed
24 | Mechanical | Ensure that the thermal load cases chosen for analysis envelope the expected worst case ground test Qual level temperature. See Chart 3.11) | Tracker temperature 30 C / Qual survival 50 C. Do not want to expose structure to a load case that has not been considered in the analysis | McCarthy | Nordby | The thermal soak structural load case has been modified to reflect worst-case hot and cold survival soak temperatures for subsystems. Results of this load case are planned to be part of the CDR material. | 4/21 CLOSED
25 | Mechanical | Ensure test instrumentation is correlated to flight thermistors, especially on the Tracker, at the unit level | This correlation is important to achieve in order to carry forward into system level testing since test instrumentation may be limited at the system level | McCarthy/ Schirle | Wang | Correlation of flight thermistors at unit level will be done for both the Tracker and Calorimeter to establish limits at LAT level TVAC test. | Closed
27 | Mechanical | Please identify and capture development of process specifications for adhesive applications, painting (if any) etc….(anodize, iridite, plating, etc. if not provided by piece part vendor. | Necessary to complete documentation set. | Seipel/Ryan | Campell | LAT processes are being developed by Jerry Clinton. MECH specific processes will be developed and written prior to flight hardware assembly. Here is a list of processes MECH will use in the assembly of the Grid Box Assembly. (Data Provided) | Submitted
28 | Mechanical | Review heat pipe installation to see whether any protection covers can be used during ground handling and mechanical operations to prevent any accidental damage. Both the grid and radiator design appears to be vulnerable to damage. | Risk exists without any protection covers. If any were damaged it would cause severe cost and schedule penalty. | Knudson | Campell | Protective covers will be used for as long as practical. They have been added to the MECH MGSE list. | Closed
29 | Mechanical | Establish a realistic schedule for drawing release with “buyin” from all parties required for process completion, i.e. design engineering, check, stress, configuration management, etc. | Drawing release schedule provides valuable insight into project planning by identifying manpower needs and tasks to be completed. | Menning | Campell | The drawing release plan is being revised to add time for feedback from the interested parties. ECD: 5/12/03 | Submitted
30 | Mechanical | Provide evidence/reasons why MLI thermal blankets used on the LAT will not fail due to atomic oxygen degradation/erosion at the location of micro-cracks in the Germanium plating on the kapton. | Experience on space station and other space hardware in low earth orbit has shown failure of kapton coated with brittle coatings (silicone oxide and vapor deposited aluminum) due to atomic oxygen erosion at the location of micro-cracks in the coating. Isn’t this an issue with the LAT blankets? | Menning | Wang | AO Effects on Germanium Black Kapton have been documented in 28th International SAMPE Technical Conference Nov 1996. Pristine Germanium Black Kapton showed no significant effects from AO. | Not Accepted
32 | Mechanical | Verify ESD requirements are correctly flowed down to LMC from LAT | Currently no ESD requirements specified | Knudson | Campell | Working with ELEC to define applicable ESD requirements to flow down to LM. ECD: 5/12/03 | Closed
33 | Mechanical | The plan is to put the anti-freeze heaters on the front/FOSR side of the radiator and have the FOSR cover the heater. I recommend looking at the impact of putting the heater on the backside. At the temperatures the anti-freeze heaters will operate, the panel gradients should be small (small qdot = small delta T). | FOSR over the heaters may be an unnecessarily complex interface and result in unexpected lifting of the FOSR in the flight configuration | Schirle | Morrison | An analysis was conducted to assess the impact of placing the heat pipe anti-freeze heaters on the backside of the radiators. Results from the study show that survival antifreeze heaters placed on the backside of the radiator result in a minimal impact to the survival heater power required (from 89W to 91W) indicating the feasibility of placing the heaters in this location. We will continue to investigate the potential of moving the anti-freeze heaters to the back side of the radiator panels. | Submitted
34 | Mechanical | Verify that proposed Vel-therm X-LAT to electronics thermal joint design thermal performance does not degrade over time (aging issue), after multiple installation/de-installations, and during the course of the mechanical vibration these program. | The proposed thermal interface material is relatively new with limited flight history. Its advertised thermal performance relies on relatively low thermal contact pressure. It is not obvious that repeated installations/de-installations will not result in carbon fiber breakage and thermal performance degradation. It is also not obvious that the low pressure contact thermal performance will not degrade over time and exposure to the mechanical vibration environment. | Fantano/ McCarthy | Campell | A qualification program will be developed for this interface to address these issues. However, the Wide Field Planetary Camera-3 (WFC3) is a GSFC program that used this material. The instrument is waiting to fly. Therefore, it must have qualified and acceptance tested. If GSFC could provide the details of what testing was done and the test results, it would streamline our testing. Perhaps there is Qual by Similarity possibilities here that would reduce costs as well. | Not Accepted
35 | Mechanical | Evaluate performing LAT modal survey and sine vibe testing using spacecraft flexures so that mode shapes, shear forces, strains, distortion etc. of the flexures/grid/cal plate combination matches those predicted for the hardware based on existing FEM models. | If test condition/constraints are significantly different than existing FEM models then a whole new set of intermediate (and not necessarily meaningful) modes needs to be evaluated and understood. Be careful in establishing orthogonality criteria for modes shapes so that extensive analysis does not result. | Menning | Nordby | See the response to RFA #18. SC flexures have been considered for use during LAT environmental testing, but their use has not been baselined. While the use of the SC flexures is conceptually appealing, the logistics and complications of implementing them into the LAT test planning was deemed not worth the additional cost (dollars and risk) associated with using them. The LAT is currently investigating either a fixed-base or flexing mount to STE for structural/dynamics testing. The constraint is that the mount must not load the LAT-SC interface region beyond its design and test limit loads | Submitted
36 | Mechanical | Define allowable load transfer into LAT (or radiator strut stiffness) at connection of radiator to s/c. | Necessary to define interface requirement to insure positive radiator margins of safety. | Seipel/Ryan | Campell | An effective stiffness of the spacecraft support strut of at least 200,000 lb/in (strut plus Spacecraft) was used in the Radiator analysis. This should be flowed down to Spectrum Astro in the S/C working group or as a requirement from GSFC to Spectrum. | Submitted
37 | Mechanical | Limit load tests should qualify the design (1.25 x flight limit loads) | Limit load was specified as test level and did not include the 1.25 qual (or protoflight) level. | Ryan | Morrison | Lockheed Martin concurs with the recommendation to increase the yield factor of safety from 1.1 to 1.25. This recommendation has been forwarded to SLAC to update the X-LAT Level-IV Specification to reflect this change. The Level IV spec will be revised. ECD: 5/12/03 | Submitted
38 | Mechanical | Update yield F.S. to 1.25 (currently @1.1). Verify that this requirement has been flowed down to all other subcontractors. | The yield FS is required to be 1.25 (not 1.1) per GEVS. This also assures consistency with test margin of 1.25, to minimize likelihood of yielding during strength test. | Fransen/Ryan | Morrison | Lockheed Martin concurs with the recommendation to increase the yield factor of safety from 1.1 to 1.25. This recommendation has been forwarded to SLAC to update the X-LAT Level-IV Specification to reflect this change. The Level IV spec will be revised. ECD: 5/12/03 | Submitted
39 | Mechanical | Provide more detailed summary of stress margins of safety for the LAT instrument. | A detailed summary of margins of safety is typically presented at CDR peer reviews. Detailed, CDR level, margins of safety were not presented except for the radiator subsystem. | Mignosa/Ryan | Campell | Stress analyses are in work. ECD: 5/12/03 | Submitted
40 | Mechanical | Review high conductance graphite interface material available from a company named “UCAR” (formerly part of Union Carbide). They have high conductance graphite material gaskets greater than 10 milo in thickness. They have space experience. | You indicated a need for a thicker material. This company sells space qualified graphite gaskets of various thicknesses. | Knudson | Campell | Received 0.020” & 0.025” thick samples from Vendor. While the material (Grafoil) has excellent compressive properties, it has very low tensile strength (~1,000 psi). Therefore, when bending the material, it breaks. We are investigating laminated versions of the product to see if they are feasible for this application. | Submitted
41 | Mechanical | Verify that the flight data certification packages that accompany hardware delivered by Lockheed to SLAC are consistent with NASA Quality Assurance Requirements. | Flight data certification packages are essential to mission quality assurance. They have to be compliant with NASA standards. | Fantano/ McCarthy | Campell | NASA has not imposed any requirements for data package requirements on LAT (per Darren Marsh). However, Lockheed’s data package will be consistent with the LAT’s internal requirements (Mechanical to I & T) and their own standards for their Government Customers. | Submitted
42 | Mechanical | 1) What is the detailed schedule for completion of the EM Test program for the X-LAT Thermal/Mech Design, will it be complete by CDR? 2) What is the back-up design if the EM program is not successful using Vel Met? New baseline is unconventional | EM closure plan not provided. Design of the X-LAT/Electronics Box integration hinges on a success of this program, as well as successful CDR | McCarthy | Campell | 1)See EM test program schedule 2) Back-up designs (in no particular order) a)“Thick” RTV bond line between E-box and X-LAT plate with a 0.0005 inch thick Teflon film between one of the interfaces to allow disassembly. The existing push-pull bolts would still be required for Z axis restraint (parts are not bonded together). b) A thermal strap that is laminated with the Grafoil (high conductance graphite, see RFA # 40).c) Delete existing X-LAT plate and rigidly attach the X-LAT heat pipes to the E-boxes. The heat pipes would become the flexible member. A cap would fit over the entire assembly to act as EMI enclosure. Variation on this is a X-LAT plate that ties the E-boxes together, but is not tied to the EMI skirt. This keep the boxes moving in phase. | Closed
43 | Mechanical | Consider including GRID & DSHPs in the “Complete TCS” TB test. Schedule chart 1.2-4 shows cycling of grid assy by ¾ with “complete TCS test” in 6/04. Chart on page 3.1-10 conveys this config for the TB test | Complete verification of the core of the TCS prior to instrument integration would reduce risk. Need to clearly define what is part of the TCS TB test. | McCarthy | Campell | Definition of the test & hardware requirements is in work. Examining schedule options including combining the thermal vacuum acceptance testing of the radiators & X-LAT plates with this TCS TB test. The Grid delivery to I&T need date currently precludes its availability for this test, but will be part of configuration trade study (configuration vs. cost, schedule & risks mitigated). ECD: 7/13/03 | Closed
45 | Mechanical | GSFC (Brad Parker/Materials Board) provide recommendation to SLAC/LM team regarding the use of bimetal element used in heatpipes | Ensure LMC manufacturing process is compliant with recent GSFC experience. | McCarthy | Morrison | Leakage through intermetallic layers is an issue in pressure vessel design. It can be aggravated by the friction-welding process since these layers can be aligned to result in leak paths. LM has instituted strict controls on material purity to preclude the formation of intermetallic layers which can lead to leakage. Temperature control is not directly applicable to the friction welding process, however other process controls on weld energy are used in conjunction with weld process certification to carefully regulate weld quality. LM has had no failures in these joints in over 15 years of flight experience using our material and process controls. | Not Accepted
46 | Mechanical | Consider defining a “control performance” test for each VCHP that verifies ability to entirely block off the condenser, as well as ability to run full open under spec boundary conditions | Mitigation for late find of under spec control performance found at panel level. | McCarthy | Campell | Will add a “Qualification” (one time-one part) test to the Lockheed Martin Radiator specification and/or SOW. ECD 5/12/03 | Submitted
47 | Mechanical | Recommend use of a more standard approach to carrying load at the Cal/Grid interface by incorporating slip fit shear pins. The areas of particular concern are the fasteners near the spacecraft interfaces | Current plan is to use an unconventional combination of friction, epoxied fasteners and backing plates. | Ryan | Nordby | This has been identified on the LAT risk list. The shear pin design has been baselined, but the design with current lateral loads shows significant negative margin. Closure plan includes re-assessing lateral input loads as generated from the CLA. Shear pin prototype testing is on-going, and results will be addressed at CDR. | Submitted
48 | Mechanical | Have strength qualification requirements been flowed down to the electronic boxes? Are interfaces (box to box) qualified for strength and are boxes being qualified with sine burst testing? | Missed the Peer review on this part of the LAT design | Ryan | Nordby | The LAT Environmental Specification flows static-equivalent accelerations and interface limit loads down to the Electronics subsystem for box design, analysis and testing. Qualification of box designs will include sine burst testing, among other dynamics tests. | Closed
1 | ACD | Evaluate delivery date and completion readiness of ACD EGSE software delivery from Code 584 to Code 568 for I&T activities. If warranted, identify and provide experienced Code 584 personnel (civil servant and/or contractor) to assist present 584 ACD S/W engineer to assure timely delivery and completion of the ACD EGSE software. Identify the type of support, schedule, and deliverable items help that are needed. If a support contractor is identified to support this task, Code 584 and the ACD Project to coordinate in provide funding. | Concern was raised by Mr. Jim La, ACD I&T Lead from Code 568, on the timely EGSE software delivery to I&T from Code 584. In May 2002, 584 was tasked to provide to Code 568 (via SOW): 1. Design, develop, and deliver Python (was SCL)+ scripts and Qt (was Labview) Graphical User Interfaces (GUIs) to test the assembly of the ACD subsystem through ACD integration and test. 2. Assist Goddard personnel in writing ACD assembly test procedures. 3. Assist Stanford Linear Accelerator Center (SLAC) personnel in debugging their AEM simulator through the creation of test Python (was SCL) scripts. 4. Provide technical oversight on how the ACD EGSE works from an Python/Qt (SCL/Labview) perspective (including AEM database). This oversight is needed through both I&T and environmental testing. Because the complexity of the task, additional resources may be needed to assist the current 584 effort so that timely delivery and completion of the ACD EGSE S/W may be produced. | Huegel | Thompson | We expect a new EGSE hardware and software delivery from the LAT in April and another one in July. We have assembled a requirements document for the required EGSE software for these systems. Three milestones are identified: April 15 – Ability to handle GARC commands and readback (single FREE card with one GARC and one GAFE), exercise some test scripts, display simple pulse height histograms, and monitor some items for status and alarms. May 15 - Add full pulse height histograms and spectrum fitting. August 1 – Full functionality (not in final form) for full ACD. We are meeting regularly with Code 584 (John Donahue) and contractor software engineers with considerable EGSE experience (Greg Greer and Bruce Wendel). They are reviewing requirements and will develop an implementation plan by about March 1. We are considering sending the software engineers (at least one) to SLAC for several weeks to work with the new system before it is delivered to Goddard. | Closed
2 | ACD | The ACD Reliability requirement is .96 at 5 years, current estimate is .92. ACD requested to review reliability analysis, assumptions and define key drivers with LAT System Engineering and Instrument Scientist to identify resolution. Note: A splinter was held 8 Jan 03. Three preliminary alternatives were discussed, the key driver is loss of single tile assumptions which appear to be overly conservative relative to the supporting science requirement at end of life. LAT Scientist, System Engineering and ACD Subsystem closure plan in work to verify science design margin and updated assumptions. It is expected that this review will result in ACD meeting their reliability requirement of .96 | ACD subsystem reliability allocation is required to support overall LAT Mission requirements at 5 year life. | Horn | Amato | The ACD Reliability requirement is 0.96 at 5-years, but the current estimate is 0.92. The key driver to this estimate not meeting the reliability requirement is the fact that one penetration to the Micrometeoroid Shield (MMS) constitutes a failure to meet the ACD detection efficiency requirement of 0.9997. The ACD team will take the following steps to resolve this RFA. The changes described in this document shall be incorporated prior to LAT CDR in April 2003. 1) The LAT Instrument Scientist, Steve Ritz, has written a rationale of why two or more penetrations of the micrometeoroid shield constitute a failure to meet science requirements, rather than a single penetration. This document, LAT-TD-01591-01, has been placed into the Cyberdocs system and is attached to this response. The LAT mission objectives can still be met if the MMS has one penetration, rendering one tile nonfunctional, even though the overall ACD efficiency in this case would be less than 0.9997. 2) The ACD Reliability Engineer, Tony DiVenti, shall update his reliability calculations based on the new definition for an ACD MMS failure. The document to be modified is the “Worst Case Analysis & Reliability Assessments for the GLAST Anticoincidence Detector (ACD)”, ACD-RPT-00047. The ACD has assigned a 0.99 probability that the MMS will have no more than one penetration over the 5-year mission. With this change the ACD meets the 0.96 overall reliability requirement. 3) Two Level 3 requirements shall be changed to incorporate the change that with one MMS penetration the LAT system can still meet all mission requirements even if the ACD does not meet the 0.9997 detection efficiency requirement. The level 3 requirement 5.23.2 “Micrometeoroid Protection” shall change from 0.01/yr mean rate of penetrations to 0.02/yr. The level 3 requirement 5.24 “Performance Life” shall be amended to clarify that the ACD will maintain performance except for the possibility of loss of one tile due to penetration. 4) Although not explicitly referenced in the RFA, the following information is pertinent to the resolution of this problem. The reliability numbers originally used for the MMS were based on a 1996 Orbital Debris Model, ORDEM96. Recently, the ACD has been given direction that the requirement has been changed to use the ORDEM2000 model. In addition, the maximum altitude now being considered for GLAST has been raised from 515 km to 575 km (worse from the point of view of micrometeoroids and orbital debris). The ACD has tasked Johnson Space Center to redesign the MMS to meet the 0.99 probability of no more than one penetration for the ORDEM2000 model and an orbital altitude of 575 km. This redesign is expected to require only minor changes to the micrometeoroid shield design. | Closed
3 | ACD | Demonstrate adequate venting of the tile detector assemblies and the micrometeoroid shield. | Tile detector assemblies are wrapped well to be light tight. Trapped air must be adequately vented to prevent damage to light tight covering during ascent. The micrometeoroid shield (MMS) venting scheme was not clear at CDR. Need to finalize the design and demonstrate that trapped air can adequately vent from under the MMS. | Ryan | T. Johnson | The TDA’s are wrapped in two layers of black Tedlar for light protection. There are two separate vent paths for the TDA’s. The first vent path is designed into the fiber connector and is simply a 1mm square serpentine path that requires multiple (>10) bounces for the light to pass through. The second vent path is achieved by leaving a 2-3 cm long length of seam on each layer of Tedlar to be left unsealed. This can be done since there are multiple layers of Tedlar and the seams are on opposite sides so it would take multiple bounces for a light leak to occur.The MMS materials are all self venting, in that they consist of woven fabric and open cell foam. However they do have to vent at the edges. Therefore the edges will not be sealed and the volume of the MMS enclosed by the thermal blanket will be vented at the bottom of the TDA’s where there is a transition from having an MMS and Thermal Blanket to just having a Thermal Blanket. This is the same area in which the volume between the TDA’s and shell will be vented. This approach is similar to the one used for EGRET, which had a similar shield. | Closed
4 | ACD | Delineate plans and procedures for preventing helium contamination of the photomultiplier tubes (PMT’s) during ACD, LAT, and spacecraft integration. These should include:Sampling of purge gases to ensure no helium, Use of special purge lines (helium can pass through Tygon tubing). Actions to be taken if the helium detector alarm goes off. Plans for replacement detectors to be in place if the primary detector has to be removed. | The PMT’s are sensitive to helium contamination. The sensitivity was noted to be at the 5 ppm level, which is near ambient conditions. Protecting the PMT’s from contamination will be a challenge especially at the instrument and spacecraft level. | Bolek | Amato | We have recently revised our Helium sensitivity calculations and produced a detailed helium exposure requirements curve. The new curve and some updated information on how to assess helium exposure on the PMTs are included in an updated version of the document LAT-TD-00720 – ‘LAT ACD Phototube Helium Sensitivity’. Noticeable effects on the PMTs take quite some time near ambient and even at higher concentrations (over 10 weeks at double ambient helium levels). Because damage to the PMTs takes quite a bit if time we have decided we do not need continuous monitoring. Samples of purge gasses and of the room will be taken with a Helium monitor (the same one GLAS used) every 2 – 3 days and every time ACD or the PMTs are moved. Actions to be taken if Helium levels exceed the low threshold on the curve include increasing purge pressure (we will be purging with a dry nitrogen specified for low Helium levels and plan on using helium resistant purge lines), moving to constant monitoring and identifying the source. If the source can not be identified or is beyond our control and levels do not drop even with increased purge pressure, the PMTs and or ACD may have to be moved. Again the damage is quite slow, the requirement curve has quite a bit of margin in it (greater than a factor of 10) and we will have a running set of monitoring points to estimate total exposure to that point in I&T. Of course the urgency of the situation will depend on the accumulated exposure to that point (given our requirement and purging this is unlikely) which will be tracked using the monitor results. This information is currently in the process of being clarified on the ACD I&T plan. The requirements have been added to the latest draft of the Spacecraft IRD. It will be added to the GLAST LAT Contamination plan in its next update. We do not own a back up monitor but if the monitor becomes disabled we do have access to a Goddard sample collection service we used after the first PMTs arrived but before we had the monitor. The only disadvantage is that the results are delayed about a day. We are currently awaiting delivery of the Helium monitor that GLAS used. It is scheduled to be delivered to Building 2, Room 218 the first week of March. It does not come with an operating procedure, however we will generate one by March 28. The procedure will include standard operating procedures for the monitor, data recording tables, and procedures for handling high levels of Helium. | Closed
5 | ACD | Provide the concept and details of how the various layers of the micrometeoroid shield will be electrically grounded to prevent static charge build up within and between the layers. | It’s not obvious how this will be done since it seems to require a certain level of sheet electrical conductivity within each layer of the shield. | Michalek | Scott | The micrometeoroid shield will be sandwiched between a grounded MLI Thermal Blanket and a grounded piece of aluminized Kapton. The MLI and aluminized Kapton will be grounded following standard Goddard procedures, using ground straps attached to the LAT instrument grid. The grounding procedure is that used for the EGRET instrument on the Compton Observatory, which had a similar shield. | Closed
6 | ACD | Environmental testing at the system level should be at “qualification” levels not “acceptance” levels. If strength qualification can be demonstrated by subsystem tests and analyses, reconsider a full ACD system “sine burst” test. Examine test predictions from protoflight level random vibration and acoustics tests to see if one of these tests dominates (eliminate one or the other test?). | The “protoflight” approach requires qualification test levels on the flight ACD assembly. A full up ETU qualification was eliminated from the verification approach (cost/schedule considerations). ETU qual would have allowed “acceptance” testing of the flight ACD assembly. | Ryan | Amato | "Environmental testing at the system level should be at “qualification” levels not “acceptance” levels." We have since changed the levels planned for all environmental tests (including thermal vac) at the ACD full assembly level to ‘protoflight’ levels. These levels are defined as qualification levels which can be at reduced durations. One possible exception is mentioned below in response to your comment. “If strength qualification can be demonstrated by subsystem tests and analyses, reconsider a full ACD system “sine burst” test” We have reconsidered and will modify the ACD system sine burst test. Strength qualification tests have and will be performed on subsystem test components. The full mechanical structure will see a sine burst test to qualification levels prior to I&T. A sine burst test on the assembled ACD is not seen as necessary. “Examine test predictions from protoflight level random vibration and acoustics tests to see if one of these tests dominates (eliminate one or the other test?).” At the time of CDR the decision had already been made that random vibration tests would not be done at the full ACD assembly level because the acoustic loads dominate and in fact encompass our maximum launch loads. This approach has been discussed with LAT and has been agreed upon as an acceptable approach. Again, the ACD system level tests will be at protoflight levels. | Closed
7 | ACD | Although a web-based secure CM system (NGIN) was recently identified by the project, there was no mention of a CM document that defines the roles/responsibilities of personnel with respect to configuration management. Is there a requirement for a CM plan? If yes, does it exist? | Roles/responsibilities for CM did not appear to be documented. | Ryan | T. Johnson | Yes, there is a Configuration Management Plan for the ACD. It is ACD-PROC-000107, ACD Configuration Management Plan. We had experienced some previous difficulties with incorporating an ACD CM system with a system that the LAT Instrument Project Office wanted us to use. However it has been determined that we will use GSFC’s on-site Instrument Systems and Technology Center configuration management system for all ACD work internal to GSFC (Level 4 and greater tasks). Interface documents between the LAT and ACD (Level 3) will reside on the LAT CM system. This approach has been agreed to by LAT project management and is a system that will meet the needs of the ACD. | Closed
8 | ACD | Check to make sure that the thermal conduction from the BFA to the LAT grid is representative of the planned mechanical connection of the BFA to the LAT grid. | Since shims will be used to make the BFA to LAT grid mechanical joints, this may not give a good thermal conductive interface. | Michalek | Peters | Parametric study has been performed on conductance value between BFA and Grid. The results show that radiation and not conduction is the primary mode of heat transfer between the BFA and Grid. Utilizing radiation only the ACD requirements are satisfied, conduction does provide additional thermal support. | Closed
9 | ACD | Mechanical analyses that consider extreme thermal loading conditions should consider a case or cases where one or more of the five sides of the TSA are at the extreme hot temperature while the remainder of the sides are at the cold temperature. Such asymmetrical thermal loading should also be applied to the BEA/BFA structural analysis. | Thus far, mechanical loading cases have considered all five sides either at hot or cold extreme. It is realistic on-orbit that 1 or 2 sides could be facing the sun while the remainder of sides will see a cold environment. | Michalek | Segal | Asymmetric temperature loadings for the ACD were obtained from the ACD Thermal Engineer. Two cases were considered, hot case which is when the GRID and Tracker are in a hot case scenario and thermal hot case environmental parameters are applied and a cold case which is when the GRID and Tracker are in a cold case scenario and thermal cold case environmental parameters are applied. The cold case exhibited the highest temperature gradient across the TSA so the analysis was based on this case. The various temperatures were applied to the ACD FEM to produce the asymmetric thermal loading condition. The following tables show the results from the uniform temperature loading and the results from the asymmetric loading. (Data Provided) | Closed
10 | ACD | Complete the GAFE test procedure ASAP, and provide a copy. | New versions of the GAFE arrive almost monthly. A test procedure should be available for consistent testing from version to version. | Huegel | Unger | GAFE test procedure development is occurring in two phases. The first phase was to develop a manual test procedure and the second is to develop an automated test procedure. The manual test proc (ACD-PROC-00067) was used as a basis for testing the first three generations of GAFEs (see the ACD Web site for the formal write-up on the GAFE2 testing, for example). The final version of the manual test proc is in review and is planned to be used for GAFEv4 testing around early March ‘03. Afterwards, the automated test proc will be updated and Labview coding will be performed. Then the automated test proc will be reviewed and tested with GAFEv4 around March/April ’03. Some parts of the automated GAFE test procedure are already incorporated into the GARC Test procedure (ACD-PROC-000062) and the FREE board test procedure, which is largely complete. The current version of the GAFE manual test procedure is on the ACD website, and other versions of all procedures will be placed there as they are completed. Fred Huegel will be informed when that happens | Closed
11 | ACD | Ensure that the correct fabrication standard is used for the FREE printed circuit card. | In the electronics presentation, page 28, it is stated that the FREE PCB will be fabricated to the IPC-6012 standard. There is some question as to this being the correct standard. | Huegel | Unger | Since this is a rigid-free board a standard Printed Circuit Board (PCB) specification does not exist. Therefore the ACD parts engineers are working on a specification for the FREE PCB. It is scheduled to be completed and released for review on March 14, 2004. | Submitted
12 | ACD | Ref: I&T test flow, pg. 13, section 10. Two modal surveys are shown, one before vibration and one after acoustics. Typically a low-level sine sweep test is run before and after each vibration test axis. This checks for shifts in fundamental frequencies, but is not a true modal survey (more response accelerometers and data reduction required). Sine sweep testing for the flight Delta environment is required (0 – 50 Hz). Random vibration is required (unless acoustics testing envelopes this environment). Sine burst testing for strength may be required (unless subsystem test and analysis can show strength qual requirements have been met). Are two modal surveys planned (required)? Can the return to the vibe cell after acoustics testing be eliminated (reduce handling risks) by carefully looking at the acceleration response data from acoustics? |  | Ryan | Amato | The modal surveys mentioned were defined (in the parenthetical comment) as low level sine sweeps. A full modal test is not planned or needed prior to integration with the LAT Grid. Low Level sine sweeps will be used for monitoring structural integrity. The post acoustic low level sine sweep will be replaced with a post acoustic test review of accelerometer data. | Closed
13 | ACD | Describe in detail the problem reporting and corrective action system that will be used for ACD. When will formal problem reporting start? Describe the transition in problem reporting and corrective action systems (if any) after ACD delivery to LAT and LAT delivery to the observatory. Who will ensure that all ACD problems are tracked and closed out at all levels of integration? | This is an essential component of space flight mission assurance, overlooked in section 9, Safety and Mission Assurance. I’d prefer to see the actual ACD plans and procedures rather than just a requirement from the MAR. | Scott | Kolecki | All problem reporting will be documented using the GSFC Nonconformance reporting system as defined in GPG 5340.2C (Control of Nonconforming Product) and corrective action required will be documented using GPG 1710.1 (Corrective and Preventive Action). Formal reporting will begin post CDR with the start of procurement, fabrication and assembly and continue through final delivery of each subsystem to I&T. At this time, the LAT procedures are still under review, but it is expected that a similar, if not the GSFC on-line based system, will be used for observatory I&T also. The Product Development Lead will be responsible for initiating the NCR and QA will follow up on the corrective action. Configuration management and the SAM will be responsible for tracking the NCRs and coordinating dispositions with the PDL and the I&T lead. The SAM is currently developing an Assurance Implementation Plan for the ACD that will define how all the GLAST Mission Assurance Requirements will be met. | Submitted
14 | ACD | Is there a logistical support plan or spares plan? Based on the calculated reliabilities, FMEA’s, and mean times to repair, provide a full description of what spares will be provided. What spares accompany delivery to LAT and to the observatory? | A good spares plan (logistic support plan) will save time and money. Need to plan ahead. I’d like to see the list of spares and how you decided which ones to provide. | Scott | Amato | The ACD team has spent a lot of time during design of ACD determining the number of spares needed, however, we have not put all of this information in one document. The following Spares Plan will document the ACD spares plan. (Data Provided) | Closed
15 | ACD | Evaluate changing the baseline bottom tile mount concept to one that does not rely on a slipping interface. Included in this evaluation, examine the consequence of one (or two) broken flexures if the concept is not changed. Add the evaluation of broken flexures to the project risk list if the concept is not changed. | The bottom tile slip/stick flexure must accommodate 8.4 mm of thermal expansion. Tests have shown that flexures fail at >6 mm displacement in the weak axis shear direction. This means that the last three flexures are at risk. There are numerous causes that could result in the non-slip of the slip interface. If the slip/stick feature does not work, flexures will fail. Since subtle features (workmanship/tolerances/friction properties/Belleville preload/contamination) of the slip interface are important in the proper function of the flexure, the low sample rate in the proposed qualification testing may not accurately simulate the flight condition and could provide a false positive result. There are 24 slip/stick fasteners that could cause a flexure failure (2 fasteners/flexure; 3 flexures/bottom tile with >6 mm displacement; 4 bottom tiles), yet the proposed qualification test only tests a sample of 8 fasteners. | Sneiderman | Segal | The bottom tile flexure support design is a support flexure in the 'fixed/free' concept common to the other ACD tiles. This design does not rely on a 'slip stick' mechanism. The flexure design is a thinner composite laminate, .025 inch compared to .035 inch, than the baselined tile flexures. This thinner flexure design allows adequate compliance and has positive strength margins under thermal loading as well as launch loads (less severe of the two load cases). Testing plans include fabricating bottom tile flexures and testing them in strong and weak axis shear. Loading to failure in the weak axis will be performed after 12 load cycles to the maximum predicted deformation ( based on survival temperature predictions). This approach will prove the design is capable to withstand repeated loading and maintain a margin after the repeated loading. Flexure failure is not deemed a risk on orbit. Even with three flexures in a row broken the tile would maintain its position as it is contrained by the Micrometeoriod Shield, the 4 flexures. No science impact would result. | Closed
16 | ACD | Identify TDA’s that will/may require the most disassembly to access or replace/repair. Suggest building “protective covers” to ensure that these TDA’s will not be easily damaged. Recommendation is: Work with the LAT team to identify impacts and benefits (tech/cost/schedule) of building and integrating a hard cover to be installed from ACD assembly through launch prep. Include evaluation of ease of application/removal of the cover and potential of collateral damage from applying and removing the cover. | Probability of handling damage from ACD assembly through launch prep is a reality and must be assessed and mitigated where possible. | Horn | Segal | The TDA's that require the most disassembly to replace are the tiles on the top of ACD. Because the TDA’s have a shingle overlap, to remove a top center row TDA, all of the TDA’s in the same column as the TDA to be replaced would need to be removed. This means that a minimum of 6 TDA’s would have to be removed to gain access to a top center row TDA. A soft protective cover will be designed and built to protect the ACD during integration, transportation and storage. A hard cover was considered, however the risk of damaging the ACD due to frequent installing and removing a large 'hard' cover that would need to be in close proximity to sensitive ACD surfaces is deemed too great. A soft cover can do an effective job protecting the ACD at a fraction of the design cost of a hardcover, therefore the softcover was selected. When the ACD is fully integrated it is fairly rugged. All fibers are shielded by 1 cm thick plastic scintillator and the ACD is covered with the thermal blanket and micrometeoroid shield (which has many layers of foam). The outer layer of the thermal blanket would be the most sensitive item at full assembly, and it is fairly rugged and can be easily repaired should the need arise. | Closed
17 | ACD | The duration of the ACD integration is shown to start on 02/03/04 and finish on 04/22/04 on the top-level schedule. The integration flow up to the pre-environmental review was shown to take 115 days in the I&T presentation. Please provide an explanation for the discrepancy in the duration of the integration activity. | Time required for integration may not be accounted for in the project master schedule. | Goans | T. Johnson | Semantics and task definitions have led to the confusion in this area. What is defined as “ACD Integration” (WBS 4.1.6.7.2 in the project schedule) on the top level schedule is integrating the TSA to the BEA. This task involves taking the fully integrated BEA and the nearly complete TSA and integrating them together. The following sub-tasks make up the overall “ACD Integration”: Install the TSA on the BEA, Mate 186 fiber cables to PMTs, Integrate 4 bottom TDA’s, Perform Functional Test, Install MMS/Thermal Blanket, and perform Performance/Efficiency Test. The Assembly/Integration Flow shown in the I&T section (Section 10 - page 7) starts with the integration of the BEA and the TSA. We defined these tasks as “ACD Subsystem Integration”. Both the integration of the BEA and TSA begin in November, 2003. When the integration of the BEA and TSA are complete, we begin “ACD Integration”. This accounts for a 67 day variance from November through February 3, 2004. An additional source of variance is that the I&T Assembly/Integration Flow represented in (Section 10 - page 7), displayed the days as “calendar” days, not “working days.” This led to the additional discrepancy regarding the allocated time for these tasks. In actuality, the total “working day” duration is 82 and not 115 as represented on the chart. (Data Provided) | Closed
18 | ACD | Present a QA plan for the fabrication work at Fermilab of the scintillator tile assemblies. This plan should include the written procedures and the personnel involved, particularly the chain of command from the ACD management to the on-site personnel. | The manufacturing plan for these assemblies was not presented at this review. Fermilab has extensive experience in producing similar devices for high energy physics detectors. But, they have little experience with space programs. Based on a visit to Fermilab prior to this review, I am concerned about the process control. The ACD management should assure that the operators are adequately trained and that adequate inspection procedures and personnel are in place to assure quality units. | Klaisner | T. Johnson | The ACD TDA’s will be fabricated in accordance with ACD-PROC-00059, Fabrication and Assembly Procedure for the ACD Tile Detector Assembly (TDA). A Work Order Authorization shall be used as a traveler for all work performed on each TDA. There are Quality Inspection steps specified in ACD-PROC-00059 to verify that the TDA’s meet or exceed all specifications and requirements prior to proceeding to the next step. As noted, Fermilab has a great deal of experience building similar detectors for ground based detectors. Fortunately, there is none to very little difference in the ACD TDA’s and detectors used for ground based systems. The only potential differences would be in the selection of wrapping materials, tapes and adhesives and these are all specified. The primary components, namely the scintillator material, wave shifting fibers, clear fibers, and optical epoxy are the same for flight as for ground. These materials shall be qualified, tested, and controlled as specified in ACD-PROC-00059. The most important steps in the fabrication of the ACD TDA’s are the machining of the scintillator, polishing the edges of the scintillator, fiber polishing (including connectors), fiber end mirroring, and epoxying the fibers into the scintillator. With the exception of epoxying the fibers into the scintillator, the group at Fermilab has a great deal of previous experience building detectors. We worked closely with Fermilab during the fabrication of the ACD development and engineering test unit TDA’s. They have successfully fabricated every type of TDA that is required for the ACD, including the bent TDA and the long bottom TDA. All TDA’s have been completed with a high level of quality and meet or exceed all requirements. | Closed
19 | ACD | Provide a risk management plan for ACD. | ACD has a risk list that they feed upwards to LAT. However, it was not clear how/when/by whom this list gets updated within the ACD subsystem. Need to clarify risk management roles/responsibilities. | Dillman | Amato | As part of LAT, ACD risks and risk related issues (mitigation, flow, procedures etc) are captured in the LAT Continuous Risk Management Plan (LAT-MD-00067). Specific ACD risks and risk parameters are specifically identified in this document in ACD tables. New risks and risk updates will be actively asked for during the main leads and team meeting and by occasional e-mails containing the current ACD risk tables. Newly identified risks identified by anyone on the team are forwarded to the principal scientist and the systems engineers who discuss the issue. Newly identified risks are then entered into the LAT continuous risk management system by going to this web site (http://www-glast.slac.stanford.edu/systemengineering/lat_risk_management.htm) and entering required information on the on-line form | Closed
1 | Tracker | Present a summary of predictions vs. requirements. In addition, a form of a “fever chart” relative to the current margins should highlight the appropriate level of concern. | The verification presentation had a separate slide for numerous requirements from the tracker performance specification. This needs to be put into a higher level summary and concerns chart to put the situation in perspective. This information could be utilized to trend the instrument performance during design and development. | McCarthy | R. Johnson | A summary chart will be presented at the LAT CDR. | Closed
2 | Tracker | Specify a temperature requirement for the heat dissipating IC components located on the tracker trays. | It was indicated that the 30°C tracker temperature requirement was applicable to the silicon in the SSDs which are not heat dissipating components. The heat dissipating ICs will likely experience temperatures warmer than the SSDs. Are these components temperature sensitive? If so, what are their temperature requirements? | Fantano/ McCarthy | R. Johnson/ Sadrozinski | The TKR operates the ICs with extremely low power consumption: the GTFE consumes 10mW on an area of 0.33 cm2 and a thickness of 0.03 cm, resulting in a temperature difference between MCM and the IC surface of less than a degree, as has been verified by measurements on prototype MCMs. In any case, the 30°C requirement does not apply to the ICs—they could easily operate tens of degrees hotter than that with no ill effect. They connect to the SSDs via wire bonds, but a simple calculation shows that most of the IC heat will flow through the MCM to the tray closeout, not through the wire bonds. Since the power density is so low that the temperature difference between the IC and tray cannot be more than a fraction of a degree, there is no need to specify an upper temperature limit for the ICs. The SSD limit will always take precedence. | Submitted
3 | Tracker | Maximum temperature predicts presented do not reflect the customary 5° analytical uncertainty used to establish these levels. Why not? For failure case, what temperature limits are used, operating or acceptance? What is system requirement? | Predictions shown more thermal design margin than you can demonstrate analytically. Design is at limits. | McCarthy | Borden/ R. Johnson | The “failure limit” listed is based on end-of-life SSD functionality and is not a part or system failure but only a potential science performance degradation. The degradation is very gradual, as it results from an increase in leakage current that produces shot noise, which adds in quadrature with the amplifier noise. Operationally, this will require raising the discriminator thresholds in the hotter regions of the Tracker, resulting in some loss of efficiency in those regions. Furthermore, the limit assumes at end-of-life an unlikely high radiation dose, so it has that margin already built into it as well. The SSD’s will not reach a part failure level until well in excess of 60°C. The limiting issue is CTE mismatch between SSDs and the tray mechanical structure. All other parts of the Tracker have even higher part failure levels. | Submitted
4 | Tracker | Provide rationale that shows that the additional EMI shielding provided by employing a conductive paint (Z-307) on the 2 mil aluminum tracker shields outweighs the contamination risks associated with having electrically conductive paint particles distributed throughout the tracker system. Consider employing the non-conductive version (Z-306) for this application to eliminate this potentially serious contamination risk. | The contamination risk associated with employing an electrically conductive paint on the 2 mil thick aluminum foil needs to be seriously considered. The added benefit of employing electrically conductive paint on the 2 mil aluminum foil is not obvious considering that the trackers are encapsulated by electrically grounded ACD MLI blankets. Although the plan is to conformal coat, epoxy, etc. all electrical interconnects, the huge number and small sizes associated with the tracker design makes one wonder whether these techniques will be 100% effective. Particles have a funny way of ending up exactly where they do not belong. | Fantano/ McCarthy |  | The conductive paint is not used for EMI. It is used only to increase radiative transfer of heat. The electrical conductivity was intended only for ESD protection. The paint is on a 2 mil aluminum foil that is bonded to a very rigid 1.5mm thick composite panel. The only way to generate paint chips or particles would be for some larger object to be loose within the instrument, banging against the Tracker. Nevertheless, Z-306 paint will be investigated for its level of conductance, and if it is within a range that will allow electrostatic charge to be dissipated then it will be used instead of the Z-307 paint. | Submitted
5 | Tracker | What drives the “hot spot” in the thermal analysis? Path length to grid, worst case contact, conductors, or a combination? Would a hot spot in center tower in center tray be hotter than presented if the tray had a poor conduction path? What sensitivity analysis in addition to the failure case was done to investigate hot spot, i.e. range of contact conduction and how they were applied? | Details and analysis parameters were not discussed fully. Do these analysis results tie into system level predictions? Was the directional nature of the thermal conductivity of the composite material accounted for in the analysis. | McCarthy |  | a)The tracker hot spot, located in the center of the towers (Bays 5,6,9,10, about 3 trays down), is a result of a combination of a contact at the interface to the grid, gradient up the tower through the walls, and limited radiation out to the ACD. b) A sensitivity study was completed adjusting all the conductors in the model –10%. Results show that the maximum tracker temperature increased 2.3°C. c) See b. | In Work
6 | Tracker | Identify the locking feature planned for all tracker fasteners. Pay particular attention to those required to secure a conduction contact for thermal hardware. Also, document use of conductive adhesive on screws used for grounding tray (MCM Ground) to the aluminum core. | A loss of thermal conduction could have negative impacts on thermal margin. Also, fasteners could be lost during vibration testing. If Urelane is used, it may interfere with grounding. | Kolecki/Seipel/ Ryan | Borden/ R. Johnson | The screws holding the TMCM boards in place are being replaced by a bonded joint. The screws will be replaced by pins for alignment of the MCM during bonding. The screws between the sidewalls and the trays will have two beads of structural epoxy on the head of each screw. The screws from the bottom tray to the flexures will have epoxy on the threads. The screws between the flexures and the grid will use Nusil silicone on the threads. The screws between the thermal strap and the grid will use Nusil silicone on the threads. The aluminum core will have wires welded to the core and bonded to the closeout with conductive adhesive; screws will not be used for this application. | Submitted
7 | Tracker | Run lateral load cases (quasistatic and random vibration) at 45° to the X & Y axes. | X & Y axes are aligned with the maximum stiffness of the tracker side walls. The 45° cases will investigate how loads are carried around the corners of the tracker towers. | Ryan |  | We will perform FE analysis and determine margins to this load case. If the margins are lower than those calculated for the two load cases parallel to the X & Y axes, proof testing to this load case will be considered. | Closed
8 | Tracker | EM testing and planning should be reviewed by the GLAST Project Office before test is conducted. | Testing will likely occur after CDR. Review by GLAST Project Office will facilitate quick closure of RFA at CDR. | Seipel/Ryan |  | The project office will review the EM test plan and bottom tray static proof test plan. This is a normal process required by the GLAST Project office. | Closed
9 | Tracker | Complete testing to define allowable material properties and recomputed margins-of –safety as necessary. If work cannot be completed by CDR show detailed closure plan and associated schedule. Revisit need (thermally) to use K13D sidewall material vs. YS90. Understand and present flow down of thermal margins driving material change. | Need to establish final design margins. | Seipel/Ryan |  | This action is scheduled. Material & Joint testing will be completed prior to CDR, and new allowables and margins will be available at CDR. Sidewall material (K13D) testing will not be complete by the CDR, according to the current CDR schedule. These tests will be underway, with YS-90A being the fallback position should the allowables come in with unacceptable margins. YS-90A allowables are already in hand. | Closed
10 | Tracker | Provide mass breakdown showing percentages of estimated, calculated, and actual masses. Based on the percentages request additional mass contingency (or lien) on project held mass reserves. | A less than 1% mass margin was shown. At pre-CDR a 10% margin is not uncommon. | Ryan/Spieler | R. Johnson | Preparation of a mass breakdown in progress. Mass margin is adequate, but it is held at the LAT level, not by the subsystem. The Tracker mass estimate has not changed more a few kilograms for several years. Actual measured mass values have been less than estimates for all measured masses. | Submitted
11 | Tracker | Verify that the latest gap (2.5 mm) is used in the dead area calculations. Recheck that all structural dimensions used in the calculations (in charts by Bill Atwood) are verified against the latest LAT baseline design (CDR level). | Chart 13 seems to use 1.5 mm as gap number in calculations. | Seipel/Ryan | R. Johnson | Atwood’s slide 13 has a typo relating to the gap (1.5mm was shown, but the gap actually is 2.5mm). However, whether he used the incorrect number in his calculation cannot be determined and is irrelevant. Numerically the error would be less than the rounding error in the next line. It would not change the result on dead area whatsoever. | Closed
12 | Tracker | Ensure that the connection is made in a manner that holds up to vibration and maintains electrical contact over long term. | The honeycomb core must be maintained at constant high-frequency potential with reference to the silicon strip detectors and front-end electronics. We have concerns about the long-term integrity of the current connection method. | Breidenbach/ Spieler | Borden/ R. Johnson | The honeycomb core will be electrically connected to the closeouts with wires welded to the honeycomb core and bonded with conductive adhesive to the closeout pieces orthogonal to the MCM sides. The closeouts will be guaranteed to connect electrically to each other by bonding a wire with conductive adhesive in a groove that wraps around the corner. The various pieces in the core are connected electrically via the face sheets, which are bonded to the sharp core edges under high pressure. The tungsten converter foils will connect to the face sheets with conductive adhesive. The MCM ground will connect electrically to the closeout via 3 pins in plated-through holes. The pins will be bonded into the closeout with conductive epoxy. | Closed
13 | Tracker | Provide both detailed FEM and reduced dynamic FEM to GLAST Project Office. | Independent verification of proper modeling will reinforce analysis case at CDR, especially since EM testing and subsequent model correlation will not be complete most likely at that time. | Seipel/Ryan |  | The CLA FEM has already been given to the mechanical systems group at SLAC. If they would like to share a copy of that model with GSFC, they can do so for systems level model verification. The detailed TKR model is not a deliverable under the contract with the vendor, nor is it a deliverable from SLAC to GSFC. The cost and schedule implications of delivering the detailed FEM model can be explored if a formal change request is submitted. | Submitted
14 | Tracker | Please update random vibration margin of safety calculations for bottom tray and sidewall margin of safety to include standard factors-of-safety (i.e. not derated as shown on page 31 Section 2-D). Also, a model uncertainty factor (MUF) of 1.25 should be factored into 3-sigma peak responses (The random vibration margins referred to are on pages 44-51). | Derating of Factors of Safety is not appropriate, given that rationale provided is not consistent with standard practice (i.e. 3-sigma peaks may well occur during a 60 second test) and that prototype vibration test results show non-linearity of response, suggesting reduced Q of 7 may be unconservative at lower input levels (also, tracker was deteriorating during test possibly causing lower Qs). | Fransen/Ryan |  | Derating the FS to 1.12 and not including a MUF of 1.25 was deemed to be acceptable for the Peer-Review presentation for the following reasons: 1)The GEVS general random vibration levels are known to be overly conservative for the TKR tower structure. 2) The random vibration analysis is by nature conservative because it assumes that a 3σ event occurs for all frequencies simultaneously. Phase differences are not accounted for here. 3) A MUF is a recommended practice if the model has not been correlated against test data. Although this exact configuration has not been tested, test data exists to suggest that the assumptions used here are reasonable. Prototype testing of an earlier structure can be used to validate modeling techniques. Given the new loads now officially provided by the project office, a FS of 1.4 (ultimate) and MUF of 1.25 (TBR) will be included in margin calculations and presented at CDR. | Submitted
15 | Tracker | Provide an MCM timing analysis based on the 20MHz signal from the T&DF sub-system which refers to a detailed block diagram (at component level) of the MCM. | The MCM electronics design was not sufficiently detailed. | Graf/Klaisner | R. Johnson/ Sadrozinski | After finishing the timing analysis for the CAL subsystem, the MCM timing analysis is being worked by the SLAC electronics team. It will be available for the CDR, together with a detailed block diagram. Note that the TEM/CAL communication hardware is essentially identical to that of the TEM/TKR (the same LVDS I/O cells are used in the ASICs of both subsystems, and the same LVDS drivers and receivers are used in the TEM). The Peer-Review electronics presentation showed that we have successfully operated the MCM with flight ASICs up to 28 MHz, to be compared with the 20 MHz nominal. | Submitted
16 | Tracker | Look at interaction of lateral displacement of tracker flexure blades with compression buckling of same flexures. | Lateral displacement of flexure blades, due to assembly tolerances and thermal temperature changes, will decrease the allowable critical flexure-buckling load. | Mignosa/Ryan |  | This was always planned and is scheduled to be completed before Instrument CDR. | Submitted
17 | Tracker | Review environments that could cause one flexure mount, at the base of the tracker module, to be out of plane from the seven other flexures at this interface. | There could be environments or enforced displacements, at this interface, that cause undesirable forces at this redundant interface. These forces should be evaluated. | Mignosa/Ryan |  | No action planned. This has been addressed in previous analyses of the flexure and interface. | Submitted
18 | Tracker | Consider use of annealed titanium instead of STA titanium for the flexure material. These flexures should also have a non-destructive inspection to screen for flaws, and component level strength / fatigue testing. | Annealed 6AL-4V titanium has much better ductility and fracture properties than STA 6AL-4V titanium even though material strength allowables are a little lower. Structural and non-destructive testing should be performed on the flexures due to the criticality of this high stress structural element. | Mignosa/Ryan | ES & R. Johnson | 6Al-4V Annealed Titanium is the desired flexure material and was considered first in all flexure analysis. However, analysis has shown that annealed titanium does not have the strength to meet the requirements imposed by the GEVS design loads. For that reason STA was used in lieu of annealed titanium. Given the new random-vibration environment provided by the project office, STA titanium is not longer required. Annealed titanium will replace STA titanium as the baseline flexure material. | Closed
19 | Tracker | Provide detail design assumptions that were incorporated into the tracker design thermal analyses. Include the values and basis for key contact resistances (i.e. contact area, interface medium, and contact pressure) that are incorporated. | The fifteen minutes that were allocated to discuss tracker thermal issues was not sufficient to understand detailed assumptions that were incorporated into the analyses. | Fantano/ McCarthy |  | Radiation: External tower-to-tower included (e=0.88). Internal not included (conservative). Sources: Q input directly to MCM closeouts, Q per tower=10.2W(hot) Key conductances: Tray to closeout: through facesheets only Closeouts to wall(except bottom tray): through mount bolts, dry joint, 0.4 W/K per tray/closeout interface (adjust based on tray grouping in nodalization) Down wall: K13D/YS90 lay-up: 297 W/cm-K (Across wall, 147 W/cm-K) Interface to grid: Wet RTV joint between bottom of tracker wall and copper strap, 4.4 W/K per interface Copper strap, 0.8mm effective thickness, 2.2 W/K per strap Dry joint between copper strap and grid. 12 mount points per interface, totaling 1.2 W/K Titanium flexures not included. | In Work
20 | Tracker | Track individual dies through MCM testing to allow analysis of possible post wafer-probe yield losses. |  | Spieler | R. Johnson/ Sadrozinski | We considered die tracking and rejected it because of cost, schedule and reliability impact at the MCM assembly vendor. dies will be tracked at the wafer level. We are helped by the excellent yield of the Agilent 0.5 um process. As an additional hedge, we segregate and hold back the dies on the perimeter of the wafers, even though they might pass the wafer-probe tests. The edge dies that pass all wafer probe tests are most likely as good as any other chips and will be retained as spares. | Submitted
21 | Tracker | Justify range of particles used for SEL tests. | 130 mm range of Ag ions at TAMU appears excessive. | Spieler | Sadrozinski | The LAT TKR proposes testing at INFN Legnaro, where the range of ions is about 32um. The GSFC Radiation Branch insists on the higher range. We have requested justification since November 2002 but so far have not received anything rigorous and quantitative. Because the train is leaving the station, we are agreeing to do a single SEL test at TAMU. We are left to believe that only the TKR ASICs have to go through this added requirement. If no difference to the Legnaro SEL test is found, then the remaining LAT ASICs do not have to go to TAMU, given that they using the same process and are laid out with the same rules. | Submitted
22 | Tracker | Review possibility of introducing redundancy of tower power supply / connections. | Failure mode with significant science impact. | Spieler | Sadrozinski | The power feeds to the TKR TEM modules are redundant. The loss of any TKR power supply will result in the loss of one of the 16 TKR towers, with the probability for the loss of two TKR towers being negligible. The science impact of the loss of one tower is being quantified in the LAT FMEA study. It has to be traded against cost and complexity of a redundant system. On the face of the performance numbers, the LAT “over-design” allows the LAT to achieve the performance goals of the SRD even with loss of one tower. A preliminary analysis indicates that loss of a single tower will still allow LAT to meet the science requirements, though the impact is significant. More details on this will be presented at CDR. | Submitted
23 | Tracker | Check for compounded design margins. | Can lead to excessively conservative specifications / requirements and as a consequence, wasted efforts that would be better applied elsewhere. | Spieler | Sadrozinski | This is a good suggestion for an early stage of the design, but given that we are close to building flight hardware, we most likely would not benefit from such a study at this point. But it should be pointed out that we have been adjusting specifications, when we found that requirements had large impacts on needed resources or efforts. One example is the thermal management, where the TKR was able to respond to the need to increase the maximum silicon temperature, because only a few layers were impacted, and because the expected end-of-mission leakage current, which drives this TKR requirement, has a 5x-engineering margin. | Submitted
24 | Tracker | Require fiber volume / void content test of face sheets for trays? | Standard composites fabrication test to assure proper properties (strength, modulus, thermal conductivity). Fiber volume range should be checked against drawing to assure performance void volume is a check on the porosity cured into the face sheet this should be 2% of less. | Rodini | ES & R. Johnson | This is a valid point and should be incorporated into the test matrix as a quality control test of the facesheet laminates. This will be discussed with the face-sheet vendor in Italy. | Submitted
25 | Tracker | Define peel strength test method. I do not think ASTM D100299 is a test method. Is the test D 1002-99? | ASTM D1002-99 is a lap shear test not a peel test. | Rodini |  |  | In Work
26 | Tracker | Define defect acceptance accept/reject criteria for flaws in face sheet and between face sheet and H/C core. | Unclear on what the requirements is. | Rodini | A. Brez |  | In Work
27 | Tracker | Investigate nondestructive method to determine if previously found defects in sandwich panel have grown during vibration. | A defect critical for thermal performance may not change the frequency of the panel. | Rodini | A. Brez |  | In Work
28 | Tracker | Strength qualification of the tower assembly must be demonstrated. This can be easily accomplished by incorporating a sine burst test (low frequency) of the Qualification Tower A. Consideration should be given to sine burst testing the flight towers at acceptance levels (because of the composite design and complexity of assembly). | Strength qualification of tower assembly must be demonstrated by test and / or analysis. | Ryan |  | This is a valid point to verify that the TKR tower structure can meet quasi-static load requirements. The test is simple to incorporate and will be included in the test plan. | Closed
29 | Tracker | Establish the necessary procedures to bond and debond instrumentation to the painted tower sidewalls. | Care must be taken to avoid damage to the paint both mechanically (peeling, contamination) and thermally (degradation of thermal properties due to use of improper solvents). | Seipel/Ryan | Borden/SB | The number of accelerometers is small and the accelerometers themselves are small such that they will be bonded to unpainted surfaces. If small amounts of paint are removed to bond the accelerometers the effect on the thermal properties is negligible. | Closed
30 | Tracker | Consider moving the flexure centerline closer to the tracker sidewall. | The bottom tray of the tracker assembly seems to have much more strain energy, in the first mode, than the other trays above it. Any offset between the flexure centerline and the tracker sidewalls could cause this strain energy. Movement of the outside flexure blade to be flush with the edge of the mounting flange, at the sidewall interface, would decrease this offset and increase the first mode of the tracker. | Mignosa/Ryan |  | No action planned. This has already been considered and optimized for the geometric requirements of the grid interface below. | Closed
31 | Tracker | Provide completed Tracker test matrix. | Test matrix was not provided. Will need to be presented at LAT CDR. | Ryan | R. Johnson | This is available and will be included in the LAT CDR presentation. | Closed
32 | Tracker | Complete conceptual design and analysis of all mechanical GSE, including tower vibration / handling fixture, tower lifting fixture and shipping container(s). Margins of safety and proof testing plans should be included, along with a schedule to show successful completion of required items by integrations need dates. | More development is required to be shown by CDR stage. | Seipel/Ryan | R. Johnson/ NM/SB |  | In Work
33 | Tracker | Specific pass / fail criteria should be established for testing at all levels of assembly. These criteria shall be clearly captured in the procedures for the execution of each test. Necessary steps to “safe” the flight hardware in the event of anomalous data should also be included in the procedures. | Necessary to protect flight hardware, properly execute testing, and allow the hardware to proceed to the next level of assembly. | Seipel/Ryan | R. Johnson/ NM/SB/ Borden | We understand the importance of this recommendation and will incorporate clear criteria in all test procedures. This was already done for those flight hardware assemblies already under test: SSD ladders (see LAT-PS-635) and ASIC wafer testing (see LAT-TD-247 and LAT-TD-248). | Closed
34 | Tracker | Consider reducing the 0.5 g high frequency sine sweep test to 0.25 g or less. | Concern is that sweeping through resonant frequency at 0.5 g will cause significant response to the tower. | Ryan |  | Agree. Test levels will be reduced to 0.25 g or less. | Closed
35 | Tracker | Include a thermal balance test in the test sequence for each flight tower if it is not already included in the baseline test plan | A thermal balance test for each flight tower would validate key tower heat transfer paths. Thermal vacuum cycle testing will not accomplish this. The added cost associated with performing a thermal balance test could be quite modest considering that plans already exist to perform thermal vacuum cycle test. This activity would greatly mitigate the very significant cost and schedule risk associated with having to de-integrate a tower or towers after instrument level thermal balance tests. | Fantano/ McCarthy |  | A Thermal balance test of each tower will be studied, and a cost and schedule change request will be submitted to the LAT project office for approval. | Closed
36 | Tracker | Flight thermistors are embedded in cables that run along sides of the tower. They are not mounted directly to hardware, trays, or boards. Why not? Do cable temperatures really reflect hardware temperatures? | By embedding the thermistors in the cables, temperatures will be dominated by copper and possibly a “thermal short” to bottom of tower, monitoring cable temperatures not tray temperatures. | McCarthy | R. Johnson/ Sadrozinski | The cables connect directly to the MCMs about every 6 cm, and they are sandwiched tightly between tray closeouts and tower walls every 6 cm. Their thermal resistance due to their copper content is about 15 times larger than the thermal resistance of the tower walls, which provide the cooling path for the TKR electronics. Hence the postulated “thermal short” does not exist. Each section of the cable will be in good thermal equilibrium with the tower structure. Mounting the thermistors on the MCMs was initially considered (the BTEM was built that way) but would be more expensive and has no advantage. The thermistors will give accurate measurements of the tower temperature at 16 different points covering all sides and all heights. | Closed
37 | Tracker | Consider temperature cycle screen test (done in non-vacuum environment) to a wider range than tower will see. Box/tower will see thermal vacuum cycles to –30 °C to +50 °C. Consider temperature cycles of trays to –30 °C to +60 °C. Attribute the additional 10 °C as follows: 5 °C because it is done in air and 5 °C because you want to screen above the box level requirement. | Typically, lower level assemblies, i.e. tray, would see a more sever temperature screen test beyond the tower level. Testing to –30 °C will be more sever, from a from a part perspective, done in air, so this level is OK. | McCarthy | Borden | The tray cycle test will be modified to the range of -30°C to +60°C. | Closed
38 | Tracker | Consider acceptance test temperature levels at 45 °C vs. 35 °C for tower assembly. Ensure that the acceptance thermal vacuum test of each tower provides a characterization to verify the “thermal character” of each tower. | Qualification testing is being done to 50 °C. Acceptance test should be qualification minus 5 °C. Acceptance testing to 45 °C provides a more robust level of screening and would provide more design margin going into the system level test. Test level of instrument test will be predicts ± 10 °C, and hence, instrument qualification could be at 49 °C. The “thermal workmanship” of each tower needs to be validated. | McCarthy | R. Johnson/ Borden | The qualification and acceptance levels for all the LAT hardware are specified in the LAT environmental requirements document. The Tracker requirements documents simply reference the LAT document, LAT-SS-00778, which is under the control of the LAT systems engineer. Therefore, any change to these requirements needs the concurrence and approval of the LAT systems engineer. For this particular requirement, the acceptance test is defined in LAT-SS-00778 as “the range over which the unit will operate within specifications at both BOL and EOL.” We expect that the tracker will not operate within specifications at EOL at a temperature of 45°C, simply because of shot noise from leakage current. (At BOL, with no radiation damage, it might be possible to operate the SSDs at that temperature within specifications.) Hence we could not satisfy the given definition of acceptance test if the level were raised to 45°C. A practical solution might be an acceptance test to 35°C and a “thermal worksmanship” test to 45°C with the SSD bias turned off. The latter test could operate the electronics at the elevated temperature but not take actual data from the detectors. The Tracker team has no problem with raising the temperature to 45°C if the SSD bias is turned off. | Submitted
39 | Tracker | Provide plans to address the grid to flexure to bottom tray precision assembly. | “Tight tolerance” pins and shoulder bolts are used to secure the flexures to the grid / bottom tray interfaces. It will be necessary to document and verify this critical assembly step. | Ryan |  | The bottom tray will have the midspan flexures bonded and bolted to the bottom tray using an assembly fixture fabricated from the drill fixture used to drill the grid. The corner flexures will have the bolt hole for the mounting bolt to the grid drilled and reamed to size using the same drill fixture. This process and the fixtures involved have been jointly designed with the Mechanical Subsystem. | Closed
1 | I&T | What are I&T interfaces with other organizations during project? | What interfaces/reviews are in place to interface with subsystem design/fab groups to assure I&T needs are met? How are observatory I&T needs addressed? Is there any interchange between personnel of I&T and subsystem groups? | Shippey | Bloom | 1) All subsystem managers are required to attend a weekly CAM meeting called by the LAT Project Manager, and an engineering meeting Chaired by the LAT Chief Engineer. The I&T Manager’s signature is required on all Subsystem-LAT ICDs. 2) The I&T Manager and Engineer participate in the Observatory I&T working group Chaired by the Spectrum Astro I&T manager; the SIIS also has a working group where the I&T Engineer is the LAT point of contact. 3) The Online Dept. Head holds weekly meetings with representatives of the Subsystems to discuss EGSE issues. The IFCT Dept. Head has just begun weekly meetings with representatives of the Subsystems to didcuss EM integration issues. This meeting well before flight hardware arrives. | Closed
2 | I&T | Will MGSE be compatible with S/C for integration of LAT with S/C? | I had heard in previous conversations that there might be interferences with the S/C that might affect the LAT MGSE. | Shippey | Bloom | I&T is planning to have MGSE available at Spectrum Astro for observatory integration. This MGSE will allow us to place the LAT on the S/C without interferences. The S/C-LAT IDC should ensure that such interferences will not occur. | Closed
3 | I&T | Confirm that vertical installation of X-LAT plate doesn’t present any problems such as stresses, deformation, etc. | Meet concerns expressed by GSFC/Swales | Shippey | Bloom | With new design of LAT Integration MGSE, there is no I&T Requirement to install the X-LAT plate vertically. However, the I&T MGSE LAT Rotation fixture would allow vertical installation if that was required. | Closed
4 | I&T | General concern about coordination of subsystem design with I&T requests, e.g.: Need for breakouts, Keyed connections, Length/interchangeability with cables, Wire gage/physical strength, Protection of equipment during I&T | Concerned that subsystem design reflects special needs of I&T. | Shippey | Bloom | I&T is coordinating with Electronics on these issues. There will be break out boxes and extender cables. According to electronics, given the design of the connectors they cannot be keyed. We will use labels and procedures to insure correct mating. In addition, connectors with differing functionality have different form factors. The gage/physical strength of the cable are considered adequate for the LAT application. All multistrand cables will be sheathed. I&T will protect equipment during installation. | Closed
5 | I&T | Carefully control and test electronic units for EMI/EMC compatibility. Radiated emissions and radiated susceptibility corrective actions may require additional harness dressing. | There is little room available for modifications to harnesses. EMI/EMC deficiencies may require additional harness and connector dressings after integration. | Bolek | Bloom | EMI/EMC testing is done during the EM2 design phase of the electronics boxes. This is done by the electronics subsystem. Cables will be removed for rework if needed. | Closed
6 | I&T | Make provisions for troubleshooting electronics. Provisions should include BOBs and cable extenders so that units can still be electrically interconnected during troubleshooting procedures. Key connectors so that connectors will be properly mated Wire harnesses and connector/harness interfaces must be tightly controlled. This process should be clearly defined for the harness manufacturing technical staff. | The installation of the electronics is sequential in nature and somewhat confined by design. There is risk to schedule if provisions are not made to have cable extenders and BOBs available. There is risk to hardware if connectors are incorrectly mated. Keying the connectors reduces this risk. The wire harnesses are located in confined spaces. This limits the amount of room available. Things like harness bend radii, connector shielding, etc. must be considered and controlled. | Bolek | Bloom | I&T is coordinating with Electronics on these issues. There will be break out boxes and extender cables. According to electronics, given the design of the connectors they cannot be keyed. We will use labels and procedures to insure correct mating. In addition, connectors with differing functionality have different form factors. The “harness” will be laid, cable by cable, in place. This will be done via a preconstructed plan developed by I&T and Electronics. | Closed
7 | I&T | Are connectors keyed to specific locations? | Given the number of connectors on the LAT instrument (and mating sequences) the possibility of incorrect electrical connection during I&T is high. Keyed connectors reduce the risk inherent with numerous connectors similar in size/design &ID’s with only a serial number. | Kolecki/Graf | Bloom | According to electronics, given the design of the connectors they cannot be keyed. We will use labels and procedures to insure correct mating. In addition, connectors with differing functionality have different form factors. | Closed
8 | I&T | Investigate/consider how troubleshooting will be done with BOB, cable extenders, etc. | Tight tolerances make the use of troubleshooting equipment difficult. | Graf | Bloom | We plan to use BOB and extenders, if TEM connectors will be accessed some disassembly will be required. According to electronics, the connectors used in the LAT during I&T can mate/demate 10 times. | Submitted
9 | I&T | When will the Flight Software Test Bed be placed under Configuration Control? | To maximize the utility of this tool, thru the GLAST life cycle, the test bed must be functionally identical to the flight unit. | Menning | Bloom | Two months before the Integration Readiness Review (IRR), there will be a subset of the test bed under configuration control in order to do EGSE validation. The full software test bed will be under configuration control before the first LAT comprehensive test. | Closed
10 | I&T | What timeframe is the Beam used for testing available? I&T presentation stated that beam was off during the summer. What test mitigation is planned? | With a tight schedule, any slips in hardware fab and component delivery to SLAC can affect I&T schedule. If beam testing needs to be done in June to August timeframe (instead of April/May) what is impact on mitigation? | Kolecki | Bloom | The beam supplied for the LAT beam test by SLAC is an off project cost. The project has been told by SLAC’s Associate Director of Research that the beam will be available for the LAT beam test as required. If we need to use the beam in the summer, SLAC will incur additional off-project expenses as compared to the currently scheduled beam test time. NB: It is not formally an I&T responsibility to guarantee that the beam is available as promised by SLAC. This is a negotiation between the LAT project office and SLAC. | Submitted
11 | I&T | Need an EGSE/MGSE verification plan (including both SLAC and NRL) prior to CDR. |  | Graf | Bloom | Both EGSE and MGSE verification plans are in our documents: LAT-MD-01462- MGSE, LAT-MD-01563- EGSE. These docs are currently in draft and are planned to be released by CDR. | Submitted
12 | I&T | Why are you using random vibe for developing “signature” and subsequent verification of results of sine vibe? | Normal practice at GSFC is to use low level sine sweep. Correlation of before/after is easier. | Shippey | Bloom | For the vibrations tests of the LAT I&T will follow the requirements specified in LAT-MD-01196, the LAT Dynamics Test Plan. This document is held by SE. | Closed
13 | I&T | By the LAT CDR, SLAC should be prepared to address their needs/expectations/plans during observatory I&T. This should include “expected” compatibility of EGSE, MGSE, LAT testing plans, facility requirements (cont. cont.environment). | I think this is extremely important for a successful CDR | Shippey/Graf | Bloom | Many of these issues were addressed in a special section in our peer review. With our current knowledge of the Observatory integration plan we cannot proceed much further. I&T has been working with the S/C vendor in the observatory I&T group to coordinate issues. The S/C-LAT ICD is addressing many of these issues, and is held by SE and the Project Manager. | Closed
14 | I&T | Perform a muon survey at the same time as the optical survey before ACD integration. | This allows the two surveys to be directly compared. The current plan shows that the LAT will be tipped for X-LAT plate integration before the first muon survey. This tipping will probably cause internal alignment shift making survey comparisons difficult. | Lovelette/ Marcellini | Bloom | Such a test is in our current survey plan as test 1c in LAT-MD-00895 “LAT Instrument Survey Plan”. | Closed
15 | I&T | Suggest that all non flight hardware/software be the responsibility of I&T and that all technicians and support personnel for I&T activities be hired by I&T. Responsibility includes holding budget and personnel as well as cost and schedule performance. | Integration and test needs to have increased authority over their schedule performance and hardware/software required for I&T. Org chart shows that mechanical techs but not electronic techs are within I&T organization. Miscellaneous non flight hardware seems to be the responsibility of other organizations. | Menning | Bloom | The LAT IPO has decided that the current organization will work. To mitigate against misunderstandings between Electronics and I&T concerning allocation of manpower, I&T will produce a detailed Integration and Test Staffing plan well before the IRR. This plan will include the day-to-day labor hours expected from the integrators under the budgetary control of the Electronics Subsystem. | Closed
16 | I&T | Provide accurate assessment of scheduled late deliveries to I&T by identifying a high density of discrete milestones and earned value for each milestone for each task. If this effort still shows little or no positive float, develop and implement recovery plans for each task which appears late. Provide progress report until schedule is recovered. | Cal Module A&B shows 0 days float on delivery to I&T (about 5). Chart 6-15 show many projected late deliveries. | Menning | Bloom | I&T expects deliveries to the level 3 milestones held by the Project Manager. | Submitted
17 | I&T | Evaluate the schedule impact caused by delaying grid turnover to allow epoxy on calplate/grid fasteners to set up /partially cure. (See Mark Molini for curing details). | A two part epoxy will likely be implemented on several fasteners which attach each cal plate to the grid. | Menning | Bloom | I&T does not anticipate the additional few hours of cure time specified by Mechanical Systems to impact the integration schedule. | Closed
18 | I&T | There should be a scheme to calibrate the absolute efficiency of L1T of the entire LAT. One easy way of doing this is to have a muon telescope exterior to LAT and compare its counting rate with that of LAT. Please show the plan. | There will be no way to calibrate the absolute trigger efficiency once in orbit. | Kamae | Bloom | There is a way to calibrate the L1T trigger in space using the CAL Low trigger. This is part of the trigger strategy for the LAT. Reference: Project Scientist. We will also be able to use this technique for the ground tests. | Closed
19 | I&T | Risk of not doing the Beam Test needs to be estimated in SAS and FSW area. | Once in orbit, it will be very difficult to calibrate FSW (filtering, etc.) and SAS. | Kamae | Bloom | With the current schedule for the beam test the FSW delivered for the test will not have filtering. This is due to the ELX hardware and FSW schedule that do not support the full flight system for the beam test (e.g., no EPUs). However, the filtering efficiency can be checked offline as part of the verifying the Monte Carlo. A later beam test would not impact complete checks. NB: The FSW would be ready by then. We intend to do a beam test well before launch. | Closed
20 | I&T | Provide sufficient detail with respect to on-orbit calibration to ensure feasibility of on-orbit calibration methods are understood sufficiently to verify that LAT on orbit science performance will be achieved. | CDR needs to show LAT design achieves science performance requirements, since this depends upon on-orbit calibration. | Horn/Mrcellini | Bloom | The work has been done (TBR), but we only presented a short overview in our presentation. We will show more in the CDR. See the LAT SVAC Plan, LAT-MD-00446, Section 7. | Closed
21 | I&T | Need to better describe “loads” during tilt/turnover operations. Is there a point of instability at top of turnover? What are lateral constraints on fixture to prevent movement/slipping? | When crane/lift point are in line, configuration is very unstable. | Shippey | Bloom | The tilt over stand concept has been replaced with a roll over stand which has continuous control of the LAT during movement. No crane operations are required for rotation. This design has been under development since the Engineering meeting on 3/11/03 during which we discussed LAT assembly. | Closed
1 | CAL | Preload of end caps. State minimum preload for end caps (max load of 30 N was only presented). How will preload be verified for all CsI logs? | It is not clear how the “less than 30N” requirement will be verified. | Ryan | N. Johnson | There is limited data on the compressive strength of CsI(Tl). In response to the RFA we will measure the compressive strength of a few samples (20 x 27 x 30 mm) of our CsI(Tl) from Amcrys. The test will load the crystal sample against the endcap as in the PEM design. These tests will be executed in the next week and results will be reported. This report may not be available until after CDR. We should note that the EM module just completed qualification level vibration test without mechanical problems. I believe the only issue is perhaps a long-term compressive set that changes the preload. This would not be enough to impact the light yield performance of the crystals. We presume that the explanation of the preload requirement is sufficient and the only issue is the ability of the CsI to handle the loads. As to the tolerance issue of the composite structure (length 339mm +/- 0.1mm), this tolerance has been demonstrated in the manufacture of the EM structure and subsequently in the recent autoclaved structure that is the pre-SM test structure. | In-work
2 | CAL | Cal structure - Request coupons “with titanium inserts” also be fabricated during flight structure curing. Pull inserts to failure to verify strength/process. | All loads go into composite structure through titanium inserts. Plan was to only fabricate coupons without inserts. | Ryan | N. Johnson | IN2P3 has agreed to incorporate titanium inserts into their co-cured sample coupons. Verification of the strength/process will also include pull testing of the inserts. | Closed
3 | CAL | Fastener availability - Check availability of metric fasteners from GSFC supplies ASAP. | Flight qualified metric fasteners are a very long lead item. | Ryan | N. Johnson |  | In-work
4 | CAL | Fastener locking - Locking feature on fasteners was stated to be epoxy on heads of screws, which is not a reliable way of locking fasteners. Consider uralane on threads or locking screws. | Epoxy on head of screws is adequate for torque striping but not for locking the fastener. | Ryan | N. Johnson | NRL has agreed to implement uralane as a thread lock on all fasteners of the EM module. Torque striping of the fastener heads will still be implemented. | Closed
5 | CAL | CsI logs - Determine stress margins of safety on CsI logs. Need to determine stress allowables and applied loads. | Margins of safety for the CsI were not presented. | Ryan | N. Johnson | There is limited data on the compressive strength of CsI(Tl). In response to the RFA we will measure the compressive strength of a few samples (20 x 27 x 30 mm) of our CsI(Tl) from Amcrys. The test will load the crystal sample against the endcap as in the PEM design. These tests will be executed in the next week and results will be reported. This report may not be available until after CDR. We should note that the EM module just completed qualification level vibration test without mechanical problems. I believe the only issue is perhaps a long-term compressive set that changes the preload. This would not be enough to impact the light yield performance of the crystals. | In-work
6 | CAL | Margins of safety - For consistency, use GEVS margins of safety equations. | Margins of safety calculations should be consistent across the LAT program. | Ryan | N. Johnson | Margins of safety were recalculated using the GEVS margins of safety equations. These values are summarized in Section 4 of the attached technical note, LLR-GLAST-TN-082 The attached view graphs, which were presented at the CAL Peer Review, have been updated to address the request of this RFA. | In-work
7 | CAL | Strength Qual - Lay out plan for strength qualification of “flight” composite structure. | Process changes are being made from EM to “flight” composite structure. Composite structures are very process dependent. It is my understanding that flight structures will not be tested at 1.25 times maximum flight predicted loads. | Ryan | N. Johnson | Please see attached verification plan for the flight structure, GLAST-LLR-SP-078. The strength qualification of the composite structure is addressed in this document. Strength qualification of the flight composite structure will involve sine sweep, sine burst, and random vibration of the structure built up with its aluminum piece parts are mass simulators representing the CDEs. | Closed
8 | CAL | Electronic Board Structural Analysis - Document AFEE board structural analysis. Fundamental frequency of board, maximum stresses, maximum deflections should be documented. Assess mounted parts to see if they can tolerate the planned number of cycles at these deflections. | AFEE board structural analysis was not presented. | Ryan | N. Johnson |  | In-work
9 | CAL | Parts thermal analysis - Update Board level analyses using vacuum rated parts parameter, i.e., theta-jc, theta-cl, etc. | Board level analysis used theta-ja to tie component to board. The use of theta-ja, an ambient part parameter, to represent the part in vacuum may not be conservative. For vacuum/space application analysis, each part must be considered using theta-jc and how is part tied to board, i.e., through lead and/or is it bonded? | McCarthy | N. Johnson | Analysis was rerun using the theta-jb (junction to board), which accounted for theta-jc (junction to case) and theta-cb (case to board). The attached view graph corrects the board level thermal analysis summary that was presented at the Peer Review (page 7-38) to address the request of this RFA. The AFEE Thermal Study report will be updated to add this information. | Closed
10 | CAL | Sidewall thermal analysis - Does the K-composite consider its directional nature in the composite? Was this accounted for in the analysis? | This property is different in film direction vs through-epoxy and was not noted in the analysis. | McCarthy | N. Johnson | Thermal conductivities of the CAL composite material were calculated in the in-plane and transverse directions. These calculations are summarized in the attached technical note, LLR-GLAST-TN-080-A. The thermal analysis will be re-run accounting for the directional nature of the conductivities. The updated analysis is covered in RFA CAL-014. | Closed
11 | CAL | CsI temperature - Add CsI temperature to Summary Chart | Summary does not highlight critical part temperature, i.e. crystal, photodiode etc. All temperatures reported are structural. | McCarthy | N. Johnson |  | Closed
12 | CAL | Emissivity parameter - Consider clarifying emissivity parameter with respect to coating it applies to. |  | McCarthy | N. Johnson |  | In-work
13 | CAL | Parts Qual temps - Consider raising part (i.e. DPD, PDA & CDE) Qual temperatures to +55C. | Part Qual Hot temp level for cycling is +50C. This is the box level environment. Part temperatures will run some delta-T above box temperature. Passive components will be driven by board temperature, which will run hotter than baseplate/box. | McCarthy | N. Johnson |  | Closed
14 | CAL | Thermal qualification - Consider presenting thermal analysis using Qual Level boundary conditions. This applies to both box and board level analyses. | Thermal design goals is to ensure critical part temperatures stay below derated limits, that ensure the life of the parts in the qualification environment. | McCarthy | N. Johnson |  | In-work
15 | CAL | Thermal analysis – Board -Add list of derated part temperatures that apply to all parts as part of the Board level temperature summary. | The board level thermal analysis needs to show that the thermal design of the board/box maintains part temperature below derated limits in the Qual environment. | McCarthy | N. Johnson | The attached view graph corrects the board level thermal analysis summary that was presented at the Peer Review to address the request of this RFA. The AFEE Thermal Study report will be updated to add this information. It can be found via URL: http://hese.nrl.navy.mil/glast/CM/rpt/AFEEThermalStudy-LAT-TD-01114-02.pdf | Submitted
16 | CAL | Systems verification and test - Revisit EMI acceptance testing with LAT and receive direction. | Ongoing discussions between the GPO and LAT have focused on the necessity of conducting limited EMI acceptance testing on ALL follow-up units. First unit must receive complete qualification testing. | Graf | N. Johnson | With the concurrence of the GPO and the LAT IPO, this RFA has been closed since the issue raised is one that is being addressed by the LAT system engineering office and the GPO for all LAT testing. CAL will support any required modifications to the environmental test plan as long as appropriate adjustments are made in the cost and schedule for the CAL program. The current CAL program performs qual level EMI/EMC testing on the EM and FMA(Qual) modules only. | Closed
17 | CAL | Use of 28 AWG wires - Look into the use of 28 AWG wire for space flight; is there any heritage? Consider using a different gauge wire, preferably 24 AWG. Due to the large number of wires to be used in this subsystem, please give this careful consideration. | GSFC advises against the use of 28 AWG wire for spaceflight. Due to the very small diameter of this wire, experience has shown it to be highly susceptible to damage. | Graf | N. Johnson | 28 AWG wire as per M22759/11-28 (7x36) Polytetrafluorethylene (PTFE) insulated copper, silver coated, 600 volt, 200°C was selected from the NASA Standard Part List (NSPL). This wire carries a current of no more than 10 nanoamps and a maximum voltage drop of 100V. That shows that this wire has an adequate safety margin and we will not melt any wire. These wires are used as twisted pairs for unique functional signals, EMI reduction, noise reduction, and flexibility requirement for integration of CDE assembly to AFEE board, which does not permit the use of higher gauge wires. Precautions are taken during assembly activities and acceptability inspections are carried out to ensure the wire integrity by providing proper stress relief where required at all times. Magnification aids and handling fixtures shall be used for visual inspection of in-process and completed assemblies. Wires will be used and inspected as defined in NASA-STD-8739.3 for Soldered Electrical Connections and NASA-STD-8739.4 for Crimping, Interconnecting Cables, Harnesses, and Wiring. Hence we do not see any issue in using this 28 AWG wire for the application as defined above. | Submitted
18 | CAL | Grounding of composite structure - RE pg 7-7, complete diagram including more detail. Show how grounding of the composite structure will be accomplished. | The grounding diagram does not show the composite structure being grounded, so there is the possibility for an ESD event. All surfaces must be kept at the same potential. | Graf | N. Johnson | The attached view graph is a correction to the presentation that addresses the grounding of the composite structure relative to the rest of the CAL module. The carbon composite structure is well grounded to the aluminum structure that surrounds it via titanium inserts embedded in the composite. These inserts provide solid mechanical and electrical attach points for the baseplate, closeout plates, PWBs and side panels. The CAL grounding plan is LAT-MD-00272. A link to it is http://hese.nrl.navy.mil/glast/CM/plan/CalGroundingPlan-LAT-MD-00272-02.pdf | Submitted
19 | CAL | Radiation damage to PIN diodes - Expose PIN diodes to protons or heavy ions during one of the upcoming beam tests. Measure the leakage current after exposure to see if it has increased. | BABAR has observed a factor of two increase in the leakage current of their PIN diodes after operation in their beam. They attribute the increase to a relatively small dose of neutrons. It is not clear to me that they really understand what is going on, but it is worth checking. GLAST can withstand approximately a factor of four increase in leakage current before they see an impact. | Ray | N. Johnson | Acting on the recommendation of this RFA, on April 7 – 8, we exposed two diodes to proton irradiation along with CsI crystals in Sweden. The diodes will be returned to France for comparative measurements. Results of this irradiation will be provided in a summary report. Additional radiation testing will be performed as part of the flight diode evaluation and qualification program. Proton and neutron testing is being considered for inclusion in the evaluation of the flight prototype lot which will be received in April. | Closed
20 | CAL | Radiation testing - To what extent is radiation damage reproducible? Are the results just fluctuations due to experimental procedures? Tables had no error bars. | Verify test results are true representations of capability vs test procedure variance. | Schindler | N. Johnson |  | Closed
21 | CAL | Diode Performance - Investigate impact of leakage current rise on irradiation over the expected life of GLAST. Measure effect and understand consequences to noise budget and calorimeter performance. | BaBar has observed factor or 4 to 12 increase in leakage currents, depending on location (hence dose), during the last three years. | Wisniewski | N. Johnson | The calorimeter noise budget and energy resolution are not dominated by photodiode leakage current. For our shaping time of ~2.5 us, the typical diode dark current of ~ 2.5 nA contributes ~250 electrons (rms) of noise. This scales with the square root of the dark current, hence yielding ~500 e (rms) at 10 nA dark current. This is to be added in quadrature to the preamp noise (~800 e). It would take an increase in dark current of greater than a factor of 10 to be comparable to the preamp noise and a factor of ~50 to cause failure to meet the overall requirement of < 2000 e (rms) noise in the low energy channels. Our measurements to date with 60Co hot cell irradiation indicates that after 23 kRad the dark current from two test units was less than 10 nA (~ 4 nA at 10 kRad). While the two units started with different dark currents (~x2), they tracked approximately the same absolute current with radiation dose. Additional radiation testing will be performed on the flight PIN diode lot as part of the qualification testing. On April 7 – 8, we exposed two diodes to proton irradiation along with CsI crystals in Sweden. These results are being analyzed at this time – a report shall follow. We are investigating the possibility of neutron irradiation tests as suggested in RFA CAL019.The reference to the 60Co irradiation test report is http://hese.nrl.navy.mil/glast/CM/rpt/EMDPDIrradiation-LAT-TD-00787-01.pdf | Closed
22 | CAL | PIN-diode testing - LAT-DS-00209-10 specifies 10Krad ionizing radiation for lot testing/qualification of pin-diodes. The spec does not say whether under bias voltage or not, please clarify. | Increase in leakage current with neutron dose has been observed. But only folklore whether it must be done under bias or not. | Schindler | N. Johnson | The irradiation of the PIN photodiodes during the GLAST mission will occur while biased at ~ 70V. The LAT total ionizing dose requirement for EEE parts is 4.5kRad(Si) under worst case bias (GLAST Mission System Specification, 433-SPEC-0001). According to Jim Howard, NASA/GSFC Radiation Effects Branch, for simple structures such as PIN photodiode total dose testing without bias is acceptable. All our radiation testing to date has been with unbiased diodes. The accelerated dose rate (10 – 1000 Rad/hour) of our testing would create large currents in the diodes. The following note summarizes the on-orbit evaluation of the PIN photodiodes that were used on PICsIT experiment on ESA’s INTEGRAL mission. It uses similar, but smaller (~ 1 cm2) Hamamatsu PIN photodiodes. (additional data provided) | Submitted
23 | CAL | Crystal – Photodiode I/Fs 1) Verify that Tl leaching/migration is not a problem with “primer” layer on crystal/photo-diode interface; 2) Bond tests for the crystal--photo-diode interface were carried through ~100 thermal cycles. This test was carried out for ~10 samples. Better identify/extrapolate failure point to verify capability over life of detector by using more than 10 test samples; 3) Investigate thermal limit for crystal – photo diode bond: test to failure. | Bond interface is a key risk area with a history of difficulty. Should take further steps to fully stress bond and understand design limits. There is a lack of clear target for reliability and a program to achieve a knowledge of what reliability of the three joints (diode-encapsulant, encapsulant to silcone, silicone to primed xtal). Several different test ranges for temp, # of cycles and never saw a failure. Also concerned that during manufacture, bonding process errors will not be caught fast enough, leading to multiple units to be repaired and schedule loss. | Wisniewski/ Schindler | N. Johnson |  | Submitted
24 | CAL | Crystal purity - To what extent is material purity (CsI salt) being monitored for impurities? Some impurities will not lead to radiation damage propensity, but may change relative fractions of each component time-constant, and also mechanical properties of crystals. |  | Schindler | N. Johnson |  | In-work
25 | CAL | CAL calibration - How can you calibrate CAL in MeV-GeV using heavy ion if fast shaper outputs are not recorded? Can you separate alpha, carbon, nitrogen, oxygen by other info? |  | Kamae | N. Johnson | The calibration on heavy ions is independent of the fast-shaper output. The fast shaper only provides an auxiliary trigger for the CAL (and thereby LAT) and is not required in any way for this calibration process. The calibration relies on well-defined tracks derived from good TKR triggers. From these well-defined tracks, we will select only penetrating galactic cosmic rays, and trivially make corrections for the pathlengths of heavy ions through the CDEs. With these corrections for pathlength -- and the approximate calibrations of CDEs from sea-level muons and charge-injection processes -- the energy deposited per unit pathlength (dE/dx) by each heavy ion can be measured. Because the expected energy deposition and elemental composition of the galactic cosmic rays is well understood, the species of each heavy ion can be identified. No independent measure of charge is required. This was demonstrated with the BTEM at GSI in the summer of 2000. Only the most common GCR species (He, C, O, Ne, Mg, Si, Fe) are required for the calibration, since they give more than adequate coverage of the overlapping gain ranges. This further simplifies the analysis, by allowing us to neglect, e.g., the potentially confusing, low-abundance species of the sub-Fe region. | Closed
26 | CAL | CDE Production - Very complex scheme handing off to vendors, receiving back, etc. This is designed to lose float/schedule. Consider options to do production in-house. Contract part of production with experienced offshore vendor. | This is a critical path and has already slipped due to complexity of contracting, and has potential slip of another 2 months. | Wisniewski | N. Johnson | The production of the CAL Crystal Detector Elements is the responsibility of CEA/Saclay. This responsibility has been detailed and documented in the Memorandum of Agreement among Stanford, NRL and CEA. These details are also in the Letter of Agreement between NASA and CNES. CEA has developed a CDE manufacturing plan that is compatible with their available in-house resources – both labor pool skills and manufacturing space. Due to the large number of CDE to be manufactured per week and the limited available pool of technicians, CEA determined that it would be impossible to sustain the required rate with in-house resources. CEA’s staff will be responsible for acceptance testing of the CDE component materials – PIN diodes, crystals, wrap material – which are delivered to contractors for the assembly. CEA is then responsible for the final performance and acceptance testing of the CDE delivered by the outside contractor. The CEA search for supporting contractors is well underway and has been limited to French industry. Supporting an “offshore” vendor would involve more transportation issues with associated customs problems, or the CDE would have to be accepted offshore, thereby relieving CEA of its responsibility. After much discussion among the CAL team and with the LAT IPO, there is general agreement that the flight qualification of two sources of CDEs represented an equally great risk to the cost and schedule of LAT. The plan is to establish this source in France and to make sure it has adequate resources to meet the LAT schedule. Such a source has been identified in the French procurement process and options to the statement of work have been included in the procurement process which increase the manufacturing rate to hold the later CAL modules delivery schedule. Unfortunately, due to the delay in the initiation of the procurement process in France, the first four CAL modules can not meet the delivery dates and we have been unable to find an alternate solution to this problem. LAT is planning a revised integration and test program which accommodates the late delivery of the 1st four CAL modules. It appears that the revised program must delay the beam test of LAT components until the end of LAT assembly. At this late date – CDR – it is essentially impossible to recover the lost schedule and deliver the first CDEs on the baseline schedule. Even if the work was transferred to some other organization, it would take several months for that new organization to organize and manufacture the required tooling and qualify their manufacturing process. That task would even be a challenge for an organization with experience in CDE manufacturing. We are currently struggling with a new problem in the CDE manufacturing. CNES has withdrawn its support of GLAST in France and CEA has been unable to initiate procurements necessary for the preparation and qualification of CDE components. The procurement selection process for PDA and CDE contractors is continuing on the schedule presented at the Peer Review but diode evaluation and qualification contracts are on hold along with shipping container manufacturing. The LAT IPO is working with the French and CAL team in attempting to restore the CNES funding and, at the same time, developing alternate plans for funding and execution of this work. While the CAL team is, to the extent possible, continuing along the scheduled work plan, these issues will likely add additional delay in the delivery of CDEs and consequently represent a major risk to LAT. | Closed
27 | CAL | Transport path - Investigate methods to streamline transport path; minimize multiple connections/acceptance test points. Consider test receipt of crystals by Swedes in France. | Multiple receiving and test operations may add unnecessary risk to hardware and schedule delay. | Wisniewski | N. Johnson | The procurement and acceptance of the CsI crystals is the responsibility of the Swedish Consortium. With the fabrication and acceptance testing of engineering model crystals (~250 crystals) they have developed transportation and customs procedures to expedite deliveries in Sweden. The testing program in Sweden has been operating for over one year. The first flight crystals will be shipped from Amcrys-H in April. The acceptance test manpower plan has been developed for the ~ 9 months of processing in Kalmar, Sweden. At this point, it would be a significant disruption to identify and train personnel that could be detailed in France for nine months to do the work there. We have attempted to mitigate this multipoint handling and testing by using identical test hardware in all sites and common test procedures. Six optical test benches have been fabricated – all identical. Two are used at Amcrys-H, two in Kalmar for acceptance testing, and one each at CEA and NRL. The crystals are accepted in Kalmar using identical equipment to the preship measurements performed at Amcrys-H. Amcrys data is provided on CD Rom with the shipment. When the crystals are delivered to France, CEA needs to establish a light yield baseline for each crystal that will be used to accept the finished CDE. CEA believes that this baseline can be best established with the PIN diode of the ultimate CDE and are planning to adapt PIN diode readout to the PMT-based optical test bench. We are also testing with aperture masks for the PMT. The issue is establishing a correlation, if possible, of the PMT measurements to the CDE light yields with a PIN diode. If a reliable correlation can be established, CEA will use the PMTs since that test is faster and has better resolution. We are currently testing 48 flight prototype crystals to investigate the best procedure. The standard GLAST optical test bench uses photomultiplier tubes for improved measurement accuracy (yield and tapering) and faster test results using radioactive sources.The associated schedule risk of multipoint handling is somewhat mitigated by scheduling the work well off the critical path of CDE manufacturing (approx 4 months positive float.) At this time we feel that there would be considerable risk in reorganizing the shipping and acceptance testing work in order to transfer it from Kalmar to Paris. | Closed
28 | CAL | Crystal Production delivery - Schedule is tight: pre-plan for about a month of cumulative delays in delivery of crystals. If schedule analysis indicates that the crystals are on the critical path, consider tuning “bad” crystal light taper on receipt rather than returning to vendor (This may be several percent of the crystals!). | Schedule risk is high. | Wisniewski | N. Johnson | The CsI crystal production is planned on a schedule that has significant float against need dates for CDE manufacturing. The first 48 flight crystals will be completed by April 15th and will be inspected by Swedish collaborators at the factory in the Ukraine. The first 120 crystals are needed in France in late July. The flight production rate of 200 crystals per month will deliver essentially all CsI crystals to Sweden before the end of the calendar year. This plan indicates 80 days of float against need dates in France. The crystals will be stored in France until needed. With the delivery of ~250 crystals in about 6 lots (including redelivery of modified crystals), the shipping and customs issues for delivery of crystals from the Ukraine to Sweden are well established. The typical delivery takes about 3 days. The CAL team has demonstrated the ability to correct light tapers. This correction was required due to the excessive handling many of the EM crystals received during rework of the length and chamfers. These problems with the light taper are not expected with the flight crystals. Amcrys-H, Sweden and France all have the same optical test bench to measure light yields and tapers. The French are considering an adaptation of their bench for a PIN diode readout to create light yield measurements that may be more representative of the expected CDE performance. We are also testing aperture masks on the normal PMT readout from the bench as a modification to all benches that might correlate better with the final CDE measurement. We have demonstrated that the same light taper can be verified with either PMT or diode readout. For absolute light yield, a conversion factor is required. EM correlations of PMT measurements to CDE light yields are not as tight as we would like. Contributors to this include quality of the bonds, differing wrapping materials and differing crystal end treatments. Amcrys and Sweden must use identical benches and configurations to verify contracted performance of the crystal. CEA is more concerned with predicting CDE performance based on crystal light yield as a control of their contractor’s bonding process. To that end, they want the best measurement of light yield with little or no corrective factors for differing test conditions. In EM CDEs we have also been able to use large/small PIN diode light ratios and end-to-end ratios (for center muons) to detect bad bonds. The fact of the matter is that we have 40% more light than the requirement. So the objectives are mainly to obtain a more uniform performance from the CDEs and to detect poor quality bonds. Our taper requirements are minimal – essentially monotonic. The actual product is much better. The taper is calibrated with cosmic muons on the ground and recalibrated with cosmics (protons and heavy ions) in orbit. These calibrations provide absolute gain measurements, taper gain corrections, and positional calibration which are used in ground data analysis. When we receive crystals that haven’t had so much rework as the EM crystals received, we expect few, if any, bad tapers. Material with bad taper shall be set aside for return to Amcrys-H or for repair in Sweden, depending on schedule constraints. | Closed
29 | CAL | Crystal raw materials - How secure is the supply of raw salt for AMCRYS-H? | History of BABAR XTAL production - we had to provide external supply of raw material because of problems in FSU of availability of processed salt Fallback is use of offcuts and scrap at cost of quality of XTAL produced. | Schindler | N. Johnson | During the engineering model development, the Swedish Consortium authorized and paid Amcrys-H for sufficient CsI salt for approximately half of the flight CsI crystal production. This material, enough remaining for approximately 800 crystals, is in hand at Amcrys-H. As a result of this discussion at the peer review, the Swedish Consortium has negotiated with Amcrys-H for the remaining CsI salt and authorized its immediate procurement. The salt in hand represents approximately 4 months of production, which started at the end of March. The delivery of CsI crystals to Sweden is well off the critical path for manufacture of CDEs. The later deliveries have approximately 4 months of schedule float. | Submitted
30 | CAL | In general block diagrams are too high level. For a CDR presentation need to have more detailed and complete diagrams. Diagrams don’t seem to link up by signal names. In GCRC design details diagram (7-32): Itemize commands being handled, Show data formats and contents, Temperature telemetry – how many? Health telemetry? Need to show timing diagrams and analog waveforms associated with block diagrams. (7-34 is a good example.) Need to provide or reference documents related to the optical/electronics front-end design explaining the physics of light à electrical conversion, equations, etc. Design and revision history may not be necessary for presentation. If at all – may be provided as backup material on web page. Show a typical LVDS circuit details. A/D and DAC basis characteristics – how many bits? How fast, etc? |  | Sosino | N. Johnson | See attached updated presentation slides (15 pages) that address the requested topics. (Additional Data provided) | Submitted
1 | Elec | GRB alert line from SC is an interrupt signal. Can the interrupt rate be controlled (or shut-off) if as a result of a failure the rate becomes too high? |  | Schalk | Haller | The GBM discrete alert signal can be masked/disabled within the RAD750 processor board. (Programming) | Closed
2 | Elec | Provide a complete, sequential timeline of all the events in the boot-up sequence from initial application of power to completion of the boot-up sequence. Provide this timeline for both Primary Boot Process and the Secondary Boot Process. | Primary Boot Code is treated as critical code. Secondary Boot Code is essential to run the application code | Scott | Haller | LAT-TD-01806 describes the primary boot sequence in time order. We agree that the document needs to be extended to include the secondary boot also. The goal is to provide that at CDR, or 4 weeks after CDR at the latest. | Closed
3 | Elec | Provide an explanation of the terms and concepts of “Framework”, “Event Fabric”, “Task”, and “Package” and how they fit into the flight software architecture | It is not clear that these terms have been used in an industry-wide sense and how they provide an integrated architecture and what “pieces” might be missing. | Scott | Haller | Many of these terms are already defined in detail in the appropriate FSW documents. The FSW team will provide a summary of terms in a separately released document prior to CDR. | Closed
4 | Elec | Show the allocation and derivation of requirements from the Mission System Specific to the Flight Software Requirements showing the Level III (and Level IV) Software Requirements and where the designs addressing them are instantiated ( i.e., in what package, task, build, etc. they are contained) | This was done for the electronics hardware but was not done for the FSW, contributing to some confusion about the allocation and derivation of FSW requirements. Only follow the FSW portion of the allocation/derivation since hardware was done. | Scott | Haller | A version of the SRS with the references to higher level requirements documents included (these references were also included in the SRS review presentation) will be released prior to CDR. We are also planning a series of slides in the CDR that maps requirements to tasks, tasks to packages, and packages to releases. This sequence of slides will also be included in a revised release of the development plan prior to the CDR. | Closed
5 | Elec | Show how “Overview” p. 4, “Overview” p. 7, “Flight Software I” pp. 3,4, “Flight Software I” p. 26, and “Flight Software III” p. 25 are equivalent representations of the same system (and traceable to one another). Show us the level of development required for each element for each build EM1, EM2, Flight, etc. | Need to demonstrate requirements, architectural design and implementation consistency/ equivalence | Scott | Haller | We combined this RFA with RFA4, so see RFA4. | Closed
6 | Elec | Specify when detailed design documents (at the level of task inputs and outputs) will be under change control |  | Jacobsen | Haller | According to the MAR (Mission Assurance Document) the detailed design documents are due at the time of the final release. At that time they undergo change control. Higher level FSW documents are under change control at CDR, according to the MAR. Design information that evolves with the code is kept in the SDF (SW development folder) and that is managed by CVS, so there is a complete history of revisions. | Closed
7 | Elec | LAT Electronics and FSW testing, as well as Instrument testing, assumes a timing source that meets the fidelity specified in the SC-LAT IRD (+- 1usec per 100 sec accuracy). Current SIIS design does not meet that accuracy, and LAT does not intend to implement an accurate source in its own GSE. Please identify (both subsystem and instrument level) specific testing limitations. If possible, identify tests in test plan/ procedure documents. |  | Andrews | Haller | This problem has been removed since peer-CDR. The SC SIIS will provide the fidelity as called out in the SC-LAT IRD. | Closed
8 | Elec | LAT Electronics and FSW testing, as well as Instrument testing, assumes a Two-sided (Primary and Redundant) Spacecraft – Instrument Interface Simulator (SIIS). Current SIIS design is single-string. Please identify specific testing limitations (both s/s level and instrument level) given a single-string SIIS. If possible, point to specific tests in subsystem and instrument test plan/procedures. | There is some amount of risk associated with not testing the LAT with two-sided GSE (unknown or unidentified feedback/noise on redundant lines). | Andrews | Haller | During development and verification testing, at the sub-system, as well as on the instrument level, the primary and redundant inputs and outputs have to be verified. This includes MIL1553 and discrete LVDS lines from/to the prim and redundant LAT SIU's, as well as the 1PPS signal and the LVDS science interface signals from/to the primary and redundant LAT GASU's. Furthermore there are 96 analog monitoring one set prim, and one set redundant) to be verified.Presently there seems only to be a single-string SIIS planned. In other words only one set of the primary and redundant LAT inputs and outputs would be connected simultaneously. The other port is electrically disconnected. That is not how the SC will be connected for the mission. However since the LAT inputs from the prim and redundant SC outputs are either logically directly OR'ed (e.g. Reset to CPU) or Maskable Or'ed (e.g. SC-Not-Ready signal from SC science interface) one relies on that a not-connected input/output yields the same results as an electrically connected one. This is in respect to DC, AC, as well as it relates to grounding/EMI, cross-talk, and signal return characteristics. Furthermore the process of powering one SC port down, and then powering the other set up can not be simulated. Power-down or power-up is one crucial test since the two interface are merged in the LAT and power-down and up might put the interface in a state which locks up. The system is designed to prevent that, but of course that applies to all interfaces. The simulator is supposed to verify the design and to prevent surprises at integration time. There is a risk in that this major section of the interface compatibility, as well as LAT functionality, and performance tests can not be performed. A problem in this section may lead to a major delay at integration time, if there is a problem discovered. This only applies to the MIL1553, discrete, and science interface section. For those interfaces, a single-string simulator is not sufficient. A second copy of the interface simulator is required for that test, at least that seems to be the simplest way to provide the prim/redundant simulator. It does not apply to the 96-port analog monitoring part since the prim and redundant LAT sensors are electrically independent. Thus for the monitoring interface, only a single-string simulator is sufficient. Therefore the solution seems to be to provide one copy of the SIIS with a single-string of all interfaces, plus a second copy which does not need the analog monitoring port interface. Power Interface: for the heater power, regulated or unregulated, the single string SIIS is sufficient since the heaters are block redundant and the prime power feeds and heaters are completely decoupled from the redundant set. For the SIU feeds the same is true. For the main DAQ it is desired to have the prim and redundant SC feeds, since they are routed to both LAT PDU's. If one if the main feeds is powered, the redundant feed interface should behave exactly as a feed which is not powered (and not just "not connected"). It is not clear (to the LAT) what the exact circuit the SC is implementing is at this time, so the risk associated to not having a full interface simulator can not be assessed correctly. | Closed
9 | Elec | Decide on whether or not to populate the parts for functions not needed in the EPUs. | Manufacturing and test plans will be impacted by this decision. In addition, some minor design changes will be required to properly terminate unused outputs and to properly tie unused inputs high or low | Huegel | Haller | This RFA is specific to the Spacecraft Interface Board (we are aware that the name is not correct anymore since this board is also used in the EPU crates). The plan is as follows: the PWB’s are identical, only the loading is slightly different in the following: EPU SIB has ½ the EEPROM loaded compared to the SIU SIB, EPU SIB has MIL1553 components not loaded. Instead there are pull-ups/downs loaded to handle otherwise floating nodes. The plan is to have two different loading diagrams. The test procedure for the two versions are the same with the exception that the tests of the removed block on the EPU SIB are skipped. All board level qualification tests are planned for both versions. The crate level qualification is planned only for the SIU crate (the EPU crate is the same with the exception of the missing components on the SIB). Acceptance tests are planned for all components/crates. | Closed
10 | Elec | Agree on a metric, or set of benchmarks, by which to evaluate efficiency of data reduction (event rejection) algorithm | Clearly the software team is aware of the issue; they need something like a set of Monte Carlo events, with noise, etc. to evaluate algorithm efficiency. Need to measure ho big a baby we can throw out with the bath water | Smith | Haller | Tests have already been run on data sets of photons that indicate large numbers of photons are being rejected. However, preliminary analysis suggests that the rejected photons are being legitimately rejected because they are not reconstructable. More detailed analysis is necessary to determine the statistics for rejection of reconstructable photons. There is a need for a test data set of tagged photons (with tags indicating which photons are reconstructable), so that reliable statistics can be generated. Richard Dubois’ group is working on generating this data set. The goal is to have a preliminary report by CDR and a complete analysis by 60 days after CDR. | Closed
11 | Elec | Create an independent test team. (Recommend a level of effort equivalent to development effort.) Test team should have minimal contribution to the Requirements and design of the software. | The appropriate level and nature of the software test program are not being achieved. | Zellar | Haller | Our development plan acknowledges that an independent perspective can, under certain circumstances, be valuable, but also recognizes that we do not have the budget or personnel resources for a separate team of similar size to the development team. When the project was approved, this item was not in the requirements (MAR), plan, schedule, or budget. | Not Accepted
12 | Elec |  |  |  | Haller |  | Retracted
13 | Elec | Modify the Requirements document to reflect actual requirements of the GRB alert notification, namely the software is only required to service the discreet input. It does not need to switch filter parameters, or take additional actions initiated by this event. | The GLAST project stated that the LAT should not make accommodation for receiving this event. Since the LAT hardware is designed to accept it, and the electronics are being tested for connectivity, the software driver for the GRB interrupt should be similarly designed and tested. Software requirements should explicitly state that the interrupt is being serviced and nothing more | Zellar | Haller | Good RFA. SRS will be modified to state that the GRB alert interrupt is being serviced and that no further action is being taken. This will be included in the SRS release prior to CDR. | Closed
14 | Elec |  |  |  | Haller |  | Retracted
15 | Elec | Please provide additional information on event builder “router/switch” characteristics | Design not presented in sufficient detail to determine if network will meet timing requirements of LAT instrument. Data rate margins were presented but latency, buffering were not addressed. Interference and coordination of tasks using the network was not addressed | Schnurr | Haller | The maximum required trigger/event rate to be handled is 13 KHz. 2) The average event-size from the clients to the EBM is 1 Kbyte and consists of: TEM: 60 bytes x 16 TEM's = 960 bytes, AEM: 20 bytes x 1 = 20 bytes, GEM: 52 bytes x 1 = 52 bytes 3) the max data flowing into the event builder (EBM) is 13 KHz x 1 Kbytes = 13 Mbytes/sec. 4) the max data flowing in regular run mode from the event-builder to each EPU is 13 Mbytes/s divide by 2 = 6.5 Mbytes/s This compares to the bandwidths in the LAT into the event builder: 18 links x 20 Mbits/sec = 90 Mbytes/sec (need 13) from the event-builder to the EPU: 8 x 20 Mbits/sec = 20 Mbytes/s (need 5) Instantaneous higher rates are averaged by buffering on the TEM and the Event-builder (FIFO's). The FIFO depths implemented have been determined from simulation of the network traffic. | Closed
16 | Elec | Program should verify that the SU ROM/VxWorks BSP meetsw the program requirements. At a minimum the wait state settings/exception handling and bridge chip error handlers should be reviewed by the program. Rad750 error handler provided by the vendor should be reviewed as well | User can induce errors into the Rad750/Bridge which might not leave a signature after reset | Schnurr | Haller | This is extremely good advice and the FSW team will be implementing it. The team will ensure that all exception vectors lead to known locations. During controlled reboots, bridge chip info will be captured and stored in RAD750 memory for examination after reboot. The team welcomes additional inputs in this area. | Closed
17 | Elec | Make sure to interface with GSFC groups about experience with Rad750 | Rad750 is new and has not been flown. GSFC has several groups planning to fly it. Rick Schnurr has volunteered to provide the contacts | Sadrozinski | Haller | Rick Schnurr (GSFC) already emailed the contact information of Mark Voyton at GSFC. The plan is to start exchanging information after CDR. | Closed
18 | Elec | A bulleted list of functionality that is needed in each package for EM1/EM2/… |  | Schalk | Haller | The concept of functionality is more related to tasks than packages for the FSW. Packages are more related to how the actual code is organized, stored and compiled. A task is accomplished by drawing on the integration of a number of packages. The list of functionality in each release has been previously published, most recently in the peer review. The updated CDR presentation will include more details including the relationship between tasks, packages and releases. | Closed
19 | Elec | Please provide the document that describes how TFFS is integrated into the LAT FSW. Include info on drivers/telemetry | Level of effort needed to implement TFFS is not clear from the information presented. Not clear that TFFS meets mission requirements. It is typical to havea RAM buffer that is used for volatile updates. A commit process can then be used to save the changes to the EEPROM. How does the TFFS implement this? If the writes are controlled by the TFFS are they counted by driver to verify performance? | Schnurr | Haller | The LAT FSW does upload into RAM (not EEPROM) and does employ a commit process to save the changes into EEPROM. The TFFS principally maintains even wear on all locations of the EEPROM by managing where information gets written. Much of this RFA was satisfied at the time of the review when the reviewer was shown a copy of Figure 1 from Section 3.2 of the February LAT FSW Design Workshop Minutes. The diagram will be included in a formally released FSW document. | Closed
20 | Elec | Check that the ACD PMT HV hardware protection (current limit) does not interfere with GRB or Solar Flare science | If the current due to particles from GRB or Solar Flares are larger than those expected in the SAA, the protection circuit would shot the HV off and prevent the instrument from acquiring science data | Sadrozinski | Haller | The ACD PMTs are protected by series resistors to limit their current in case of extremely high rates. The requirement on the ACD is that each tile maintain its performance at rates up to 3 kHz, compared to the nominal value of about 1 kHz. Measurements (LAT-TD-01168-D1) have shown that the ACD phototubes can actually handle much higher rates, equivalent to nearly 500 kHz of MIP signals, without performance degradation.There is no automatic shutoff of the HV to the ACD tubes generated by the LAT Electronics. The plan for the SAA is to send stored commands to change the HV on entering and exiting the SAA, not based on the ACD rates but on predicted times. The backup to these commands is the current limiting on the ACD resistor networks. | Closed
21 | Elec | Modify the following documents 1. Requirements Document- include more detail and describe more fully requirements on software that will allow independent development of test procedures. 2. Test Plan a) include a requirement to test Procedure Matrix. This matrix would show mapping from requirements to procedures and procedures to requirements. b) include functional descriptions of simulators and specialized hardware required to complete a successful test program. Reference simulator design/requirements docs as required.c) include acceptance testing in software test plan. Acceptance tests will exercise the FSW as a fully delivered system at the end of Test program and will include full regression testing of all software build tests, “stress” tests, and significant operational scenarios. d)include evidence and conclusions of how the planned software test program is achievable. |  | Zellar | Haller | The SRS has been modified based on specific technical comments resulting from the SRS review. Beyond that the LAT FSW team has no plans to create a new release at a significantly higher level of detail. As described in the development plan, the existing SRS has a sufficient level of detail to define the scope of the project and allow the team to proceed with the design process. That was assumed when the project, including plan, schedule and cost, was approved. The LAT FSW Test Plan will be revised by CDR to include the desired matrix and descriptions of the tools and environment required for testing. Description of acceptance testing is included in the current revision, but will be clarified. | Not Accepted
22 | Elec | Accelerate scheduled delivery of 1. Design/Architecture document- present a draft of a highlevel design document capable of showing self-consistency across software and between software modules, and that important software functions are thought out. Present draft at CDR. 2. Algorithm document- present a draft algorithm document at CDR that identifies types and high level functions of science algorithms needed by FSW. | Design/Architecture is needed to demonstrate capability to create necessary software for LAT. Algorithm is needed to mitigate the risk of schedule delays and for software testing | Zellar | Haller | The revised MAR does not require a detailed design document until the delivery of the full LAT FSW build. The purpose of the peer reviews is to present design information for review , to demonstrate understanding of architecture, function, etc. There are several peer reviews called out in the FSW development plan. Most likely these will be scheduled to coincide with overall LAT reviews. The event filtering algorithms are extremely specialized and complex. The bulk of the code is already written and contains detailed documentation embedded in it. The relevant scientists who can provide review and guidance on the algorithm development are conversant with this format and use it directly. Production of a detailed algorithm document represents a significant amount of overhead and is not part of our development plan. | Not Accepted
23 | Elec | In order to understand EMI, perform SPICE analysis of the LAT internal power distribution bus. Include models for S/C DC/DC converters, all filters, and LAT DC/DC converters. Use model to establish EMI self-compatibility, i.e. will the internal EMI sources cause problems. Look at inrush issues as well | Internal EMI may cause excessive instrument noise | Schnurr | Haller | We are in the process of getting sufficient information from the DC/DC converter vendors to be able to simulate the system realistically. We won’t be able to obtain the complete spice model from the vendor (they do not want to distribute it because it effectively is the circuit as built), however they are working with us to get a good representation of their converter. This will take a few more weeks and may require transfer of some funding to the vendor. Work in progress. | Closed
24 | Elec | For the CDR, revise the grounding scheme chart to make it more clear and accurate. |  | Huegel | Haller | We noticed, too late, that the grounding diagram shown at the peer-CDR was wrong, it was the PDR slide. The CDR presentation will show the correct slide. | Closed
25 | Elec | Consider adding capability for FSW to monitor S/C keep-alive, and take appropriate action when they are no longer received | Lack of S/C keep-alive indicates S/C problem -> unknown S/C state. LAT needs to safe itself | Leibee | Haller | The LAT FSW team agrees with this idea and will adopt the overall concept of monitoring the attitude message from the spacecraft as a keep-alive signal. However, the details of how the LAT FSW will respond to loss of the keep-alive must still be worked out. The plan is to define this before the EM2 peer review. | Closed
26 | Elec | 1. Assess the TEMS box designs using dynamic analysis based upon the current PF spectrum. A damping value of 5% is recommended and the net CG response and interface forces should be output for direct calculation of fastener margins. It is also recommended that model’s interface assume a pinned boundary (i.e., 3 translational dofs are fixed). 2. Note that the Page 5 Lateral Load factor as currently shown is incorrect, and should be changed to 7.4 G’s to agree with the LAT Environmental Specification. It should also be noted that the Lateral and Axial load factors must be applied simultaneously in all combinations. | 1. While the use of SDOF detailed on pages 33-35 appears conservative, use of more conservative boundary conditions and actual random the results may change. A proper random analysis is particularly important considering that random vibration represents the dominant load case for the TEMS. 2. Correct for update to LAT Environmental Specification | Fransen | Haller | a) The FEM models of the TEM boxes will be changed to pinned boundary condition versus fixed. A modal search will be performed and the resulting data to be subject to a random input per the specification with a 5% damping factor. Stresses will be output.Bolt loads will be calculated. b) Models will be evaluated using the updated lateral load factors applied simultaneously. Since the random loads are generally limiting, the static load factors may be compared to resultant loads from dynamic analysis to see if they are enveloped by previous load cases. | Closed
[6 empty] | Total | 179
[6 empty] | Closed | 102
[6 empty] | Close at CDR | 6
[6 empty] | Submitted | 44
[6 empty] | Not Accepted | 8
[6 empty] | In Work | 15
[6 empty] | Retracted | 2
[6 empty] | No status | 2

## SC PDR
RFA | Title | Originator | Responsible Org. | Assignee | Due Date | Response | Date Submitted to GPO | Project Office Review Status | Date Submitted to Code 300 | Date Approved by Originator | Closure Date
1 | Inadvertent Commands into Uncontrolled SC Modes | Steve Scott | Spectrum | Jordan Evans | 2003-11-21 | SC PDR RFA 1 Response.doc | 2004-01-05 | PM Approved 3/2/2004 | 2004-03-02 | SS approved via email 3/2/04 | 2004-03-02
2 | Use of Excess ELV Mass Margin | Joe Wonsever | GPO | Norm Rioux | 2003-11-28 | SC PDR RFA 2 Response.doc | 2004-04-21 | PM Approved 5/19/04 | 2004-05-19 | JW approved via email 5/19/04 | 2004-05-19
3 | Requirement for LAT/Spacecraft Out of Plane Distortions | Joe Wonsever | GPO | Chris Connor | 2003-10-15 | SC PDR RFA 3 Response RevB.doc | 10/20/2003 9/17/2004 | PM Approved 1/7/04 RevB addresses I/F forces and displacements PM Approved 9/19/04 | 1/15/2004 9/19/2004 | JW approved via email 1/5/05 | 2005-01-05
4 | Insufficient Margin on Battery Thermal Control System | Jean Olivier | Spectrum | Aaron Gilchrist | 2003-08-15 | SC PDR RFA 4 Response.doc | 2003-09-10 | PM Approved 3/2/2004 | 2004-03-02 | JO approved via email 3/2/04 | 2004-03-02
5 | Solar Array Wing Level Dynamic Testing | Jean Olivier | Spectrum | Deva Ponnusamy | 2003-11-21 | SC PDR RFA 5 Response.doc | 2004-03-08 | PM Approved 4/15/2004 | 2004-04-16 | JO approved via email 4/17/04 | 2004-04-17
6 | Low Observatory Mass Margin | Marty Davis John Hrastar | GPO | Norm Rioux | 2003-11-28 | SC PDR RFA 6 Response RevA.doc | 2004-05-10 | PM Approved 6/26/04 | 2004-06-30 | JH approved via email 6/30/04 MD approved via voicemail 7/13/04 | 2004-07-13
7 | Over-current Protection Requirements | Joe Wonsever/Fred Huegel | Spectrum | Robb Pinkerton | 11/21/2003 9/17/2004 | SC PDR RFA 7 Response RevB.doc | 2004-01-05 | PM Approved as an interim delivery 4/15/2004 PM Approved 10/4/04 | 4/16/2004 10/4/2004 | FH approved via email 10/8/04 | 2005-02-02
[6 empty] | GLAST Power Block Diagram 05-01-31.pdf |  |  |  | JW approved in a meeting 2/2/05
8 | Ten-minute Peak Power Limit for LAT | Joe Wonsever/Fred Huegel | GPO | Art Whipple | 2003-11-28 | SC PDR RFA 8 Response RevA.doc | 11/12/2003 3/10/2004 | PM Approved 3/2/2004 Rev A written to address JW comments | 3/2/2004 4/13/2004 | JW approved via email 5/19/04 | 2004-05-19
9 | Temperature Margin Philosophy | Tom McCarthy | GPO | Tom McCarthy | 2003-10-15 | SC PDR RFA 9 Response.doc | 2003-08-15 | PM approved 12/8/03 | 2003-12-11 | TM approved via email 12/18/03 | 2003-12-18
10 | Reliability of Series Redundant Thermal System | Tom McCarthy | Spectrum | Aaron Gilchrist | 2003-10-15 | SC PDR RFA 10 Response.doc | 2003-09-10 | PM Approved 3/2/2004 | 2004-03-02 | TM approved via email 4/6/04 | 2004-04-06
11 | Spacecraft Radiator Design Margin | Tom McCarthy | Spectrum | Aaron Gilchrist | 2003-10-15 | SC PDR RFA 11 Response.doc | 2003-09-10 | PM approved 12/8/03 | 2003-12-11 | TM approved via email 12/18/03 | 2003-12-18
12 | Lack of Preliminary Thermal Design Information | Tom McCarthy | Spectrum | Aaron Gilchrist | 2003-11-21 | SC PDR RFA 12 Response RevC.doc | 1/5/2004 12/10/2004 1/14/2005 | PM Approved 3/2/2004 Update sent to TM 12/10/04 | 3/2/2004 2/18/2005 | TM approved via email 2/22/05 | 2005-02-22
13 | Temperature Level Exceedances | Tom McCarthy | Spectrum | Aaron Gilchrist | 2003-10-15 | SC PDR RFA 13 Response.doc | 2003-09-10 | PM approved 12/8/03 | 2003-12-11 | TM approved via email 12/18/03 | 2003-12-18
14 | Corporate Experience/Lessons Learned on Margin Depletion | Earl Reese | Spectrum | Jordan Evans | 2003-11-21 | SC PDR RFA 14 Response.doc | 2004-01-05 | PM Approved 2/19/04 | 2004-02-20 | ER approved via email 2/24/04 | 2004-02-24
15 | Updated Mass Properties Verification | Son Ngo | Spectrum | Ron Zitek | 2003-10-15 | SC PDR RFA 15 Response RevA.doc | 1/29/2004 3/30/2004 | PM Approved 2/19/04 Update based on SN comments approved by PM 5/10/04 | 2/20/2004 5/11/2004 | SN approved via email 5/19/04 | 2004-05-19
16 | Handling Load Evaluation of Fill and Vent Valve Boom | Son Ngo | Spectrum | Scott Dow | 2003-11-21 | SC PDR RFA 16 Response.doc | 2004-01-05 | PM Approved 2/19/04 | 2004-02-20 | SN approved via email 2/23/04 | 2004-02-23
17 | Expedite Decision on Need for De-Orbit Propulsion | Jean Olivier | GPO | Terry Ford | 2003-11-28 | SC PDR RFA 17 Response.doc | 2004-01-29 | PM Approved 2/19/04 | 2004-02-20 | JO approved via email 2/22/04 | 2004-02-22
18 | Wheel Torque Noise in Jitter Analysis | John Gagosian | Spectrum | Igor Lazbin | CDR | SC PDR RFA 18 Response.doc | 2004-03-10 | PM Approved 4/15/2004 | 2004-04-16 | JG approved via email 5/3/04 | 2004-05-03
19 | Overwriting the RAD750 Flight Software | Steve Scott | Spectrum | Cyp Colbert | 2003-10-15 | SC PDR RFA 19 Response RevA.doc | 2004-01-05 | PM Approved 4/15/2004 Steve Scott wants to hold open until Mission Robustness complete EA sent update to SS 9/3/04 | 2004-04-16 | SS approved via email 9/8/04 (other RFAs open for EEPROM and boot code) | 2004-09-08
20 | Missing Software Code Descriptions | Steve Scott | Spectrum | Cyp Colbert | 2003-11-21 | SC PDR RFA 20 Response.doc | 2004-01-05 | PM Approved 4/15/2004 | 2004-04-16 | SS approved via email 5/3/04 | 2004-05-03
21 | Vague and Ambiguous Software Requirements | Steve Scott | Spectrum | Cyp Colbert | 2003-10-15 | SC PDR RFA 21 Response.doc | 2003-09-10 | PM Approved 1/7/04 | 2004-01-15 | SS approved via email 3/4/04 | 2004-03-04
22 | Packaging and Manufacturability Peer Review | Steve Scott Tom McCarthy | Spectrum | Kendall Nii | 2003-11-21 | SC PDR RFA 22 Response RevE.doc | 1/5/2004 12/10/2004 1/14/2005 1/30/2005 | PM Approved 5/17/04, Updated response sent to TM 12/10/04 KG OK AV comment re: TBDs in structal analysis Comment sent back to SASS on 3/4 re: TBD Agreed in meeting with Goans to provide to SS and TM 4/14/05 | 2005-04-14 | SS approved via email 6/1/05 | 2005-06-07
[10 empty] | TM approved via email 6/7/05 |  | Resent on 4/28
23 | Actuation of S-Band Mechanical Transfer Switch | Joe Wonsever | Spectrum | Kendall Nii | CDR | SC PDR RFA 23 Response RevA.doc | 2004-04-01 | PM Approved 6/6/04 | 2004-06-07 | JW approved via email 1/5/05 | 2005-01-05 | Reminder sent to JW 6/30, 7/22, 8/13 & 9/13
24 | C&DH Self Maintainability During Periods of Poor Contact | Bob Menrad | Spectrum | Mark Davis | 2003-10-15 | SC PDR RFA 24 Response.doc | 2004-01-29 | PM Approved 2/19/04 | 2004-02-20 | BM approved via email 3/8/04 | 2004-03-08
25 | Fault Management Design Peer Review | Steve Scott | Spectrum | Kendall Nii | Peer Reviews | SC PDR RFA 25 Response.doc | 2004-03-10 | PM Approved 5/14/04 | 2004-05-14 | SS approved via email 5/16/04 | 2004-05-16
26 | Flight Heritage of Lambda DC-DC Converter in the PRU | Fred Huegel | Spectrum | Robb Pinkerton | 2003-10-15 | SC PDR RFA 26 Response RevD.doc | 9/10/2003 6/9/2004 | PM Approved 6/9/04 | 2004-06-09 | FH approved via email 7/1/04 | 2004-07-01
27 | LAPSS of Solar Arrays Before Spacecraft Testing | Fred Huegel | Spectrum | Robb Pinkerton | 2003-10-15 | SC PDR RFA 27 Response.doc | 2003-09-10 | PM approved 12/8/03 | 2003-12-11 | FH approved by email 12/15/03 | 2003-12-15
28 | Erosion of Solar Array Insulation | Fred Huegel | Spectrum | Robb Pinkerton | 2003-10-15 | SC PDR RFA 28 ResponseRevA.doc | 2004-01-29 | PM Approved 2/19/04 | 2004-02-20 | FH approved by email 2/24/04 | 2004-02-24
29 | Verified Thermal Control System Design | Tom McCarthy | Spectrum | Aaron Gilchrist | CDR | SC RFA 29 Response.ppt | 2004-02-17 | PM Approved 3/17/04 | 2004-03-22 | TM approved via email 4/6/04 | 2004-04-06
30 | Propulsion System Thermal Design | Tom McCarthy | Spectrum | Aaron Gilchrist | 2003-10-15 | SC PDR RFA 30 Response.doc | 2003-09-10 | PM approved 12/8/03 | 2003-12-11 | TM approved via email 12/18/03 | 2003-12-18
31 | Propulsion System Bimetallic Joint | Tom McCarthy | Spectrum | Scott Capehart | 2003-12-12 | SC PDR RFA 31 Response RevB.doc | 3/8/2004 6/9/2004 7/22/2004 8/12/2004 | PM Approved 8/16/04 | 2004-08-18 | TM approvied via email 8/18/04 | 2004-08-18
32 | Review of the Cup-Cone Interface for Solar Array and Antenna Deployment | Son Ngo | Spectrum | Deva Ponnusamy | 2003-12-12 | SC PDR RFA 32 Response.doc | 2004-03-08 | PM Approved 4/15/2004 | 2004-04-16 | SN approved via email 5/3/04 | 2004-05-03
33 | MOSFETS Derating Specification | Jim Trainor | Spectrum | Mark Porter | 2003-10-15 | SC PDR RFA 33 Response.doc | 2003-09-10 | PM approved 12/8/03 | 2003-12-11 | Mark Goans approved via email 5/20/04 | 2004-05-20
34 | Consider Building a GLAST/Spacecraft Mass Simulator | Jean Olivier | Spectrum | Scott Dow | 2003-11-21 | SC PDR RFA 34 Response.doc | 2004-01-05 | PM Approved 3/2/2004 | 2004-03-02 | JO approved via email 3/2/04 | 2004-03-02
35 | Document GN&C Dynamic Simulator Requirements | John Gagosian | Spectrum | Igor Lazbin | 2003-12-12 | SC PDR RFA 35 Response.doc | 2004-02-17 | PM Approved 3/17/04 | 2004-03-22 | JG approved via email 3/22/04 | 2004-03-22
36 | Predicts from Correlated/Validated TMM | Tom McCarthy | Spectrum | Aaron Gilchrist | 2003-10-15 | SC PDR RFA 36 Response.doc | 2003-09-10 | PM approved 12/8/03 |  | TM approved via email 12/18/03 | 2003-12-18
37 | Mass Properties Testing | Son Ngo | Spectrum | Ron Zitek | 2003-10-15 | SC PDR RFA 37 Response RevA.doc | 9/10/2003 4/8/2004 | PM approved 12/8/03 Update based on SN comments approved by PM 5/10/04 | 12/11/2003 5/11/2004 | SN approved via email 5/11/04 | 2004-05-11
38 | Separation System Risk Assessment | Anthony Arrigo Steve Scott | GPO | Tony DiVenti | 2003-11-28 | SC PDR RFA 38 Response.doc | 2003-12-01 | PM Approved 3/2/04 | 2004-03-29 | SS approved by email 3/30/04 | 2004-03-30
39 | Solar Array Verification Plan | Son Ngo | Spectrum | Deva Ponnusamy | 2005-07-31 | SC PDR RFA 39 Response RevD.doc | 3/8/2004 3/13/2005 4/24/2005 | PM Approved 9/30/05 | 2005-10-03 | Reply to Response of GLAST SC PDR RFA.doc
40 | Risk Assessment of Early Mission Propulsion System Test | Jean Olivier | GPO | Mark Underdown | 2003-11-28 | SC PDR RFA 40 Response.doc | 2004-05-11 | PM Approved 5/24/04 | 2004-05-24 | JO approved by email 5/25/04 | 2004-05-25
41 | Combined Effects of Mass and CG | Joe Wonsever | GPO | Norm Rioux | 2003-11-28 | SC PDR RFA 41 Response.doc | 2004-03-05 | PM Approved 4/15/2004 | 2004-04-16 | JW approved via email 5/19/04 | 2004-05-19
42 | Summary of Peer Reviews | Joe Wonsever | Spectrum | Jordan Evans | 2003-11-21 | SC PDR RFA 42 Response RevA.doc | 2004-01-05 | PM Approved 2/19/04 Updated per JW comments | 2/20/2004 3/22/2004 | JW approved via email 5/19/04 | 2004-05-19
43 | Confirm X-Ray Heat Pipe Requirements | Tom McCarthy | GPO | Ron Kolecki | 2003-11-28 | SC PDR RFA 43 Response.doc | 2004-03-04 | PM Approved 5/19/04 | 2004-05-19 | TM approved via email 5/19/04 | 2004-05-19
[10 empty] | Total RFAs | 43
[10 empty] | # Closed | 42
R1 | Thermal Coating Committee Review | Tom McCarthy | GPO | Ron Kolecki | N/A | SC PDR Recomm 1 Response.doc
R2 | Under Reporting of Temperature Margin Against Allowable Range | Tom McCarthy | Spectrum | Aaron Gilchrist | N/A | SC PDR Recomm 2 Response.doc
R3 | Observatory Lift from LAT Interface | Son Ngo | GPO | Sharon Seipel | 2003-10-10 | SC PDR Recomm 3 Response.doc
R4 | High PRU Temperature Fault Mode | Fred Huegel | Spectrum | Kendall Nii | N/A | SC PDR Recomm 4 Response.doc
R5 | Recommend Designing CPTs and E-to-E Tests to Support MOCs Off-line Needs (Mass Props Testing - Bad Title) | Bob Menrad | Spectrum | Ron Zitek | N/A | SC PDR Recomm 5 Response.doc
R6 | Consider Bakeout of Harness and Thermal Blankets | Marty Davis | GPO | Ron Kolecki | N/A | SC PDR Recomm 6 Response.doc
R7 | FPGA Design Review | Steve Scott | GPO | Ron Kolecki | N/A | SC PDR Recomm 7 Response.doc
R8 | Structural Alignment Testing | Son Ngo | Spectrum | Ron Zitek | N/A | SC PDR Recomm 8 Response.doc
R9 | SIRU Risk Mitigation Plan | John Gagosian | Spectrum | Jordan Evans | N/A | SC PDR Recomm 9 Response.doc
R10 | Purge Gas Contaminants | John Gagosian | Spectrum | Jordan Evans | N/A | SC PDR Recomm 10 Response.doc

## SC FSW PDR
RFA # | Title | Originator | Responsible Org. | Assignee | Due Date | Response | Date Submitted to GPO | Project Office Review Status | Date Submitted to Code 300 | Closure Status | Closure Date
1 | Describe Hotbench Spares Philosophy | Steve Scott | Spectrum | Tim Irwin | 2003-10-15 | FSW PDR RFA 1 Response.doc | 2003-09-10 | PM Approved 1/7/04 | 2004-01-15 | SS approved via email 3/4/04 | 2004-03-04
2 | Describe Software Maintenance During Hotbench Delivery | Steve Scott | GPO | Erik Andrews | 2003-11-28 | FSW PDR RFA 2 Response.doc | 2003-11-17 | PM Approved 2/19/04 | 2004-02-20 | SC approved via email 3/4/04 | 2004-03-04
3 | Timely Involvement of NASA WV IV&V | Steve Scott | GPO | Erik Andrews | 2003-11-28 | FSW PDR RFA 3 Response.doc | 2003-11-17 | PM Approved 2/19/04 | 2004-02-20 | SC approved via email 3/4/04 | 2004-03-04
4 | Project Level Transition Plan Including Hotbench Access | Bob Menrad | GPO | Erik Andrews | 2003-11-28 | FSW PDR RFA 4 Response.doc | 2003-11-17 | PM Approved 2/19/04 | 2004-02-20 | BM approved via email 3/8/04 | 2004-03-08
5 | Skipped Commands After 8 Commands Per Second | Lisa Shears | Spectrum | Cyp Colbert | 2003-10-15 | FSW PDR RFA 5 Response RevB.doc | 2004-01-05 | PM Approved 8/2/04 | 2004-08-06 | LS approved via email 8/6/04 | 2004-08-06
6 | General Flight Software Requirements Questions | Lisa Shears | Spectrum | Cyp Colbert | 2003-11-21 | FSW PDR RFA 6 Response.doc | 2004-01-05 | PM Approved 5/19/04 | 2004-05-19 | LS approved via email 5/20/04 | 2004-05-20
7 | Consider Procuring a Second Hotbench | Ann Merwarth | GPO | Erik Andrews | 2003-11-28 | FSW PDR RFA 7 Response.doc | 2004-05-21 | PM Approved 5/25/04 | 2004-05-25 | AM comments 5/26/04 M Goans closed based on Project accepting risk | 2005-04-20
8 | Description of Flight Software Formal Qualification | Steve Scott | Spectrum | Ron Zitek | 2003-11-21 | FSW PDR RFA 8 Response RevA.doc | 2004-01-29 | PM Approved 8/28/04 | 2004-09-03 | SS approved via email 9/8/04 | 2004-09-08
9 | Risk Tracking | Ron Zellar | Spectrum | Jordan Evans | 2003-11-21 | FSW PDR RFA 9 Response.doc | 2004-01-05 | PM Approved 2/19/04 | 2004-02-20 | EA worked with RZ to address comments Email from RZ to EA closed on 4/5/04 | 2004-04-05
10 | Independent Verification Team for GN&C Algorithms | Ron Zellar | Spectrum | Igor Lazbin | 2003-11-21 | FSW PDR RFA 10 Response RevA.doc | 2004-02-17 | PM Approved 8/2/04 | 2004-08-06 | RZ approved via email 8/18/04 | 2004-08-18
11 | Delivery of Simulink Model Definition Files | Ron Zellar | Spectrum | Al Lepore | 2003-12-12 | FSW PDR RFA 11 Response RevA.doc | 2004-02-17 | PM Approved 3/17/04 PM Approved 1/31/05 | 2005-01-31 | RZ approved via email 2/1/05 | 2005-02-01
12 | Security of Sensitive Elements of the Flight Software | Ron Zellar | Spectrum | Cyp Colbert | 2004-02-09 | FSW PDR RFA 12 Response.doc | 2003-09-10 | PM Approved 3/2/2004 | 2004-03-02 | RZ approved via email 3/2/04 | 2004-03-02
13 | Plan to Mitigate the Risk of Resource Sharing With Swift | Steve Scott Steve Husty | Spectrum | Al Lepore | 2003-12-12 | FSW PDR RFA 13 Response.doc | 2004-03-08 | PM Approved 4/15/2004 | 2004-04-16 | SS approved via email 5/3/04 | 2004-05-03
14 | Assumptions Used to Convert Lines of Code to Manpower Needs | Frank Martin | Spectrum | Cyp Colbert | 2003-11-21 | FSW PDR RFA 14 Response.doc | 2004-01-05 | PM Approved 2/19/04 | 2004-02-20 | FM approved via email 2/21/04 | 2004-02-21
[10 empty] | Total RFAs | 14
[10 empty] | # Closed | 14

## LAT CDR
RFA # | Title | Originator | Responsible Org. | Assignee | Due Date | Response | Date Submitted to GPO | Project Office Review Status | Date Submitted to Code 300 | Closure Status | Closure Date
1 | On-orbit Performance of Event Filtering Software | Fred Huegel/Don Kniffen | SLAC | Ritz | 2003-12-01 | LAT CDR RFA 1 Response.doc | 2004-03-30 | PM Approved 5/19/04 | 2004-05-19 | DK approved via email 5/19/04 | 2004-06-04
FH approved via email 6/4/04
2 | LAT Baseplate Mock-up to Manufacturer for Harness Fabrication | Fred Huegel | SLAC | Haller | 2003-10-31 | LAT CDR RFA 2 Response RevB.doc | 2/12/2004 8/24/2004 | PM Approved 8/2/04 Rev B to address FH comments sent PM Approved 8/28/04 | 8/6/2004 8/30/2004 | FH approved via email 8/30/04 | 2004-08-30
3 | Conducted Emissions and Conducted Susceptibility | Fred Huegel | SLAC | Horn | 2003-10-15 | LAT CDR RFA 3 Response.doc | 2003-08-29 | PM Approved 2/19/04 | 2004-02-20 | FH approved by email 2/24/04 | 2004-02-24
4 | Electrical Derating Criteria for MOS Transistors in the DAQ | Fred Huegel/Scott Kniffen | SLAC | Haller | 2003-10-31 | LAT CDR RFA 4 Response.doc | 2004-02-12 | PM Approved 5/24/04 | 2004-05-24 | FH approved by email 5/26/04 | 2004-06-10
SK approved via email 6/10/04
5 | Qualification Method for MCM Burn In | Fred Huegel/Scott Kniffin | SLAC | R. Johnson | 2003-10-31 | LAT CDR RFA 5 Response RevA.doc | 2/20/2004 4/26/2004 | PM Approved 3/17/04 Update based on SK comments approved by PM 5/10/04 | 3/22/2004 5/11/2004 | SK approved via email 6/10/04 | 2004-06-10
6 | Electrical Derating Criteria Used on ASICs | Fred Huegel/Scott Kniffin | SLAC | Parts | 2003-10-31 | LAT CDR RFA 6 Response RevB.doc | 3/31/2004 9/9/2004 | PM Approved 9/12/04 | 2004-09-13 | SK approved via email 9/13/04 FH approved via email 9/14/04 | 2004-09-14
7 | Verification Plan for LAT Hardware and FSW Control of VCHP | Fred Huegel/Chris Bebek | SLAC | Haller | 2003-10-31 | LAT CDR RFA 7 Response RevA.doc | 11/18/2003 8/23/2004 | PM Approved 9/7/04 | 2004-09-07 | FH approved via email 9/7/04 CB approved via email 9/7/04 | 2004-09-07
8 | Complete Selection Study of XML vs MySQL | Ron Zellar | SLAC | Bator | 2003-10-15 | LAT CDR RFA 8 Response.doc | 2003-08-29 | PM Approved 2/19/04 | 2004-02-20 | RZ approved by email 2/27/04 | 2004-02-27
9 | Conduct Detailed Design Reviews | Ron Zellar/Steve Scott/ Ann Merwarth/Ed Tadlock | SLAC | Haller | 2003-12-01 | LAT CDR RFA 9 Response RevA.doc | 2004-02-12 | PM Approved 3/17/04 | 2004-03-22 | Updated on 3/24/04 to address RZ comments RZ approved by email 3/24/04 | 2004-03-26
SS approved by email 3/26/04
10 | Eliminating Sine Burst Testing on Full Instrument | Jim Ryan | SLAC | Nordby | 2003-10-15 | LAT CDR RFA 10 Response RevA.doc | 10/9/2003 3/2/2004 | PM Approved 2/19/04 Updated per JR comments | 2/20/2004 3/22/2004 | JR comments sent to BG, SS, CF JR approved by email 3/26/04 | 2004-03-26
11 | Use of Contingency Mass in LAT Design and Analysis | Jim Ryan/Larry Mignosa | SLAC | Nordby | 2003-10-15 | LAT CDR RFA 11 Response.doc | 2003-10-09 | PM Approved 2/19/04 | 2004-02-20 | JR Approved via email 2/20/04 | 2004-02-20
12 | Provide Comprehensive Stress Analysis Report | Jim Ryan | SLAC | Nordby | 2003-10-15 | LAT CDR RFA 12 Response.doc | 2003-10-09 | PM Approved 5/19/04 | 2004-05-19 | Paul Baird summarized Swales review JR approved via email 5/25/04 | 2004-05-25
13 | MGSE Detailed Dimension Study | Jim Ryan/Sharon Seipel/Ed Shippey | SLAC | Bloom | 2003-10-15 | LAT CDR RFA 13 Response RevA.doc | 8/29/2003 3/16/2004 | PM Approved 5/19/04 | 2004-05-19 | JR approved via email 5/20/04 | 2004-05-20
14 | Lack of ACD and Radiator MGSE Information | Jim Ryan/Sharon Seipel | SLAC | Bloom | 2003-12-01 | LAT CDR RFA 14 Response RevA.doc | 8/31/2004 1/25/2005 | PM Approved 1/28/05 | 2005-01-31 | JR approved via email 2/17/05 | 2005-02-17
15 | Mechanical Qualification Testing with Spacecraft Flexures | Jim Ryan/Sharon Seipel | SLAC | Nordby | 2003-10-15 | LAT CDR RFA 15 Response.doc | 2003-10-09 | PM Approved 2/19/04 | 2004-02-20 | JR approved via email 2/20/04 | 2004-02-20
16 | Assessment of the MECO High Frequency Transient | Jim Ryan/Sharon Seipel | SLAC | Nordby | 2003-10-15 | LAT CDR RFA 16 Response.doc | 10/9/2003 3/23/2004 | PM Approved 8/2/04 | 2004-08-06 | JR approved via email 8/9/04 | 2004-08-09
17 | Conduct Mechanical/Thermal Peer Review | Tom McCarthy/Jim Ryan | SLAC | Nordby | 2003-10-31 | LAT CDR RFA 17 Response RevA.doc | 10/9/2003 1/27/2005 | PM Approved 8/16/04 | 9/13/2004 1/31/2005 | TM approved via email 9/15/04 | 2005-03-02
JR approved via email 3/2/05
18 | Improving Temperature Margin on Tracker and Calorimeter | Tom McCarthy | SLAC | Horn | 2003-10-31 | LAT CDR RFA 18 Response.doc | 2003-11-18 | PM Approved 5/19/04 | 2004-05-19 | TM approved via email 5/19/04 | 2004-05-19
LAT-TD-02320-01.pdf
19 | Thermal Design Acceptance Criteria Under Failure Condition | Tom McCarthy | SLAC | Horn | 2003-10-15 | LAT CDR RFA 19 Response.doc | 2003-10-09 | PM Approved 2/19/04 | 2004-02-20 | TM Approved via email 2/20/04 | 2004-02-20
20 | Thermal Design Failure Mitigation Scenario | Tom McCarthy | SLAC | J. Wang | 2003-10-15 | LAT CDR RFA 20 Response.doc | 2003-10-09 | PM Approved 1/7/04 | 2004-01-15 | TM Approved via email 1/22/04 | 2004-01-22
21 | Radiator Panel MGSE and Wet Joint Process | Tom McCarthy | SLAC | J. Wang | 2003-12-01 | LAT CDR RFA 21 Response RevB.doc | 7/26/2004 8/18/2004 | PM Approved 9/12/04 | 2004-09-13 | TM approved via verbal response 9/13/04 | 2004-09-13
22 | Box Level Thermal Design Analysis | Tom McCarthy | SLAC | Haller | 2003-10-15 | LAT CDR RFA 22 Response RevA.doc | 10/9/2003 9/9/2004 | PM Approved 9/12/04 | 2004-09-13 | TM approved via verbal response 9/13/04 | 2004-09-13
23 | Observatory Level Thermal Testing Requirements | Tom McCarthy/Sharon Seipel | SLAC | J. Wang | 2003-12-01 | LAT CDR RFA 23 Response.doc | 2004-08-27 | PM Approved 9/12/04 | 2004-09-13 | TM approved via verbal response 9/13/04 | 2004-09-13
24 | Assessment of Structural-Thermal Distortions on LAT | Steve Scott | SLAC | Nordby | 2003-10-15 | LAT CDR RFA 24 Response RevB.doc | 8/29/2003 9/17/2004 | PM Approved 9/19/04 | 2004-09-20 | SS approved via email 9/22/04 | 2004-09-22
25 | Analysis and Simulation for LAT-Spacecraft Alignment | Steve Scott | SLAC | Ritz | 2003-12-01 | LAT CDR RFA 25 Response.doc | 2004-03-02 | PM Approved 3/17/04 | 2004-03-22 | SS approved via email 3/26/04 | 2004-03-26
26 | LAT and GBM Performance Comparison | Steve Scott | SLAC | Ritz | 2003-12-01 | LAT CDR RFA 26 Response.doc | 2004-03-02 | PM Approved 3/17/04 | 2004-03-22 | SS approved via email 3/26/04 | 2004-03-26
27 | Schedule for Completion of Engineering Drawings | Steve Scott | SLAC | Hascall | 2003-12-01 | LAT CDR RFA 27 Response.doc | 2004-02-05 | PM Approved 4/4/04 | 2004-04-08 | SS approved via email 4/8/04 | 2004-04-08
28 | Process for Performing Worse Case Circuit Analysis | Steve Scott | SLAC | Haller | 2003-10-31 | LAT CDR RFA 28 Response.doc | 9/16/2004 6/1/05 | PM Approved 7/21/05 | 2005-07-22 | SS approved via email 7/25/05 | 2005-07-25
29 | GLAST LAT Fault Management | Steve Scott/Joe Bolek | SLAC | Bielawski | 2003-10-15 | LAT CDR RFA 29 Response RevB.doc | 10/9/2003 7/26/2004 | PM Approved 8/16/04 Rev B updated for overvoltage | 8/18/2004 8/31/2004 | SS approved via email 8/19/04 | 2004-09-14
JB approved via email 9/14/04
30 | Beam Test Plan | Steve Scott/Don Kniffen | SLAC | Bloom | 2003-10-15 | LAT CDR RFA 30 Response RevA.doc | 2003-08-29 | PM Approved 5/19/04 Rev A written to address DK comment | 5/19/2004 6/23/2004 | SS approved via email 5/20/04
[10 empty] | DK approved via email 6/29/04 | 2004-06-29
31 | Impact of the Conductive Carbon Particles | Steve Scott/Chris Lorentson | SLAC | Marsh | 2003-10-15 | LAT CDR RFA 31 Response.doc | 2003-10-09 | PM Approved 1/7/04 | 2004-01-15 | SS approved via email 3/4/04 | 2004-03-04
32 | Testing of Calorimeter Engineering Module with Latest ASIC's | Phil Sabelhaus | SLAC | N. Johnson / Haller | 2003-10-31 | LAT CDR RFA 32 Response RevA.doc | 11/18/2003 4/19/2004 | PM Approved 5/19/04 | 2004-05-19 | PS approved via email 5/30/04 | 2004-05-30
33 | Possible Temperature Rise Due to Rise in Detector Event Rate | Jim Rose | SLAC | Horn | 2003-10-15 | LAT CDR RFA 33 Response RevA.doc | 2003-08-29 | PM Approved 2/19/04 Rev A written to address JR comments | 2004-02-20 | JR approved Rev A via email 3/9/04 | 2004-03-09
34 | Install Calorimeter Test Module with Flight ICs Before I&T | Helmuth Spieler | SLAC | N. Johnson | 2003-10-31 | LAT CDR RFA 34 Response.doc | 2003-11-18 | PM Approved 6/26/04 | 6/30/04 (Sent to Mark Goans) | Fred Huegel approved via email 1/19/05 | 2005-01-19
35 | Accelerated Performance Life Testing of PIN Diode Elastomer | Ron Ray | SLAC | N. Johnson | 2003-10-31 | LAT CDR RFA 35 Response.doc | 2004-02-18 | PM Approved 3/17/04 | 3/22/2004 (Sent to Mark Goans) | MG approved via email 4/7/05 | 2005-04-07
36 | Addition of Test Engineers to Software Team | Ron Zellar | SLAC | Haller | 2003-12-01 | LAT CDR RFA 36 Response.doc | 2004-02-12 | PM Approved 5/19/04 | 2004-05-19 | RZ approved by email 5/21/04 | 2004-05-21
37 | Investigate XLAT/Electronics Interface Design Option | Tom McCarthy | SLAC | TBD | 2003-10-15 | LAT CDR RFA 37 Response.doc | 2003-10-09 | PM Approved 3/2/2004 | 2004-03-02 | TM approved via verbal response 3/15/04 Email approval 4/6/04 | 2004-03-15
[10 empty] | Total RFAs | 37
[10 empty] | # Closed | 37
S1 | Improving Radiator Efficiency | Tom McCarthy | SLAC | Nordby | N/A | LAT CDR Sugg 1 Response.doc |  | PM Approved 5/19/04 | 2004-05-19

## MPDR
RFA # | Title | Originator | Assignee | Due Date | Response | Date Submitted to Systems | Project Office Review Status | Date Submitted to Code 300 | Closure Status | Closure Date
1 | Open Issues in IRDs and ICDs | Steve Scott | Art Whipple | 2003-11-28 | MPDR RFA 1 Response.doc | 2004-07-13 | PM Approved 8/2/04 | 2004-08-06 | SS approved via email 9/8/04 | 2004-09-08
2 | Open Trade Studies | Steve Scott | Norm Rioux | 2003-09-30 | MPDR RFA 2 Response.doc | 2003-10-02 | PM Approved 4/15/2004 | 2004-04-16 | SS approved via emai 5/3/04 | 2004-05-03
3 | Re-evaluate Options to Resolve Orbital Debris Issue | Marty Davis | Jack Leibee | 2003-09-30 | MPDR RFA 3 Response.doc | 2003-09-30 | PM approved 12/8/03 | 2003-12-11 | MD Approved via voice mail 12/14/03 | 2003-12-14
4 | GBM Schedule Detail | Marty Davis | Bill Browne | 2003-09-01 | MPDR RFA 4 Response.doc | 2003-08-26 | PM Approved 3/30/04 | 2004-03-30 | MD approved via voice mail 4/14/04 | 2004-04-14
GBM MPE Delivery Schedule 2-17-04.pdf
5 | RAD750 Upset/Reset Effects on Design | Steve Scott Jim Rose | Joe Sonsino | 2003-11-28 | MPDR RFA 5 Response.doc | 9/15/2004 12/20/2004 |  | 2005-01-03 | JR approved via email 1/3/05 | 2005-01-21
[7 empty] | PM Approved 1/3/05 |  | SS approved via email 1/21/04
6 | GBM FSW Test Plan | Ron Zellar | Erik Andrews | 2003-11-28 | MPDR RFA 6 Response.doc | 2003-11-17 | PM Approved 2/19/04 | 2004-02-20 | RZ approved by email 2/27/04 | 2004-02-27
7 | Modify the Sequence of GBM Environmental Tests | Joseph Bolek | Bill Browne | 2003-07-31 | MPDR RFA 7 Response.doc | 2003-07-10 | PM approved 12/8/03 | 2003-12-11 | JB approved by email 3/5/04 | 2004-03-05
8 | Re-evaluate Performing GNC End-to-End Testing | Joseph Bolek | Connor/Stoneking | 2003-07-31 | MPDR RFA 8 response.doc | 2003-07-21 | PM approved 12/8/03 | 2003-12-11 | JB approved by email 3/5/04 | 2004-03-05
9 | Actions for NASA IV&V Representative | Steve Scott | Erik Andrews | 2003-11-28 | MPDR RFA 9 response.doc | 2004-03-24 | PM Approved 5/19/04 | 2004-05-19 | SS approved via email 9/8/04 | 2004-09-08
10 | SLAC Procedures for H/W Protection Against Seismic Activity | Steve Battel | Bernie Graf | 2003-11-28 | MPDR RFA 10 response.doc | 8/15/2003 3/24/2004 | PM Approved 5/19/04 | 2004-05-19 | SB approved via email 5/21/04 | 2004-05-21
11 | Mission Level Temperature Summary | Tom McCarthy | Rioux/McCarthy | 2003-08-15 | GLAST TCS Metrics.xls | 2003-08-15 | PM approved 12/8/03 | 2003-12-11 | TM Approved via email 12/18/03 | 2003-12-18
MPDR RFA 11 response.doc
12 | Consistency of the Thermal Requirements in the MAR Documents | Tom McCarthy | Kolecki/McCarthy | 2003-11-28 | MPDR RFA 12 response.doc | 2003-11-18 | PM Approved 1/7/04 | 2004-01-15 | TM Approved via email 1/22/04 | 2004-01-22
13 | Appoint Single Individual Responsible For Achieving Launch Readiness | Ann Merwarth | Mike Rackley | 2003-11-28 | MPDR RFA 13 response.doc | 2004-03-04 | PM Approved 6/26/04 | 2004-06-30 | AM approved via email 6/30/04 | 2004-06-30
14 | Identification of LAT Processing Choke Points | Joe Wonsever | Bernie Graf | 2003-11-28 | MPDR RFA 14 response.doc | 2004-09-09 | PM Approved 9/12/04 | 2004-09-13 | JW approved via email 1/5/05 | 2005-01-05
[9 empty] | Total RFAs | 14
[9 empty] | # Closed | 14
S1 | System Engineering Tracking of Temperature Margin and Exceedances | Tom McCarthy | Connor/McCarthy | N/A | GLAST TCS Metrics.xls
S2 | Incorporating Photo Inspections | Steve Battel | Jack Leibee | N/A | MPDR Sugg 2 response.doc
S3 | Create a GLAST Observatory Temperature Directory | Tom McCarthy | Connor/McCarthy | N/A | The suggestion for a Temperature Directory has been taken under advisement with the goal of having it published prior to the Mission CDR

## GS SRR
RFA # | Subject | Originator | Assignee | Due Date | Response | Date Submitted to Systems | Project Office Review Status | Date Submitted to Code 300 | Closure Status | Closure Date
1 | Reword requirement as a "Near-term Prediction of Resource Availability" | Al Levine | Ross Cox | 2003-09-03 | GSRR RFA 1 Response.doc | 2003-10-03 | PM Approved 1/7/04 | 2004-02-20 | BM approved via email 3/11/04 | 2004-03-11
2 | Provide the status of international, interagency and interproject level agreements, include ITAR implications | Glenn Iona | Mike Rackley | 2003-09-03 | GSRR RFA 2 Response RevB.doc | 2004-03-04 | Sent to PM 3/24/04 Ken sent update to Al and Glenn | 2004-08-02 | GI approved via email 8/2/04 | 2004-08-02
3 | Describe the "Peer Review Process" or "GSSC Software Development" methodolgoy | Robert Schweiss | David Band | 2003-09-03 | GSRR RFA 3 Response RevA.doc | 10/3/2003 3/4/2004 | PM Approved 3/30/04 | 2004-03-30 | BM approved via email 6/10/04 | 2004-06-10
4 | Requirements should contain functional and in some case performance data and should be written in a testable form | Madeline Butler / Steve Scott | Mike Rackley | 2003-09-03 | GSRR RFA 4 Response.doc | 2004-03-04 | PM Approved 4/15/2004 | 2004-04-16 | BM approved via email 6/10/04 | 2004-06-10
5 | The GLAST team needs to ensure that RF compatability is completely defined including the verification of key RF h/w such as the bit synchs to be located at each GS | Bob Menrad | Ross Cox | 2003-09-03 | GSRR RFA 5 Response.doc | 2003-12-18 | PM Approved 3/2/2004 | 2004-02-20 | BM approved via email 3/18/04 | 2004-03-18
6 | Define the required set of triggers which determine when a risk is automatically raised to the project manager's level | Bob Menrad | Mike Rackley | 2003-09-03 | GSRR RFA 6 Response.doc | 2004-03-10 | PM Approved 4/15/2004 | 2004-04-16 | BM approved via email 6/10/04 | 2004-06-10
7 | Evaluate need for orbit determination capabilities on list of launch critical functions | Elizabeth Corderman / Dave Tracewell | Mark Woodward | 2003-09-03 | GSRR RFA 7 Response.doc | 2003-12-18 | PM Approved 3/2/2004 | 2004-03-02 | BM approved via email 3/11/04 | 2004-03-11
8 | More details are required for some of the flight dynamics requirements. Specifically, accuracy and latency requirements for orbital products should be documented | Elizabeth Corderman | Mike Rackley | 2003-09-03 | GSRR RFA 8 Response.doc | 2003-12-18 | PM Approved 2/19/04 | 2004-03-02 | BM approved via email 3/11/04 | 2004-03-11
9 | Define general attitude sensor calibration approach / requirements / tools necessary to meet the 10 arcsec pointing knowledge requirement | Dave Tracewell | Mark Davis | 2003-09-03 | GSRR RFA 9 Response RevA.doc | 10/3/2003 8/4/2004 | PM Approved 9/19/04 | 2004-09-20 | BM approved via email 9/27/04 | 2004-09-27
10 | Determine the real need/role of FDF for Phase E of the GLAST mission | Elizabeth Corderman / Dave Tracewell / Ron Mahmot | Mark Woodward | 2003-09-03 | GSRR RFA 10 Response.doc | 2003-10-03 | PM Approved 1/7/04 | 2004-02-20 | BM approved via email 3/11/04 | 2004-03-11
11 | Determine if there are any proprietary issues specifically with Spectrum Astro and their subcontractors regarding sustaining engineering of the S/C bus and GSFC/AETD involvement | Ron Mahmot | Joy Bretthauer / Jerry Edmonds | 2003-09-03 | GSRR RFA 11 Response.doc | 2003-10-03 | PM Approved 4/15/2004 | 2004-04-16 | RM approved via email 4/19/04 | 2004-04-19
12 | Determine if there is enough of a security threat to add a command encryption requirement and if the requirement is feasible to implement | Ron Mahmot | Mark Melton | SDR | GSRR RFA 12 Response.doc | 2004-02-24 | PM Approved 4/15/2004 | 2004-04-16 | RM approved via email 4/19/04 | 2004-04-19
13 | Determine if there should be a requirement to maintain a star catalog | Ron Mahmot | Mark Davis | 2003-09-03 | GSRR RFA 13 Response RevA.doc | 2003-10-03 | PM Approved 1/7/04 | 2004-02-20 | BM approved via email 6/10/04 | 2004-06-10
14 | Determine GSFC requirement for a common database for Ground System and S/C anomalies | Ron Mahmot | John Nagy | 2003-09-03 | GSRR RFA 14 Response RevA.doc | 10/3/2003 9/29/2004 | PM Approved 1/7/04 | 2004-02-20 | RM approved by email 9/30/04 | 2004-09-30
15 | Consider archiving Packets in the MOC rather than Frames | Ron Mahmot | John Nagy | 2003-09-03 | GSRR RFA 15 Response.doc | 2003-10-03 | PM Approved 1/7/04 | 2004-02-20 | BM approved via email 3/11/04 | 2004-03-11
16 | Consider automated method(s) to process ToO requests for off shift periods | Ron Mahmot | Doug Spiegel | 2003-09-03 | GSRR RFA 16 Response.doc | 2003-10-03 | PM Approved 1/7/04 | 2004-02-20 | BM approved via email 3/11/04 | 2004-03-11
17 | The schedule for use of the "Hot Bench" should be examined in detail | Mark Goans | Mike Rackley | 2003-09-03 | GSRR RFA 17 Response RevA.doc | 2004-03-10 | PM Approved 8/2/04 | 2004-08-06 | MG approved via email 9/27/04 | 2004-09-27
[9 empty] | Total RFAs | 17
[9 empty] | # Closed | 17

## GBM DPU CDR
RFA # | Subject | Originator | Assignee | Due Date | Response | Closure Status | Closure Date
1 | Fault Management | Jack Leibee | Michael Briggs | 2003-10-20 | GDPUC-001 Response.doc | See hard copy | 2004-01-28
2 | DPU Backplane Single Point Failure | Fred Huegel | Fred Berry | 2003-09-22 | GDPUC-002 Response.doc | See hard copy | 2004-03-23
3 | Resolve several open FSW/ground technical issues | Mike Rackley | Michael Briggs | 2003-10-09 | GDPUC-003 Response.doc | See hard copy | 2004-01-28
4 | FSW Build Management | Neil Gehrels | Michael Briggs | 2003-09-12 | GDPUC-004 Response.doc | See hard copy | 2003-12-04
5 | Science Data Format & Contents | Bill Paciesas | Steve Persyn | 2003-09-16 | GDPUC-005 Response.doc | Combined with #7 | 2004-04-13
6 | GBM/Spacecraft ICD Compliance | Jack Leibee | Mark James | 2003-11-03 | GDPUC-006 Response.doc | See hard copy | 2004-06-18
7 | Data Packet Timing | Robert Preece | Steve Persyn | 2003-09-16 | GDPUC-007 Response.doc | Combined with #5 | 2004-04-13
[6 empty] | Total RFAs | 7
[6 empty] | # Closed | 7
C1 | Alerts (General Comment) | Matt Bolling |  | N/A

## LAT Post CDR Peer Reviews
CAL-GRID Peer Review
RFA # | Request | Reason | Originator | Assignee | Response | Date Submitted to GPO | Project Office Review Status | Date Submitted to Originator | Closure Status | Closure Date
1 | Coupled loads model, as delivered to Swales, should match LAT mass properties with contingency included. Mass properties should match at LAT subsystem (ACD, CAL, GRID, etc.) level. | Current, single scale factor, approach does not adequately represent actual mass distribution | T. Venator | Nordby | CAL-Grid RFA 1 Response.doc | 2003-12-08 | Mech Approved 12/11/03 | 2003-12-11 | Approved | 2003-12-16
2 | Include short beam effect for stress analysis for key | Short beam effect can increase both shear & bending stress compared with long beam solution. Please refer to Roark & Young for guide. | C. Lee | Nordby | CAL-Grid RFA 2 Response.doc | 2003-12-08 | Mech Approved 12/11/03 | 2003-12-11 | Approved | 2003-12-11
3 | Include lateral load factor with vertical 1 G for crane lifting | Suggest use 0.25 G's lateral within 1 G vertical for crane lifting case | C. Lee | Nordby | CAL-Grid RFA 3 Response.doc | 2003-12-08 | Mech Approved 12/11/03 | 2003-12-11 | Approved | 2003-12-11
4 | Grid margins of safety should include stability (buckling and crippling) allowables as well as strength allowables. | Stability allowables can be lower than strength allowables. Stability allowables should be developed for compression and shear loading. | L. Mignosa | Nordby | CAL-Grid RFA 4 Response.doc | 2003-12-08 | Mech Approved 12/11/03 | 2003-12-11 | Approved | 2003-12-12
5 | Consider using standard bolt preload of 65% of yield for all interfaces | Consistent torque for each size bolt reduces chance of error at assembly. Bolt analysis should be done based on the guidelines given in NASA-STD-5001. An example will be sent to SLAC. | L. Mignosa | Nordby | CAL-Grid RFA 5 Response.doc | 2003-12-08 | Mech Approved 12/11/03 | 2003-12-11 | Approved | 2003-12-12
6 | Suggest examining design change to spacecraft mount interface to achieve 1.5 edge distance on critical fasteners in critical loading direction | Shouldn't deviate from standard design practice particularly at this critical interface. | J. Ryan | Nordby | CAL-Grid RFA 6 Response.doc | 2003-12-08 | Mech Approved 12/11/03 | 2003-12-11 | Approved | 2003-12-16
ICN-036 LAT-SC Mechanical Interfaces.pdf
7 | Consider adding steel bushings to radiator bracket clevis | Will prevent localized deformation of clevis F.D. | J. Ryan | Nordby | CAL-Grid RFA 7 Response.doc | 2003-12-08 | Mech Approved 12/11/03 | 2003-12-11 | Approved | 2003-12-16
X-LAT Peer Review
RFA # | Request | Reason | Originator | Assignee | Response | Date Submitted to GPO | Project Office Review Status | Date Submitted to Originator | Closure Status | Closure Date
1 | 1) Document X-LAT Updated TMM per CDRL102 rqmts in a report (to GSFC) 2) Run X-LAT TMM as a stand alone model thru a series of check out cases and provide results as a part of model documentation report to GSFC. | Previous (CDR) X-LAT TMM was not adequately checked out print integration into V5.00 TMM. No submodel c/o process was implemented (in all cases) in the synthesis of V5.0 TMM. | Tom McCarthy | Campell | X-LAT RFA 1 Response.doc | 6/14/2004 8/17/2004 | OK | 2004-08-18 | TM approved by email 8/18/04 | 2004-08-18
2 | Perform and document a audit of V5.0 TMM at the submodel level. Recommend running each submodel as a stand alone thru a series of developed c/o cases. There cases should reflect a process/method to rationalize key conduction networks and interfaces | V5.0 TMM has been synthesized from a number of submodel, These submodels (in all cases) have not gone thru a rigorous check out prior to this integration, (evidenced by X-LAT model from CDR). | Tom McCarthy | Campell | X-LAT RFA 2 Response RevA.doc | 6/14/2004 8/17/2004 9/10/2004 | OK | 2004-08-18 | TM comment sent to SLAC 8/18/04 Update sent to TM 9/10/2004 | 2004-09-10
3 | Recommend developing a torque sequence for bolting X-LAT plate to electronics boxes to minimize interface stresses. Torque fasteners in several steps? Torque from center of X-LAT plate out? Or from alignment pins out? | Significant interface stresses could result from non-optimum torquing of fasteners. | Jim Ryan | Nordby/ Campell | X-LAT RFA 3 Response RevA.doc | 2004-08-18 | Rev A updated per CF comment CF OK 8/26/04 | 2004-08-26 | JR approved by email 8/31/04 | 2004-08-31
4 | Conduct proof pressure tests of heat pipes @ 1.5 x MEOP. | It was unclear if 1.5 x MEOP requirement was in current documentation. There was mention of a 1.2 x MEOP test. | Jim Ryan | Nordby/ Campell | X-LAT RFA 4 Response.doc | 6/14/2004 8/17/2004 | OK | 2004-08-18 | JR approved by email 8/20/04 | 2004-08-20
5 | 1) Provide some level of detail of the bonding (Nusil) of the heat pipes to the X-LAT plate. How achieve 10 mil thickniess of Nusil? Rivet w/Nusil cured or wet? How verify appropriate pressure on Nusil to achieve necessart thermal conductance? 2) Consider enforced displacements of X-LAT plate during T/V testing to simulate non-planarity of E-Box interface. | 1) Discussions at the review did not clear up this level of detail. 2) Concern that distorted X-LAT plate might affect thermal conductance of joint. | Jim Ryan | Goodman/ Nordby | X-LAT RFA 5 Response RevA.doc | 8/27/2004 1/13/2005 2/24/05 | CF OK 1/19 TM OK 2/28 | 2005-02-28 | JR approved by email 3/18/05 | 2005-03-18
6 | Critical inspection dimensions should be noted on each piece part drawing from which X-LAT tolerance study data was taken. | Knowledge that tolerances are within spec. is key to successful integration of X-LAT assembly. | Sharon Seipel | Nordby | X-LAT RFA 6 Response.doc | 2004-08-25 | Sent to CF and PB 8/26/04 | 2004-08-26 | PB approved via email 8/26/04 | 2004-08-26
7 | Finalize U-Shape heat pipe design and determine if stress-relieved pocketing is required (0.100" regions). | Final stress margins for U-shape pipe may require design change to X-LAT plate. | Sharon Seipel | Campell | X-LAT RFA 7 Response.doc | 6/14/2004 8/17/2004 | OK | 2004-08-18 | PB approved via email 8/18/04 | 2004-08-18
8 | Consider performing a qualification strength test for the X-LAT plate or increase the safety factor for observatory left to 2.6 on ultimate. The bolts at the lift point locations could be increased in size to meet the required no test factors of safety. Also verify that all other elements of the X-LAT plate meet no test factors of safety. | The load path for a highly redundant structure should be verified by test or the model load path should be verified by model survey yesy along with no test safety factors of 2.0 on yield and 2.6 on ultimate. | Larry Mignosa | Ku | X-LAT RFA 8 Response.doc | 6/14/2004 8/17/2004 | OK | 2004-08-18 | LM approved via email 8/19/04 | 2004-08-19
Power Supply Peer Review
RFA # | Request | Reason | Originator | Assignee | Response | Date Submitted to GPO | Project Office Review Status | Date Submitted to Originator | Closure Status | Closure Date
1 | Complete part stress and derating analysis | Required per MAR & PAIP | Tony DiVenti | Haller | LAT-TD-0416-01_TPS_Part_Stress_02.doc | 2004-08-18 | Report in Project review. Comments to be submitted to SLAC and worked outside of RFA | 2004-08-20 | TD approved verbally 8/20/04 | 2004-08-20
2 | Need to get SEU report on Maxim parts out as soon as possible. Issue is not only LET but SET effects since transients can affect the power supply outputs. |  | Steve Battel | Fetter | TEM PS RFA 2 Response.doc | 2004-09-09 | OK | 2004-09-14 | SB approved via email 9/14/04 | 2004-09-14
SEL Report MAX724 2803R3.doc
3 | Need to get AR-461 filter schematic plus schematic of 28-28 supply on spacecraft. Need to develop model of power and ground distribution to verify filter performance relative to 100 kHz noise. Damping of the entire filter network should also be verified to assure that an interactive among the many identical filters cannot occur. |  | Steve Battel | Haller | TEM PS RFA 3 Response RevA.doc | 2004-09-10 | OK | 2004-09-14 | SB approved via email 9/14/04 | 2004-09-14
4 | T0-220 Maxim regulators have their mounting tabs connected to ground. This has the potential of creating an undesirable ground path with associated noise problems. The optimum grounding solution for this particular configuration is to connect all elements to chassis and use the structure as the primary ground return (as diagrammed on the conference room whiteboard). It is strongly recommended that this approach be taken to assure proper instrument performance despite the fact that the approach is slightly unorthodox. As a second issue, it is also suggested that gold foil or indium foil be used to assure reproducible heat sink contact for the regulators. The grease or no intermediate material approaches are strongly recommended against. |  | Steve Battel | Haller | TEM PS RFA 4 Response.doc | 2004-09-10 | OK | 2004-09-14 | SB approved via email 9/14/04 | 2004-09-14
5 | Maxim part screening must be carefully done to assure that the testing provides valid verification reliability. Documented methods by Maxim are for static burn-in only (diffusion based issues) and do not represent the actual operational case planned for GLAST. In that the GLAST application is actually fairly stressful AND uses the part outside of its normal operational range (for the 1.5 volt output case), it is suggested that the screening and qual test be configured to verify the 1.5 volt configuration since it is most stressful. Note that great care must be taken with the layout and instrumentation to assure that the setup does not accidentally result in part damage. |  | Steve Battel | Clough | TEM PS RFA 5 Response.doc | 2004-10-13 | OK BG reviewed and OK'd | 2004-10-14 | SB approved via email 10/16/04 fwd from SC | 2004-10-16
Q30355_EVAL__MAX724_Microcircuit.pdf
6 | The 28 volt converter planned for use by Spectrum Astro, uses a step-up transformer. A quick calculation indicates that the step-up ratio is probably 1.5 or more. therefore, a failure where the control loop goes open while the bus is at 33 volts, could put as much as 50 volts on the input to the power supply regulators. Such a condition could have catastrophic consequences to the instrument such that system level redundancy could be compromised due to progagation of the failure across interfaces. Therefore, it is strongly recommended that overvoltage protection be implemented to assure protection of the hardware plus protection against failure propagation. |  | Steve Battel | Gaddy | TEM PS RFA 6 Response.doc | 2004-09-09 | OK | 2004-09-14 | SB approved via email 9/14/04 | 2004-09-14
X-LAT Manufacturing Readiness Review
RFA # | Request | Reason | Originator | Assignee | Response | Date Submitted to GPO | Project Office Review Status | Date Submitted to Originator | Closure Status | Closure Date
1 | Clarify SCD note on flatness of X-LAT plate to specify restraining load & locations. |  | Marc Campell |  | Note revised in Rev 3 of drawing, LAT-DS-01247 | 2005-01-31 |  |  | MC approved | 2005-01-31
2 | Spectrum to approve 1/2" radius on X-LAT plate (near Spacecraft flexures). Current LM drawing reflects this. |  | Marc Campell |  | CCR approved with .125" radius which is acceptable |  |  |  | MC approved 6/21/05 | 2005-06-21
3 | Verify that there are positive margins for a 2 point lift case with 3000 kg mass (Observatory). |  | Chris Fransen |  | MRR Structural Analysis Margin Summary 052804.ppt | 2005-01-31 | CF provided attached file provided at the MRR | 2005-02-03 | CF approved via email 2/3/05 | 2005-02-03
Flight Unit Peer Review
RFA # | Request | Reason | Originator | Assignee | Response | Date Submitted to GPO | Project Office Review Status | Date Submitted to Originator | Closure Status | Closure Date
1 | Establish an ICD between FSW and Ground Calibration | The two groups need to agree on what data the FSW calibration produces | Stephen Leake |  | FSW Flight Unit RFA 1 Response.doc
2 | Please clarify how the LAT FSW Requirement Modes and FSW Implementation Modes are addressed through FSW test. This is an area that should lead to an update of requirements so test is complete. | There are LAT requirements modes, which are then transformed into LAT design / implementation modes. This leads to concern about how the test procedures will work through the two sets of modes. | Shirley Savarino |  | FSW Flight Unit RFA 2 Response.doc
3 | Clarify requirement and design for Gamma Ray Burst data capture. Make a clear commitment that attempting to meet this requirement will not be allowed to cause a schedule delay. | Baseline design does not including buffering beyond the .5MB LCB event buffer. It may turn out this is not adequate. | Stephen Leake |  | FSW Flight Unit RFA 3 Response.doc
4 | Provide clear, complete definitions of the three physics acquisition modes. | It is not clear that three modes are needed. | Stephen Leake |  | FSW Flight Unit RFA 4 Response.doc
5 | Define deadlines for resolution of requirements TBXs and clearly communicate the deadlines to the appropriate LAT systems. | LAT FSW needs to finalize its requirements and the other LAT systems need to contribute to this goal. | Ron Zellar |  | FSW Flight Unit RFA 5 Response.doc
6 | Clarify the approach to meeting deadlines for successful full integration of the flight software. Especially how integration problems will be handled. | Keeping to the schedule looks possible, but there are many possibilities for slippage. | Richard Mount |  | FSW Flight Unit RFA 6 Response.doc
2 Tower IRR
RFA # | Request | Originator | Assignee | Response | Date Submitted to GPO | Project Office Review Status | Date Submitted to Originator | Closure Status | Closure Date
1 | Ensure the Problem Resolution process that was discussed is captured in the I&T Plan. | David Harmon
2 | Need to better define the criteria under which an anomaly is declared a FLAG vs. one that gets raised to an NCR. | Ken Wagner
3 | Detail the Software Quality Assurance activities that will occur during I&T | David Harmon
4 | Ensure lifting sling configuration prior to lift. E.g. verify that proper attachments (like turnbuckles/hooks) are those dedicated for, and proof-tested with, sling. | M. Wright (NASA / GSFC) | K. Fouts
5 | To problem resolution approach, add to "Flight HW damage" - "potenial injury to personnel." Also, add safety rep to MRB membership. | M. Wright (NASA / GSFC) | K. Fouts

## GBM Det & PB CDR
RFA # | Subject | Originator | Assignee | Due Date | Response | Closure Status | Closure Date
1 | Qualification of Bonding Method used to Attach Mu-Metal and Preload Brackets to PMT | Robert Wilson | Dieter Wolter | 2004-02-16 | GDPB-001 Response.doc | See hard copy | 2004-06-22
2 | TBDs and TBCs in the Calibration Plan for the GBM | Dr. Wolf-Rainer Graefe | Jerry Fishman | 2004-05-03 | GDPB-002 Response.doc | See hard copy | 2004-06-18
3 | Applicable and Reference Documents in the Product Assurance Plan | Dr. Wolf-Rainer Graefe | Kretschmer Rainer | 2004-05-03 | GDPB-003 Response.doc | Closed per Imp. Section and M. Suchman email 7/7/04 | 2004-06-10
4 | References to processes and test plans in the MIP/KIP Plan | Dr. Wolf-Rainer Graefe | Dieter Wolter | 2004-05-03 | GDPB-004 Response.doc | Per #4 | 2004-06-10
5 | TBCs in the Hamamatsu-PMT Procurement Specification | Dr. Wolf-Rainer Graefe | Gieselher Lichti | 2004-02-09 | GDPB-005 Response.doc | Per #4 | 2004-06-10
6 | Delivery of Software | Dr. Wolf-Rainer Graefe | Andreas von Kienlin | 2004-05-03 | GDPB-006 Response.doc | Per #4 | 2004-06-10
7 | Implementation Responsibility in the MPE Product Assurance Plan | Dr. Wolf-Rainer Graefe | Andreas von Kienlin | 2004-05-03 | GDPB-007 Response.doc | Per #4 | 2004-06-10
8 | References Documents in the Product Assurance Plan | Dr. Wolf-Rainer Graefe | Andreas von Kienlin | 2004-05-03 | GDPB-008 Response.doc | Per #4 | 2004-06-10
9 | Definitions/Glossary of Terms in the Product Assurance Plan | Dr. Wolf-Rainer Graefe | Andreas von Kienlin | 2004-05-03 | GDPB-009 Response.doc | Per #4 | 2004-06-10
10 | DLR Right of Access in the Product Assurance Plan | Dr. Wolf-Rainer Graefe | Andreas von Kienlin | 2004-05-03 | GDPB-010 Response.doc | Per #4 | 2004-06-10
11 | Design Reviews in the Product Assurance Plan | Dr. Wolf-Rainer Graefe | Andreas von Kienlin | 2004-05-03 | GDPB-011 Response.doc | Per #4 | 2004-06-10
12 | Product Assurance Documentation in the Product Assurance Plan | Dr. Wolf-Rainer Graefe | Andreas von Kienlin | 2004-05-03 | GDPB-012 Response.doc | Per #4 | 2004-06-10
13 | Non Conformance Control in the Product Assurance Plan | Dr. Wolf-Rainer Graefe | Andreas von Kienlin | 2004-05-03 | GDPB-013 Response.doc | Per #4 | 2004-06-10
14 | Request for Deviation/Waiver in the Product Assurance Plan | Dr. Wolf-Rainer Graefe | Andreas von Kienlin | 2004-05-03 | GDPB-014 Response.doc | Per #4 | 2004-06-10
15 | Handling & Preservation in the Product Assurance Plan | Dr. Wolf-Rainer Graefe | Andreas von Kienlin | 2004-05-03 | GDPB-015 Response.doc | Per #4 | 2004-06-10
16 | Verification Planning and Control in the Product Assurance Plan | Dr. Wolf-Rainer Graefe | Andreas von Kienlin | 2004-05-03 | GDPB-016 Response.doc | Per #4 | 2004-06-10
17 | Acceptance and Delivery in the Product Assurance Plan | Dr. Wolf-Rainer Graefe | Andreas von Kienlin | 2004-05-03 | GDPB-017 Response.doc | Per #4 | 2004-06-10
18 | Acceptance Data Package in the Product Assurance Plan | Dr. Wolf-Rainer Graefe | Andreas von Kienlin | 2004-05-03 | GDPB-018 Response.doc | Per #4 | 2004-06-10
19 | Packaging in the Product Assurance Plan | Dr. Wolf-Rainer Graefe | Andreas von Kienlin | 2004-05-03 | GDPB-019 Response.doc | Per #4 | 2004-06-10
20 | EEE Parts Procurement in the Product Assurance Plan | Dr. Wolf-Rainer Graefe | Andreas von Kienlin | 2004-05-03 | GDPB-020 Response.doc | Per #4 | 2004-06-10
21 | Material Selection/Control in the Product Assurance Plan | Dr. Wolf-Rainer Graefe | Andreas von Kienlin | 2004-05-03 | GDPB-021 Response.doc | Per #4 | 2004-06-10
22 | Dependability in the Product Assurance Plan | Dr. Wolf-Rainer Graefe | Fred Berry | 2004-01-26 | GDPB-022 Response.doc | See hard copy | 2004-06-22
23 | MIP/KIP Planning in the Product Assurance Plan | Dr. Wolf-Rainer Graefe | Andreas von Kienlin | 2004-05-03 | GDPB-023 Response.doc | Per #4 | 2004-06-10
24 | Contamination Control in the Product Assurance Plan | Dr. Wolf-Rainer Graefe | Andreas von Kienlin | 2004-05-03 | GDPB-024 Response.doc | Per #4 | 2004-06-10
25 | TBDs and TBCs in the GBM-Power Box ICD | Dr. Wolf-Rainer Graefe | Dieter Wolter | 2004-05-03 | GDPB-025 Response.doc | Per #4 | 2004-06-10
26 | TBDs in the Power Box Specification | Dr. Wolf-Rainer Graefe | Dieter Wolter | 2004-05-03 | GDPB-026 Response.doc | Per #4 | 2004-06-10
27 | TBCs in the GBM-PB Design Description | Dr. Wolf-Rainer Graefe | Dieter Wolter | 2004-05-03 | GDPB-027 Response.doc | Per #4 | 2004-06-10
28 | TBCs in the Power Box CRTL | Dr. Wolf-Rainer Graefe | Dieter Wolter | 2004-05-03 | GDPB-028 Response.doc | Per #4 | 2004-06-10
29 | Alignment Mirror on the NaI Detectors | Jerry Fishman | Dieter Wolter | 2004-05-03 | GDPB-029 response.doc | See hard copy | 2004-06-15
30 | Critical Items Control in the Product Assurance Plan | Dr. Wolf-Rainer Graefe | Andreas von Kienlin | 2004-05-03 | GDPB-030 Response.doc | Per #4 | 2004-06-10
31 | TBDs and TBCs in the GBM ICD | Dr. Wolf-Rainer Graefe |  |  | GDPB-031 Response.doc | Per #4 | 2004-06-10
32 | Power Connection and TBDs/TBCs in the PB ICD | Dr. Wolf-Rainer Graefe |  |  | GDPB-032 Response.doc | Per #4 | 2004-06-10
33 | Critical Items Control | Dr. Wolf-Rainer Graefe |  | GBM CDR | GDPB-033 Response.doc | Per #4 | 2004-06-10
34 | Qualification and Acceptance in the Product Assurance Plan | Dr. Wolf-Rainer Graefe |  |  | GDPB-034 Response.doc | Per #4 | 2004-06-10
35 | Sinusoidal Swept Vibration | Bill Browne | Dieter Wolter |  | GDPB-035 Response.doc | See hard copy | 2004-06-22
GBM_Sine_Vib_Qual.doc
36 | Factors of Safety | Bill Browne |  |  | GDPB-036 Response.doc | See hard copy | 2004-06-22
37 | Power Connection and TBDs/TBCs in the PB ICD | Dr. Wolf-Rainer Graefe |  |  | GDPB-037 Response.doc | Withdrawn per M. Suchman email 7/7/04
38 | Lack of Thermal Vacuum Testing for the Power Box | Fred Berry | Gieselher Lichti | 2004-05-03 | GDPB-038 Response.doc | Withdrawn | 2004-06-18
[6 empty] | Total RFAs | 38
[6 empty] | # Closed | 38

## SC FSW CDR
RFA # | Title | Originator | Responsible Org. | Due Date | Response | Date Submitted to GPO | Project Office Review Status | Date Submitted to Code 300 | Closure Status | Closure Date
1 | Describe Recovery from EEPROM Bit Errors & RAM Bad Blocks | Steve Scott Ron Zellar | Spectrum | 2005-04-30 | FSW CDR RFA 1 Response RevA.doc | 4/28/2004 6/15/2005 | PM Approved 6/16/05 | 2005-06-16 | SS approved via email 6/20/05 | 2005-07-07
RZ approved via email 7/7/05
2 | EEPROM Corruption | Steve Scott | Spectrum | SC CDR | FSW CDR RFA 2 Response.doc |  | Closed at Review |  |  | Closed at Review
3 | Ensure "Artifacts" Required by IV&V are Delivered Before MRR | Steve Scott | GPO | SC CDR | FSW CDR RFA 3 Response.doc | 2004-05-06 | PM Approved 6/3/04 | 2004-06-03 | SS approved via email 6/9/04 | 2004-06-09
4 | Size Software DB and Arrays to Allow Monitoring of all Analogs | Steve Scott Erik Andrews | Spectrum | SC CDR | FSW CDR RFA 4 Response.doc | 2004-04-28 | PM Approved 6/3/04 | 2004-06-03 | SS approved via email 6/9/04 | 2004-06-09
5 | Specify Conditions the Thrusters be Enabled under Various Modes | Steve Scott Scott Schield | Spectrum | MCDR | FSW CDR RFA 05 Response.doc | 4/28/2004 7/15/2004 | PM Approved 8/2/04 | 2004-08-06 | S. Schield approved via email 8/11/04 S. Scott approved via email 9/8/04 | 2004-09-08
6 | Specify Attitude Control Policy for Selecting RW and/or Thrusters | Steve Scott Scott Schield | Spectrum | MCDR | FSW CDR RFA 6 Response.doc | 2004-04-28 | PM Approved 6/3/04 | 2004-06-03 | S. Schield approved via email 6/7/04 | 2004-06-09
S. Scott approved via email 6/9/04
7 | Detail the Software QA Evaluation of the GN&C FSW | Steve Scott Al Vernacchio | Spectrum | SC CDR | FSW CDR RFA 07 Response.doc | 4/28/2004 6/14/2004 | PM Approved 6/26/04 | 2004-06-30 | AV approved via email 8/2/04 SS approved via email 9/8/04 | 2004-09-08
8 | Perform EDAC Check to Check for Bits Stuck on Low | Fred Huegel | Spectrum | SC CDR | FSW CDR RFA 08 Response.doc | 4/28/2004 6/14/2004 | PM Approved 8/2/04 | 2004-08-06 | FH approved via email 8/13/04 | 2004-08-13
9 | Conduct Test Reviews Before and After FSW Testing | Ron Zellar | Spectrum | SC CDR | FSW CDR RFA 9 Response.doc | 2004-04-28 | PM Approved 6/3/04 | 2004-06-03 | RZ approved via email 6/8/04 | 2004-06-08
10 | Add Logic to Idle Mode Enable Command | Ron Zellar Lisa Shears | Spectrum | SC CDR | FSW CDR RFA 10 Response.doc | 2004-04-28 | PM Approved 6/3/04 | 2004-06-03 | RZ approved via email 6/7/04 | 2004-06-07
LS approved via email 6/7/04
11 | Provide Outcome of Project Assessment of the Mission CSCI | Lisa Shears | Spectrum | 2005-04-30 | FSW CDR RFA 11 Response RevA.doc | 5/17/2004 6/13/2004 | PM Approved 6/3/04 Sent to PM 6/14/05 PM Approved 6/16/05 | 6/3/2004 6/16/2005 | LS approved via email 6/24/05 | 2005-06-24
[9 empty] | Total RFAs | 11
[9 empty] | # Closed | 11
R1 | Collect Test Phase Diagnostic Data into Diagnostic T/M Packets | Steve Scott Erik Andrews | Spectrum |  | FSW CDR Recommendation 1 Response.doc | 2004-06-02 | PM Approved 6/26/04 | 2004-06-30
R2 | Expand on FSW (GN&C/C&DH) at the Upcoming S/C CDR | Erik Andrews | Spectrum |  | FSW CDR Recommendation 2 Response RevA.doc | 2004-04-28 | PM Approved 6/26/04 | 2004-06-30

## SC CDR
RFA | Title | Originator | Responsible Org. | Assignee | Due Date | Response | Date Submitted to GPO | Project Office Review Status | Date Submitted to Code 300 | Date Approved by Originator | Closure Date
1 | Acceptability of Ku Transmitting while in High Rate Slew | Fred Huegel | SAI | Robb Pinkerton |  | SC CDR RFA 1 Response.doc | 2004-08-05 | Closed @ CDR | Analysis sent on 8/12/04 | CLOSED @ CDR | 2004-05-27
2 | Use of Breakout Box to Verify the Signal Integrity on Connections | Fred Huegel | GPO | Joy Henegar | 2004-08-20 | SC CDR RFA 2 Response.doc | 2004-09-10 | PM Approved 9/12/04 | 2004-09-13 | FH approved via email 9/14/04 | 2004-09-14
3 | Perform EMI Testing with Solar Arrays Installed | Fred Huegel Pete Salerno | GPO | Fred Blanchette | PER
4 | Review of APA and SADA Qualifcation Data by Mechanism Expert | Dennis Dillman | SAI | Igor Lazbin (Scott Dow, Esteen Bottlinger) | 2005-06-30 | SC CDR RFA 4 Response RevA.doc | 7/14/2004 5/6/2005 | PM Approved 5/17/05 | 2005-05-17 | DD approved via email 5/18/05 | 2005-05-18
5 | Expedite Evaluation and Planning for Life Testing APM and SADA | Dennis Dillman | SAI | Igor Lazbin | 2005-06-30 | SC CDR RFA 5 Response RevA.doc | 6/23/2004 5/6/2005 | PM Approved 5/17/05 | 2005-05-17 | DD approved via email 5/18/05 | 2005-05-18
sada apa eval 050114.ppt
APA SOW RevA 050308_COTR.doc
6 | Consider Launching with Additional Equipment on at Launch | Phil Sabelhaus Sam Placanica Ron Zellar | SAI | Jim Howe | MCDR | SC CDR RFA 6 Response RevA.doc | 2004-08-19 | PM Approved (verbal) 9/15/04 | 2004-09-15 | PS approved via email 9/16/04 SP approved via email 9/16/04 RZ approved via email 9/18/04 | 2004-09-18
7 | Provide Summary of Qualification Status and Plans for all Mechanisms | Phil Sabelhaus Minh Phan Scott Glubke | SAI | Igor Lazbin Scott Dow | 2005-04-30 | SC CDR RFA 7 Response RevC.doc | 2004-08-05 | PM Approved 5/17/05 PM Approved update 7/20/05 | 5/17/2005 7/20/2005 | MP approved via email 8/23/05 | 2005-08-23
sada apa eval 050114.ppt
APA SOW RevA 050308_COTR.doc
8 | Provide Strength Qualification Plan for the Solar Array | Minh Phan | SAI | Scott Dow | PER
9 | Subject the Solar Array Wing to 3-Axis Sine Vibration Test | Minh Phan | SAI | Scott Dow | PER
10 | Provide Plan for the Assessment of the Delta II MECO Event | Minh Phan | GPO | Paul Baird | MCDR | SC CDR RFA 10 Response RevA.doc | 8/31/2004 2/3/2005 | PM Approved 3/2/05 | 2005-03-02 | MP approved via email 3/8/05 | 2005-03-08
SAI-TM-2468_GLAST_HF_MECO_Assessments.pdf
SAI-TM-2625_Delta II HF MECO GLAST Assessment Plan.pdf
11 | Verification of Minimum Frequency Goal of Deployed SA | Minh Phan | SAI | Scott Dow | PER
12 | Reset/Reboot Causing Loss of the Results of Amp-Hour Integrator | Steve Scott | SAI |  |  |  | SC CDR | Closed @ CDR |  | CLOSED @ CDR | 2004-05-27
13 | Describe Testing Approach for Fault Management System | Steve Scott | SAI | Ron Zitek | 2006-01-31 | SC CDR RFA 13 Response RevA.doc | 2004-08-05 | PM Review AV comment for more detail 8/16/04 AV comments rcvd 1/26/05 Sent to SASS 2/24/05
14 | Provide a Comprehensive GNC Verification Matrix | Steve Scott Mike Beims | SAI | Igor Lazbin | 2005-05-31 | SC CDR RFA 14 Response RevD.doc | 8/9/2004 3/22/2005 5/21/2005 | PM Approved 6/8/05 | 2005-06-08 | SS approved via email 6/9/05 | 2005-06-17
MB approved via email 6/17/05
15 | Perform Thruster Pulse Test Prior to L&EO 30 sec. Validation Burn | Sam Placanica | SAI | Ken Lewis | MCDR | SC CDR RFA 15 Response.doc | 2004-07-14 | PM Approved 8/2/04 | 2004-08-06 | SP approved via email 8/11/04 | 2004-08-11
16 | Upload TDRS Ephemeris Updates Following TDRS Orbit Maintenance | Sam Placanica | GPO | Ken Lehtonen | MCDR | SC CDR RFA 16 Response.doc | 2004-07-23 | PM Approved 8/16/04 | 2004-08-17 | SP approved via email 8/17/04 | 2004-08-17
17 | Provide Additional Power to Close GBM Thermal Control Requirements | Bill Fischer | GPO | Art Whipple | GBM CDR | SC CDR RFA 17 Response.doc | 2004-08-30 | PM Approved 9/12/04 | 2004-09-13 | DG approved for BF via email 12/13/04 | 2004-12-13
18 | Increase the Number of Line PRTs on the Propulsion Lines | Bill Fischer | SAI | Scott Capehart | MCDR | SC CDR RFA 18 Response.doc | 2004-07-14 | PM Approved 8/2/04 | 2004-08-06 | DG approved for BF via email 12/13/04 | 2004-12-13
19 | Increase Number of Thermal Balance Phases | Bill Fischer | SAI |  |  |  | SC CDR | Closed @ CDR |  | CLOSED @ CDR | 2004-05-27
20 | Add Element to End of I&T Allocating Time to Update SW Tables | Ron Zellar | SAI | Ron Zitek | PER | SC CDR RFA 20 Response RevA.doc | 2005-01-04 | PM Approved 2/2/05 | 2005-02-03 | RZ approved via email 2/3/05 | 2005-02-03
21 | Provide Information on Definition of Operations Verification and Validation Process | Ann Merwarth | GPO | Ken Lehtonen | Plan by MCDR | SC CDR RFA 21 Response RevC.doc | 2004-09-02 | PM Approved 9/12/04 RevC based on AM comments | 9/13/2004 9/16/2004 | AW approved via email 9/17/04 | 2004-09-17
22 | Slip Ring Geometry | Jim Rose | SAI | Igor Lazbin | 2004-07-16 | SC CDR RFA 22 Response RevA.doc | 2004-09-08 | PM Approved 9/12/04 Rev A sent on 11/23/04 | 2004-09-13 | JR approved via email 12/14/04 | 2004-12-14
23 | Effect of Variable Spacecraft Attitude on Drag Model | Jim Rose | SAI | Igor Lazbin | MCDR | SC CDR RFA 23 Response RevA.doc | 2004-08-09 | PM Approved 8/16/04 | 2004-08-18 | JR approved via email 8/18/04 | 2004-08-18
24 | Demonstrate 3 dB Margin Against EMI Susceptibility for GBM | Steve Battel | SAI | Joe Chott | MCDR | SC CDR RFA 24 Response.doc | 2004-08-05 | PM Approved 8/16/04 | 2004-08-18 | SB approved via email 8/18/04 | 2004-08-18
25 | Provide Additional Reliability Information | Steve Battel | SAI | Kendall Nii | MCDR | SC CDR RFA 25 Response RevB.doc | 8/13/2004 10/20/2004 1/10/2005 | Sent to PM 2/25/05 KG OK AV comment re RWA MTBF and impact of table 3/2/05 Agreed to send response to SB during GPO meeting with Goans 4/14/05 | 2005-04-14 | SB approved via email 4/15/05 | 2005-04-15
26 | Provide Qualification Information for Ku Antenna System | Steve Battel | SAI | Kendall Nii | 2005-06-30 | SC CDR RFA 26 Response RevA.doc | 2004-11-19 | PM Approved 5/11/05 | 2005-05-11 | SB approved via email 5/16/05 | 2005-05-16
27 | Instrument Performance Testing during Launch Operations Flow | Steve Battel Don Kniffen | SAI | Ron Zitek | MCDR | SC CDR RFA 27 Response.doc | 2004-08-05 | PM Approved 8/16/04 | 2004-08-18 | SB approved via email 8/18/04 DK approved via email 9/16/04 | 2004-09-16
28 | Install Protective Cover on Star Trackers until Launch | Steve Battel | SAI |  |  |  | SC CDR | Closed @ CDR |  | CLOSED @ CDR | 2004-05-27
29 | Define Mitigation for the Risk of cPCI Gold Fretting | Ron Kolecki | SAI | Nick Gaudio | 2004-06-30 | SC CDR RFA 29 Response.doc | 2004-07-06 | PM Approved 8/2/04 | 2004-08-06 | RK approved via email 8/12/04 | 2004-08-12
30 | Electrical Grounding versus Thermal Isolation | Scott Glubke | SAI | Scott Capehart | MCDR | SC CDR RFA 30 Response RevB.doc | 2004-08-05 | PM Approved 8/16/04 RG confirmed 9/20/04 | 2004-09-20 | SG approved via email 1/5/05 | 2005-01-05
31 | Water Hammer Verification | Scott Glubke | SAI | Scott Capehart | MCDR | SC CDR RFA 31 Response.doc | 8/19/2004 11/23/2004 | PM Approved 12/13/04 | 2004-12-14 | SG approved via email 12/20/04 | 2004-12-20
32 | Assess Orbital Heating Environments of Beta Angle up to -52 Deg. | Bill Fischer John Sharp | SAI | Ron Grebe | MCDR | SC CDR RFA 32 Response RevA.doc | 2004-08-05 | PM Approved 9/12/04 | 2004-09-13 | JS approved via email 9/21/04 DG approved for BG via email 12/13/04 | 2004-12-13
33 | Demonstrate the Design Capability to Execute the De-orbit Plan | Jim Rose | SAI | Jim Howe | 2005-06-30 | SC CDR RFA 33 Response.doc | 9/3/2004 11/19/2004 | Systems Review sent 11/23 JF comments sent to KN on 12/6/04 SASS response received 9/20/05 & sent to MU |  |  |  | Send to Mark Underdown
34 | Analyze Thermal Response of Sun on –X Face of the Spacecraft | Bill Fischer Ron Zellar | SAI | Ron Grebe | MCDR | SC CDR RFA 34 Response RevE.doc | 8/5/2004 2/15/2005 2/21/2005 | PM Approved 9/12/04 RZ intent was to analyze sun normal to -X. Resent to SASS on 12/10. KN sent updated response on 2/21 TM approved update and resent to Orig. Updated to state temps are steady state per RZ comment | 9/13/2004 3/22/2005 3/29/2005 | RZ approved via email 3/30/05 | 2005-04-04
DG approved via email 4/4/05
35 | LAT Humidity Control Requirements from I&T through Launch | Bob Vernier Tom Venator | SAI | Ron Zitek | MCDR | SC CDR RFA 35 Response.doc | 2004-08-05 | PM Approved 8/16/04 | 2004-08-18 | TV approved via email 8/24/04 | 2004-09-02
BV approved via email 9/2/04
36 | Consider Multiple Failure Cases for EOM/EOL Planning | Scott Glubke Don Kniffen | GPO | Terry Ford | MCDR | SC CDR RFA 36 Response RevB.doc | 2004-08-30 | PM Approved 9/12/04 | 2004-09-13 | SG & DK approved via email 9/16/04 | 2004-09-16
[10 empty] | Total RFAs | 36
[10 empty] | # Closed | 30
R1 | Reduce Number of Battery Pressure Triggers to Safe Mode | Phil Sabelhaus | SAI | Kendall Nii |  | SC CDR Recomm 1 Response RevA.doc | 1/28/2005 4/19/2005 | PM Approved 3/21/05 | 2005-04-01
R2 | Use BOL Properties in L&EO Thermal Analysis | Bill Fischer | SAI | Ron Grebe |  | SC CDR Recomm 2 Response.doc | 2005-01-28 | PM Approved 3/21/05 | 2005-04-01
R3 | Modify Passive S/C Thermal Design to Meet SSR and S-Band Goal | Bill Fischer | SAI | Ron Grebe |  | SC CDR Recomm 3 Response.doc | 2005-01-28 | PM Approved 3/21/05 | 2005-04-01
R4 | Review Property Data/Degradation Rates Used in TMM and GMM | Bill Fischer | SAI | Ron Grebe |  | SC CDR Recomm 4 Response.doc | 2005-01-28 | PM Approved 3/21/05 | 2005-04-01
R5 | Consider TDRS 911 Notification When SSR Nears Max Capacity | Ron Zellar | SAI | Jim Howe |  | SC CDR Recomm 5 Response RevA.doc | 2005-01-28 | PM Approved 3/21/05 | 2005-04-01
R6 | SSR Operations | Ron Zellar | SAI | Ken Lewis |  | SC CDR Recomm 6 Response RevA.doc | 2004-07-14 | PM Approved 3/29/05 | 2005-04-01
R7 | LAT-Spacecraft Thermal Distortion | Jim Rose | SAI | Jim Howe |  | SC CDR Recomm 7 Response RevA.doc | 2005-01-28 | PM Approved 3/21/05 | 2005-04-01
R8 | Verification of Propulsion System Thermal Design | Scott Glubke | SAI | Ron Grebe |  | SC CDR Recomm 8 Response.doc | 2005-01-28 | PM Approved 3/21/05 | 2005-04-01

## AETD Ptg #1
RFA | Title | Originator | Assignee | Due Date | Response | Date Submitted to GPO | Project Office Review Status | Date Submitted to Originator | Date Approved by Originator | Closure Date
1 | ST Error Budget in Body Coordinates | Mike Femiano | Eric Stoneking | 2004-06-30 | AETD Pointing Review RFA 1 Response RevB.doc | 2004-06-04 | OK, Send with SE Peer #6 8/20/04 meeting | 2004-08-23 | MF approved via email 10/19/04 per AETD review #2 | 2004-10-19
2 | ST Boresight Co-Alignment | Scott Starin | Eric Stoneking | 2004-06-30 | AETD Pointing Review RFA 2 Response.doc | 2004-05-20 | OK, Send with SE Peer #6 8/20/04 meeting | 2004-08-23 | SS approved via email 8/24/04 | 2004-08-24
3 | 3 Sigma Frequency Domain | Mike Femiano | Art Whipple | 2004-06-30 | AETD Pointing Review RFA 3 Response.doc | 2004-08-04 | OK 8/20/04 meeting | 2004-08-23 | MF approved via email 8/23/04 | 2004-08-23
4 | Calibration Alignment Sequence | Mike Femiano | Eric Stoneking | 2004-06-30 | AETD Pointing Review RFA 4 Response.doc | 2004-08-04 | OK 8/20/04 meeting | 2004-08-23 | MF approved via email 8/23/04 | 2004-08-23
5 | Show flowdown of 10 arsec to Spacecraft 6 arcsec PCS Design Requirement | Mike Femiano | Eric Stoneking | 2004-06-30 | AETD Pointing Review RFA 5 Response.doc | 2004-05-20 | OK 8/20/04 meeting | 2004-08-23 | MF approved via email 8/23/04 | 2004-08-23
6 | Analyze ST Thermal Variations | Mike Femiano | Eric Stoneking | 2004-06-30 | AETD Pointing Review RFA 6 Response.doc | 2004-05-20 | OK 8/20/04 meeting | 2004-08-23 | MF approved via email 8/23/04 | 2004-08-23
7 | Analyze ST to LIP thermal distortions for STA 1 and 3 | John Deily | Chris Connor | 2004-06-30 | AETD Pointing Review RFA 7 Response.doc | 2004-08-18 | OK 8/20/04 meeting | 2004-08-23 | JD approved via email 10/14/04 | 2004-10-14
8 | Add uncertainty factors for the thermal mechanical distortion and for jitter | Minh Phan | Paul Baird/Eric Stoneking | 2004-06-30 | AETD Pointing Review RFA 8 Response.doc | 2004-08-18 | OK 8/20/04 meeting | 2004-08-23 | MP approved via email 8/23/04 | 2004-08-23
9 | Verify that reaction wheel disturbance models include 3 axis force/torque equations which capture harmonic effects | Mike Femiano | Eric Stoneking | 2004-06-30 | AETD Pointing Review RFA 9 Response RevA.doc | 5/20/2004 4/19/2005 | OK 8/20/04 meeting | 8/23/2004 4/19/2005 | MF approved via email 4/20/05 | 2005-04-20
10 | Determine the structural damping used in the NASTRAN modal analysis and determine how sensitive the response is the assumed damping | Sandra Irish | Chris Connor | 2004-06-30 | AETD Pointing Review RFA 10 Response RevC.doc | 2004-07-23 | OK | 2004-10-18 | SI approved via email 10/25/04 | 2004-10-25
11 | Need to perform a review of the LAT STOP structural model to understand how each tower was represented | Sandra Irish | Paul Baird | 2004-06-30 | AETD Pointing Review RFA 11 Response.doc | 2004-08-23 | Systems Review OK | 2004-08-25 | SI approved via email 10/25/04 | 2004-10-25
12 | What point on the LAT (each tracker or at the 4 point mount interface between the S/C and LAT) is used for jitter analysis | Minh Phan | Paul Baird | 2004-06-30 | AETD Pointing Review RFA 12 Response RevC.doc | 2004-08-31 | OK | 2004-10-18 | MP approved via email 4/29/05 | 2005-04-29 | Resent 2/7 & 3/18, 4/28
13 | Jitter Requirement Formulation | Alice Liu | Eric Stoneking | 2004-06-30 | AETD Pointing Review RFA 13 Response.doc | 2004-06-03 | OK 8/20/04 meeting | 2004-08-23 | AL approved via email 9/3/04 | 2004-09-03
[9 empty] | Total RFAs | 13
[9 empty] | # Closed | 13

## GBM CDR
RFA | Input RFA | Subject | Initiator | Assignee | Suspense Date | Response | Date Approved by Originator | Closure Date | Sent to Mark Goans
GBSYC-001 | AW01 | Power Box Operating Voltage Specification | Art Whipple Fred Huegel | Fred Berry | 2004-07-28 | GBSYC-001 Response.tif | 2005-03-22 | 2005-03-22 | 2005-04-02
GBSYC-001 Closure.tif
GBM System CDR RFA #1.htm
GBSYC-002 | BM01 | ACTEL FPGA use on GBM Power Box | Bruce Meinhold | Al English | 2004-07-16 | GBSYC-002 Response.tif | 2004-10-13 | 2004-10-13 | 2004-12-13
GBSYC-003 | BM02 | Operational & Survival Heater Selection and Derating | Bruce Meinhold | John Sharp | 2004-07-22 | GBSYC-003 Response.tif | 2004-07-28 | 2004-07-29 | 2004-08-18
GBSYC-004 | BM03 | Optocoupler radiation degration for PSB HV status | Bruce Meinhold | Al English | 2004-07-16 | GBSYC-004 Response.tif | 2004-07-28 | 2004-07-30 | 2004-08-18
66168.pdf
1010-66168-300 Opto Coupler.pdf
GBSYC-005 | BM04 | Fuse selection and derating | Bruce Meinhold | Al English | 2004-07-28 | GBSYC-005 Response.doc | BM Comments 8/25/05 |  |  | Emailed to BM 5/9, S. Clough has concerns with the small fuses, Spoke with BM on 6/21 and left voicemail on 7/8
GBSYC-006 | DG01 | Solar reflections between detectors & spacecraft | David Gilmore | John Sharp | 2004-07-28 | GBSYC-006 Response.doc |  |  |  | Sent email (4/14) to Joy stating this is transferred to SASS and will need to be worked under Mission Robustness
GBSYC-007 | DG02 | Silvered teflon solar absorptance | David Gilmore | John Sharp | 2004-07-16 | GBSYC-007 Response.tif | 2004-07-19 | 2004-07-20 | 2004-07-21
GBSYC-008 | DK01 | Corona in high voltage power box | Donald Kniffen | Fred Berry | 2004-07-28 | GBSYC-008 Response.tif | 2004-09-16 | 2004-09-27 | 2004-11-22
GBSYC-009 | EA01 | FSW testing & maintenance approach | Erik Andrews | Bob Wilson | 2004-10-15 | GBSYC-009 Response.PDF | 2005-08-01 | 2005-10-05 | 2005-10-07
GBM-PLAN-1043 FSW Post-Launch Sustaining Engineering Plan.doc
GBSYC-010 | EA02 | FSW schedule | Erik Andrews | Valerie Connaughton | 2004-08-05 | GBSYC-010 Response.tif | 2005-03-11 | 2005-03-16 | 2005-03-17
GBM Schedule 020405 Detail.pdf
GBSYC-011 | FB01 | PSB & DPU connector EMI gaskets/fusebox/PSB | Fred Blanchette | Al English | 2005-10-15
GBSYC-012 | JB01 | Document format of science data | Joy Bretthauer | Bill Paciesas | 2004-07-22 | GBSYC-012 Response.tif | 2005-03-10 | 2005-03-11 | 2005-04-21
GBM-GUIDE-1032.doc
GBSYC-013 | JH01 | Summary of tests deleted from schedule | Joy Henegar | Chip Meegan | 2004-07-22 | GBSYC-013 Response.tif | 2004-07-20 | 2004-07-21 | 2004-08-18
GBSYC-014 | JO01 | PDU parallell fuses | Jean Olivier | Mark James | 2004-07-22 | GBSYC-014 Response.tif | 2004-09-10 | 2004-09-12 | 2004-09-12
GBSYC-015 | JO02 | Lack of documented plan for GBM detector thermal interface development | Jean Olivier | Al English | 2004-07-28 | GBSYC-015 Response.tif | 2004-11-04 | 2004-11-08 | 2004-12-14
GBSYC-015 documentation.tif
GBSYC-016 | JO03 | Lack of plan for MLI design and development | Jean Olivier | John Sharp | 2004-07-22 | GBSYC-016 Response.tif | 2004-08-13 | 2004-08-24 | 2004-08-30
GBM MLI Fab Plan 7-29-04.ppt
MLI Schedule RFQ Draft2.pdf
GBSYC-017 | JR01 | Stress margins of safety | Jim Ryan | Al English | 2004-07-22 | GBSYC-017 Response.tif | 2005-03-22 | 2005-03-23 | 2005-03-30
Structural Analysis Report GBM- Issue1.pdf
DPU_Analysis_05128-SA-01.pdf
GBM-CD-StructuralAnalysis.pdf
GBSYC-018 | JR02 | Strength qualification | Jim Ryan | Al English | 2004-07-22 | GBSYC-018 Response.tif | 2005-03-22 | 2005-03-23 | 2005-03-30
Structural Analysis Report GBM- Issue1.pdf
DPU_Analysis_05128-SA-01.pdf
GBM-CD-StructuralAnalysis.pdf
GBSYC-019 | LB01 | Software Build 1 crashes occasionally when switching tasks | Lily Bashar | Michael Briggs | 2004-08-06 | GBSYC-019 Response.tif | 2004-09-10 | 2004-09-12 | 2004-09-12
GBSYC-020 | LB02 | Software Build 1 lacks 2 important requirements | Lily Bashar | Michael Briggs | 2004-07-16 | GBSYC-020 Response.tif | 2004-09-10 | 2004-09-12 | 2004-09-12
GBSYC-021 | LB03 | Possible schedule risk due to software deliveries | Lily Bashar | Steve Elrod | 2004-07-22 | GBSYC-021 Response.tif | 2004-09-07 | 2004-09-12 | 2004-09-12
GBSYC-022 | NR01 | Verification of GRB location requirements | Norman Rioux | Chip Meegan | 2004-07-28 | GBSYC-022 Response.tif | 2004-10-18 | 2004-10-20 | 2004-11-01
GBSYC-023 | FAB01 | Effective Area req.of NaI Crystal not met @ 14 KeV | Fred Berry | Rob Preece | 2005-09-15 | GBMSYC-023 Response.pdf | 2005-10-04 | 2005-10-04 | 2005-10-07
[8 empty] | Total RFAs | 23
[8 empty] | # Closed | 20
| NR02 | Append to FSW build RFA | Norman Rioux |  |  | Combined with GBSYC-010
| FH01 | Supply voltage tolerance for the PSB | Fred Huegel Art Whipple |  |  | Combined with GBSYC-001
| LB04 | 2 Copies of Build 3 SW instead of Build 2 and Build 3 | Lily Bashar |  |  | Comment

## GS SDR
RFA | Title | Originator | Assignee | Due Date | Response | Date Submitted to GPO | Project Office Review Status | Date Submitted to Code 300 | Closure Date
1 | Logistics Plan / Spare List | Steve Scott | Ross Cox | 2004-12-15 | GS SDR RFA 1 Response.doc | 2005-03-11 | PM Approved 3/21/05 | 2005-03-21 | 2005-04-05
GLAST Ground System G001 G022 G030 RMA RevA.doc
2 | Provide Open Item Closure Dates or Need Date | Bob Menrad | Ernest Canevari | 2004-12-15 | GS SDR RFA 2 Response.doc | 2/2/2005 3/23/2005 | PM Approved 4/2/05 | 2005-04-02 | 2005-04-05
SDR Open Items for RFA 2 Final Response 032305.ppt
3 | Rework Alert Processing via SN DAS or MA Return Service | Al Levine | Ross Cox Norman Rioux | 2004-12-15 | GS SDR RFA 3 Response.doc | 2004-10-08 | PM Approved 11/17/04 | 2004-11-22 | 2005-01-05
4 | Get Agreements from COTS Vendors to Escrow their Software | Bill Potter Steve Scott | Jonathan DeGumbia | 2004-12-15 | GS SDR RFA 4 Response.doc | 2004-09-29 | PM Approved 11/17/04 | 2004-11-22 | 2005-04-08
5 | S-Band Omni Antenna Null Zones | Bill Potter | Norman Rioux | 2004-12-15 | GS SDR RFA 5 Response RevA.doc | 12/1/2004 1/9/2005 | PM Approved 2/2/05 | 2005-02-03 | 2005-02-23
6 | Simulator Placement in MOC Design | Bob Menrad Vic Gehr Madeline Butler | Jonn Nagy | 2004-12-15 | GS SDR RFA 6 Response.doc | 2004-10-29 | PM Approved 12/12/04 | 2004-12-13 | 2005-04-12
7 | Provide Results of Efforts to Close all Peer Review Open RFAs Until They are Closed | Bob Menrad | Dennis Small | 2004-12-15 | GS SDR RFA 7 Response RevB.doc | 2004-11-05 | Closed in ITA NGIN system on 5/27 by Mark Goans | 2005-05-12 | 2005-05-27
8 | Restricted Ionet "Access" Policy and Processes | Clayton Sigman | Chris Spinola | 2004-12-15 | GS SDR RFA 8 Response.doc | 2004-10-21 | PM Approved 12/12/04 | 2004-12-13 | 2005-04-05
9 | Security Requirements | Mary Foote Bill Potter | Doug Spiegel Marilyn Mix Dustin Aldridge Ross Cox | 2004-12-15 | GS SDR RFA 9 Response RevC.doc | 12/2/2004 1/4/2005 | PM Approved 2/3/05 | 2005-02-03 | 2005-04-05
10 | Review the Lewis Mission Lessons Learned | Steve Scott | Ken Lehtonen | 2004-12-15 | GS SDR RFA 10 Response RevB.doc | 12/7/2004 2/3/2005 | PM Approved 2/10/05 | 2005-02-10 | 2005-02-17
11 | Back-up MOC Plans and Operator Ceritifications | Madeline Butler | Doug Spiegel | 2004-12-15 | GS SDR RFA 11 Response.doc | 2004-10-19 | PM Approved 12/12/04 | 2004-12-13 | 2005-04-05
12 | Investigate Use of Stored Commands vs. Unattended S/C Commanding | Vic Gehr | John Nagy | 2004-12-15 | GS SDR RFA 12 Response.doc | 2004-10-27 | PM Approved 12/12/04 | 2004-12-13 | 2005-04-05
13 | Consider Adding a Second Operational LAN within the MOC | Vic Gehr | Dustin Aldridge | 2004-12-15 | GS SDR RFA 13 Response.doc | 2004-11-03 | PM Approved 12/12/04 | 2004-12-13 | 2005-04-05
14 | Coordinate with the NASA Networks Some Type of Mutual Interference Testing | Tony Christmas Vic Gehr | Ross Cox | 2004-12-15 | GS SDR RFA 14 Response.doc | 2005-05-19 | PM Approved 6/8/05 | 2005-05-19 | 2005-05-26
15 | Investigate Shipment of GFEP to WSGT | Vic Gehr | Ross Cox | 2004-12-15 | GS SDR RFA 15 Response.doc | 2004-10-29 | PM Approved 12/12/04 | 2004-12-13 | 2005-04-05
16 | Determine LEO H/W, S/W, I/F Needed to Support Instruments in MOC | Vic Gehr | Ernest Canevari | 2004-12-15 | GS SDR RFA 16 Response.doc | 2005-01-06 | PM Approved 1/19/05 | 2005-01-19 | 2005-01-28
17 | Establish TDRSS Link at S/C I&T Facility | Vic Gehr | Norman Rioux | 2004-12-15 | GS SDR RFA 17 Response.doc | 2004-10-29 | PM Approved 12/12/04 | 2004-12-13 | 2005-04-05
18 | Determine Access and Availability of S/C Simulator for Pre-Launch and Post-Launch Use | Vic Gehr | John Teter | 2004-12-15 | GS SDR RFA 18 Response.doc | 2004-11-04 | PM Approved 12/12/04 | 2004-12-13 | 2005-04-05
19 | Provide a Summary of Propulsion System Verification | Bob Menrad | Jack Leibee | 2004-12-15 | GS SDR RFA 19 Response.doc | 2004-11-29 | PM Approved 12/1/04 | 2004-12-01 | 2005-01-18
20 | FSW Maintenance and Process to Transmit an Update | Bob Menrad Bob Schweiss | Bob Sodano Jack Leibee | 2004-12-15 | GS SDR RFA 20 Response.doc | 2004-11-18 | PM Approved 12/12/04 | 2004-12-13 | 2005-04-05
21 | Star Catalog Accuracy | David Tracewell |  | 2004-12-15 | GS SDR RFA 21 Response.doc | 2005-02-16 | PM Approved 3/2/05 | 2005-03-02 | 2005-03-07
SWIFT_Star_Cat_RFA21.doc
22 | Provide a Copy of the Reliability Study Conducted for MOC Network | Ray Baldwin | Howard Dew Jonathan DeGumbia | 2004-12-15 | GS SDR RFA 22 Response.doc | 2005-03-09 | PM Approved 3/21/05 | 2005-03-21 | 2005-04-05
GLAST Ground System G001 G022 G030 RMA RevA.doc
23 | Provide a Copy of the Risk Analysis/Plan for Each Identified "Single Point of Failure" | Ray Baldwin | Jonathan DeGumbia | 2004-12-15 | GS SDR RFA 23 Response RevA.doc | 2005-02-09 | PM Approved 3/2/05 | 2005-03-02 | 2005-04-05
24 | Reconsider Choice of Tool to Track Software Discrepancies | Ron Mahmot Bob Sodano | Jonathan DeGumbia | 2004-12-15 | GS SDR RFA 24 Response.doc | 2004-11-03 | PM Approved 12/12/04 | 2004-12-13 | Submitted for closure as disagreement with Originator 6/20/05 M. Goans and B. Sodano closed on 7/21/05 See ITA NGIN
25 | Evaluate the use of 3 Different Paging Systems in the Ground System | Ron Mahmot Bob Sodano | Ross Cox | 2004-12-15 | GS SDR RFA 25 Response.doc | 2004-10-29 | PM Approved 12/12/04 | 2004-12-13 | 2005-04-13
26 | Consider having GLAST Ground System Receive DAS Burst Alert and 911 Messages from Swift | Ron Mahmot Al Levine | Ross Cox | 2004-12-15 | GS SDR RFA 26 Response.doc | 2005-01-04 | PM Approved 2/3/05 | 2005-02-04 | 2005-02-17
27 | What are the Traces to the Parent Requirements for those Listed as "Derived" | Madeline Butler Glenn Iona | Ken Lehtonen | 2004-12-15 | GS SDR RFA 27 Response.doc | 2004-12-02 | PM Approved 1/28/05 | 2005-01-31 | 2005-02-15
28 | Reconsider the use of the GMSEC Bus as a means to Communicate between S/W Applications in the MOC | Ron Mahmot | Ken Lehtonen | 2004-12-15 | GS SDR RFA 28 Response RevB.doc | 2004-11-09 | PM Approved 12/12/04 | 2004-12-13 | 2005-04-05
29 | Consider which Ground System Components will most likely need a Post Launch Release and Commit to it in Schedules | Ron Mahmot | Ken Lehtonen | 2004-12-15 | GS SDR RFA 29 Response.doc | 2004-09-29 | PM Approved 11/17/04 | 2004-11-22 | 2005-01-05
30 | Provide the Results of the Reliability, Maintainability, Availability Analysis to Provide a Level and Confidence that the GS Architecture can meet Performance Rqmts | Bill Potter | Ross Cox | 2004-12-15 | GS SDR RFA 30 Response.doc | 2005-03-18 | PM Approved 3/21/05 | 2005-03-21 | 2005-03-24
GLAST Ground System G001 G022 G030 RMA RevA.doc
31 | Document the Remaining GFEP Issues | Bill Potter | Ross Cox | 2004-12-15 | GS SDR RFA 31 Response.doc | 2004-10-08 | PM Approved 11/17/04 | 2004-11-22 | 2005-01-05
32 | Review Recommendations made by GSFC Space Asset Protection Team and Implement as Appropriate Regarding the Protection of Sensitive Information on Server | Ron Mahmot | John Nagy | 2004-12-15 | GS SDR RFA 32 Response.doc | 2004-11-02 | PM Approved 12/12/04 | 2004-12-13 | 2005-01-18
33 | Work with NISN to Ensure the MOC Network is Compliant with NASA Security Requirements | Bill Potter | Doug Spiegel | 2004-12-15 | GS SDR RFA 33 Response.doc | 2004-12-03 | PM Approved 1/19/05 | 2005-01-19 | 2005-01-28
34 | State Whom the Responsible Manager is for each Facility | Tony Christmas | Ernest Canevari | 2004-12-15 | GS SDR RFA 34 Response.doc | 2004-11-17 | PM Approved 12/12/04 | 2004-12-13 | 2005-04-05
35 | Consistency of Link Specifications, Test Information Sheets, RF Long-Loop Configuration, Test Requirements | Tony Christmas | Bruce Wagner Ross Cox Ernest Canevari | 2004-12-15 | GS SDR RFA 35 Response.doc | 2005-01-10 | PM Approved 1/28/05 | 2004-01-31 | Closed in ITA NGIN by M. Goans 7/21/05
GSRD Test Matrix 0923043.xls
36 | What is the Plan for Verifying the Requirements Allocated to the ETEs | Glenn Iona | Ernest Canevari | 2004-12-15 | GS SDR RFA 36 Response RevA.doc | 2004-10-12 | PM Approved 12/12/04 | 2004-12-13 | 2005-04-05
|  |  |  | 2004-12-15 | GSRD Test Matrix 0923043.xls
[8 empty] | Total RFAs | 36
[8 empty] | # Closed | 36

## MCDR
RFA # | Title | Originator | Assignee | Due Date | Response | Date Submitted to Systems | Project Office Review Status | Date Submitted to Code 300 | Closure Status | Closure Date
1 | Provide Decision Dates and "Net" Savings from Descope Options | Mark Goans | Tom Venator | 2004-10-29 | MCDR RFA 1 Response RevA.doc | 10/21/2004 11/8/2004 | PM Approved 11/17/04 | 2004-11-22 | MG approved via email 1/27/05 | 2005-01-27
2 | Develop a Realistic Descope List | Phil Sabelhaus | Kevin Grady | 2004-10-29 | MCDR RFA 2 Response.doc | 2004-10-27 | PM Approved 11/15/04 | 2004-11-16 | PS approved via email 12/14/04 | 2004-12-14
3 | Include a Lien for the May 2007 Launch Readiness Date | Phil Sabelhaus | Mark Seidleck | 2004-10-29 | MCDR RFA 3 Response RevA.doc | 2004-12-08 | PM Approved 12/13/04 | 2004-12-14 | PS approved via email 12/14/04 | 2004-12-14
4 | Enter Lessons Learned for GLAST RSDO Specifications and SOW | Sam Placanica | Jack Leibee | 2004-12-30 | MCDR RFA 4 Response.doc | 2005-01-27 | PM Approved 2/7/05 | 2005-02-07 | SP approved via email 2/22/05 | 2005-02-22
5 | Provide Details of Observatory Magnetics Test | Sam Placanica | Joy Henegar | 2004-12-30 | MCDR RFA 5 Response.doc | 2005-01-31 | PM Approved 2/7/05 | 2005-02-07 | SP approved via email 2/22/05 | 2005-02-22
6 | Describe Impact to FSW/Procedure Development if Hot Bench Fails | Jean Olivier | Erik Andrews | 2004-10-08 | MCDR RFA 6 Response.doc | 2004-10-04 | PM Approved 10/27/04 | 2004-10-29 | JO approved via email 11/2/04 | 2004-11-02
7 | Provide Additional LAT FSW Development Plan/Schedule Data | Jim Rose Mike Blau | Erik Andrews | 2004-10-08 | MCDR RFA 7 Response.doc | 2004-10-18 | PM Approved 10/24/04 | 2004-10-25 | JR and MB comments sent to Andrews on 11/22
8 | Implement Rigorous Project Mission-Level Plan and Requirements for Documenting Problems | Jim Rose | Joy Henegar | IRR
9 | Status the Schedule and Provide Copies to Review Team | Bill Gibson | Al Vernacchio | 2005-07-31 | MCDR RFA 9 Response.doc | 2004-11-03 | PM Approved 11/3/04 PM Approved 6/16/2005 | 11/8/2004 6/16/2005 | BG approved via email 7/6/05 | 2005-07-06
Glast 100704.pdf
Glast 060305mc.pdf
10 | Reconsider Use of Non-Flight FPGAs for FM Board Checkout | Bill Gibson Steve Scott Fred Huegel | Kevin Grady | 2004-12-30 | MCDR RFA 10 Response RevB.doc | 2004-10-08 | PM Approved 11/15/04 PM Approved Rev B 1/10/05 | 11/16/2004 1/14/2005 | FH approved Rev B via email 1/18/05 | 2005-01-27
SS approved Rev B via email 1/21/05
BG approved Rev B via email 1/27/05
11 | Please Clarify GLAST Mission Bake-out Requirements | Bill Gibson | Jack Leibee | 2004-12-30 | MCDR RFA 11 Response.doc |  | PM Approved 5/1/05 | 2005-05-18 | BG approved via email 5/20/05 | 2005-05-20
433-PLAN-0010 Baseline.pdf
12 | Re-evaluate Increasing ACD PMT Qualification Temperature Cycles | David Glimore | Bernie Graf | 2004-12-30 | MCDR RFA 12 Response.doc | 2004-10-05 | PM Approved 11/17/04 | 2004-11-22 | DG approved via email 11/30/04 | 2004-11-30
13 | Evaluate S/C Testing with and w/o LAT Mass & Power Simulator | Phil Sabelhaus | Tom Venator | 2004-12-30 | MCDR RFA 13 Response RevA.doc | 2004-10-21 | PM Approved 1/3/05 | 2005-01-03 | PS approved via email 1/4/05 | 2005-01-04
14 | Investigate whether GLAST OCXOs are Free of Failure Concerns | Steve Scott Joe Bolek | Jack Leibee | 2004-12-30 | MCDR RFA 14 Response.doc | 2004-10-04 | PM Approved 11/17/04 | 2004-11-22 | JB approved via email 11/23/04 | 2005-01-21
SS approved via email 1/21/05
15 | Provide Final Versions of FMECA, FTA, SPF, and PRA | Steve Scott Jim Rose | Jack Leibee | 2004-12-30 | GLAST Reliability Data Summary.doc | 2005-01-28 | Sent to Mark Goans on 9/24/04 | 2004-09-24 | MG and SS approved via email 1/28/05 | 2005-01-28
16 | Consider Making SC Fault Manager SW Easier to Reconfigure | Mike Blau |  |  |  |  | Closed at Review |  | Closed at Review | 2004-09-22
17 | Recommend Reviewing GBM Trigger Algorithms w/Swift SW team | Mike Blau |  |  |  |  | Closed at Review |  | Closed at Review | 2004-09-22
18 | Define Impact to Mission of a 17-20 arcsec Pointing Knowledge | Joe Bolek | Steve Ritz | 2004-12-30 | MCDR RFA 18 Response RevA.doc | 1/31/2005 3/25/2005 | PM Approved 4/2/05 | 2005-04-02 | JB approved via email 5/5/05 | 2005-05-05 | Resent to Joe 4/14/05 & 4/28
[9 empty] | Total RFAs | 18
[9 empty] | # Closed | 16
R1 | Consider Adding a Requirements Verification Manager | Joe Bolek | Jack Leibee

## ACD PER
RFA # | Title | Originator | Due Date | Response | Date Submitted to Code 300 | Closure Status | Closure Date
1 | Pre Test Liens | Tom McCarthy | 2005-07-31 | ACD PER RFA 1 Response.doc | ACD emailed to TM 7/8/05 | Approval email shown in ITA NGIN | 2005-07-12
2 | Fiber Stress | Fred Huegel | 2005-07-31 | ACD PER RFA 2 Response.doc | Submitted in ITA NGIN 7/11/05 | FH Closed at ACD PSR | 2005-08-08
[6 empty] | Total RFAs | 2
[6 empty] | # Closed | 2

## Open RFAs
RFA | Title | Originator | Due Date | Current Actionee | Impact | Project Office Review Status
SC PDR
39 | Solar Array Verification Plan | Son Ngo | 2005-07-31 | Project Office | Solar array verification testing is being updated | Submitted to Originator 9/30/05 Son Ngo provided questions on response on 10/28
SC CDR
3 | Perform EMI Testing with Solar Arrays Installed | Fred Huegel Pete Salerno | PER | Fred Blanchette |  | Response Due by PER
8 | Provide Strength Qualification Plan for the Solar Array | Minh Phan | PER | Spectrum Astro |  | Response Due by PER
9 | Subject the Solar Array Wing to 3-Axis Sine Vibration Test | Minh Phan | PER | Spectrum Astro |  | Response Due by PER
11 | Verification of Minimum Frequency Goal of Deployed SA | Minh Phan | PER | Spectrum Astro |  | Response Due by PER
13 | Describe Testing Approach for Fault Management System | Steve Scott | 2006-01-31 | Spectrum Astro | Impacts FM testing | Project Office Awaiting Updated Response from Spectrum Astro based on Project Office Comments sent on 8/17/04, updated comments sent on 2/24/05
33 | Demonstrate the Design Capability to Execute the De-orbit Plan | Jim Rose | 2005-06-30 | Mark Underdown | Provide data on parts to show design capability | Project Office Awaiting Updated Response from Spectrum Astro based on Project Office Comments sent on 12/6/04 Response to Project comments from SASS received on 9/20/05. Sent to Mark Underdown for review
GBM CDR
GBSYC-005 | Fuse selection and derating | Bruce Meinhold | 2004-07-28 | MSFC | Potential fuse change | Response sent to Originator by MSFC and by GSFC Scott Clough had concerns about small FM08 fuses Spoke to Bruce on 6/21, he will try to discuss the response with Henning Leidecker today Left voicemail on 7/8 Resent again on 7/20 & 8/3 Received response from BM on 8/25. Looking at replacing the fuses with FM-12 if box opened for EMI
GBSYC-006 | Solar reflections between detectors & spacecraft | David Gilmore | 2005-09-30 | Spectrum Astro | Additional SC MLI | Reassigned to SASS
GBSYC-011 | PSB & DPU connector EMI gaskets/fusebox/PSB | Fred Blanchette | 2005-10-15 | MSFC | Add gaskets to boxes | Failed tests, MSFC added gaskets to EMs and retested. 2 channel PB passed and DPU had exceedances. Reworked test harness to make "bullet-proof". Flight DPU still failed. Working with SwRI to resolve
MCDR
7 | Provide Additional LAT FSW Development Plan/Schedule Data | Jim Rose Mike Blau | 2004-10-08 | Erik Andrews | LAT FSW plan may not be achiveable | Response Submitted to Originators 10/25/04 Originator Comments Received 11/16/04 Project Office to Update Response per Originator Comments Submitted email exchange between Al and Jim Rose with a request for closure to Mark Goans 10/7/05 Resent email on 11/1/05
8 | Implement Rigorous Project Mission-Level Plan and Requirements for Documenting Problems | Jim Rose | IRR | Joy Henegar |  | Due at IRR
ACD PSR

## MSR-QSR Summary
Review | Date | Total # of RFA's | Responses Submitted by Project | RFA's Closed by Review Team | Open RFA's | Comments
Mission SRR | 2000-09-01 | 22 | 22 | 22 | 0 | All Closed
LAT PDR | 2002-01-01 | 57 | 57 | 57 | 0 | All Closed
GBM PDR & FSW PDR | 2002-04-01 | 27 | 27 | 27 | 0 | All Closed
LAT delta PDR | 2002-07-01 | 20 | 20 | 20 | 0 | All Closed
SC PDR | 2003-05-01 | 43 | 43 | 42 | 1 | Responding to comments from Originator
SC FSW PDR | 2003-05-01 | 14 | 14 | 14 | 0 | All Closed
LAT CDR | 2003-05-01 | 37 | 37 | 37 | 0 | All Closed
MPDR | 2003-06-01 | 14 | 14 | 14 | 0 | All Closed
GS SRR | 2003-07-01 | 17 | 17 | 17 | 0 | All Closed
SC FSW CDR | 2004-04-01 | 11 | 11 | 11 | 0 | All Closed
SC CDR | 2004-05-01 | 36 | 30 | 30 | 6 | 6 In Work by Project, 4 of Those Not Due until PER, No Design Impacts, Remaining Deal with Verification and Test
GBM CDR | 2004-06-01 | 23 | 21 | 20 | 3 | 1 being Updated per Originator Comments, 2 In Work by Project - Following MSFC RFA Process, 1 Awaiting Test Results, 1 Reassigned to SC
GS SDR | 2004-08-01 | 36 | 36 | 36 | 0 | All Closed
MCDR | 2004-09-01 | 18 | 17 | 16 | 2 | 2 Open - 1 Submitted to Board chair for closure, 1 Due at IRR
Totals |  | 375 | 366 | 363 | 12

## Summary
| Total # of RFAs | Systems Review Status |  | Project Review Status |  | Code 300 Status
Review |  | In Review | Complete | In Review | Complete | # Closed | Notes
Mission SRR | 22 |  | 22 |  | 22 | 22 | All Closed
LAT PDR | 57 |  | 57 |  | 57 | 57 | All Closed
GBM PDR & FSW PDR | 27 |  | 27 |  | 27 | 27 | All Closed
LAT delta PDR | 20 |  | 20 |  | 20 | 20 | All Closed
SC PDR | 43 |  | 43 |  | 43 | 42 | 1 Open
SC FSW PDR | 14 |  | 14 |  | 14 | 14 | All Closed
LAT CDR | 37 |  | 37 |  | 37 | 37 | All Closed
MPDR | 14 |  | 14 |  | 14 | 14 | All Closed
GS SRR | 17 |  | 17 |  | 17 | 17 | All Closed
SC FSW CDR | 11 |  | 11 |  | 11 | 11 | All Closed
SC CDR | 36 | 1 | 31 | 1 | 30 | 30 | 6 Open
GBM CDR | 23 |  | 21 |  | 21 | 20 | 3 Open
GS SDR | 36 |  | 36 |  | 36 | 36 | All Closed
MCDR | 18 |  | 17 |  | 17 | 16 | 2 Open
Totals | 375 | 1 | 367 | 1 | 366 | 363
Approved
Review | Total # of RFAs | by Originator | Notes
ACD CDR | 19 | 19 | All Closed
LAT CDR Peer Reviews | 177 | 177 | All Closed
LAT CAL-Grid Peer | 7 | 7 | All Closed
LAT Power Supply Peer | 6 | 6 | All Closed
LAT X-LAT Peer Review | 8 | 8 | All Closed
LAT X-LAT MRR | 3 | 3 | All Closed
LAT FSW FU Peer | 6
GBM DPU CDR | 7 | 7 | All Closed
GBM PB/DET CDR | 38 | 38 | All Closed
AETD Pointing Peer #1 | 13 | 13 | All Closed
ACD PER | 2 | 2 | All Closed
ACD PSR | 5 | 5
Ground System | Total # of RFAs | Project Review Status |  | Originator Status
Peer Reviews |  | In Review | Complete | # Closed | Notes
GBM IOC Preliminary | 6 |  | 6 | 6 | All Closed
GSSC Preliminary | 19 |  | 19 | 19 | All Closed
MOC Preliminary | 10 |  | 10 | 10 | All Closed
GFEP Preliminary | 7 |  | 7 | 7 | All Closed
FDF Preliminary | 14 |  | 14 | 14 | All Closed
LAT ISOC Preliminary | 8 |  | 8 | 8 | All Closed
GSSC Detailed | 7 |  | 7 | 7 | All Closed
MOC Detailed | 7 |  | 7 | 7 | All Closed
GFEP Detailed | 6 |  | 6 | 6 | All Closed
FDF Detailed | 5 |  | 5 | 5 | All Closed
USN Detailed | 1 |  | 1 | 1 | All Closed
LAT ISOC Detailed | 20 |  | 20 | 20 | All Closed
Totals | 110 | 0 | 110 | 110

## Closure Sheet
Due Dates to Project Office
2003-10-30 | 2003-10-31 | 2003-11-21 | 2003-11-28 | 2003-12-01 | 2003-12-12 | 2003-12-15 | 2004-02-15 | 2004-04-01 | 2004-04-26 | 300 Closed
75 | 86 | 102 | 119 | 128 | 133 | 135 | 141 | 143 | 146 | 105
Responses Received in Project Office
2003-10-30 | 2003-11-12 | 2003-11-17 | 2003-11-18 | 2003-12-01 | 2004-01-05 | 2004-01-30 | 2004-02-05 | 2004-02-12 | 2004-02-17 | 2004-02-18 | 2004-02-20 | 2004-02-24 | 2004-03-02 | 2004-03-04 | 2004-03-05 | 2004-03-08 | 2004-03-10 | 2004-03-24 | 2004-03-30 | 2004-03-31 | 2004-04-01 | 2004-04-21 | 2004-05-10 | 2004-05-11 | 2004-05-21 | 2004-07-13 | 2004-07-26 | 2004-09-09 | 2004-09-13 | 2004-09-15 | 2004-09-16
75 | 76 | 80 | 85 | 86 | 99 | 101 | 102 | 106 | 110 | 111 | 112 | 113 | 115 | 119 | 120 | 125 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143
Planned Responses Complete Systems Review
2003-10-30 | 2003-11-21 | 2003-12-10 | 2004-01-14 | 2004-01-28 | 2004-02-11 | 2004-02-25 | 2004-03-10 | 2004-03-24 | 2004-04-07 | 2004-04-30
13 | 22 | 39 | 54 | 69 | 84 | 99 | 114 | 129 | 143 | 146
Responses Complete Systems Review
2003-10-30 | 2003-11-21 | 2004-01-08 | 2004-01-16 | 2004-02-12 | 2004-02-19 | 2004-03-03 | 2004-03-15 | 2004-03-19 | 2004-03-22 | 2004-03-24 | 2004-04-21 | 2004-04-30 | 2004-05-13 | 2004-05-19 | 2004-05-20 | 2004-05-20 | 2004-07-13 | 2004-07-14 | 2004-07-21 | 2004-07-22 | 2004-08-13 | 2004-08-16 | 2004-08-17 | 2004-08-24 | 2004-08-27 | 2004-09-03 | 2004-09-09 | 2004-09-14 | 2004-09-15
13 | 32 | 32 | 57 | 62 | 70 | 86 | 101 | 102 | 104 | 105 | 116 | 118 | 120 | 121 | 122 | 123 | 125 | 126 | 130 | 131 | 132 | 135 | 136 | 138 | 139 | 140 | 141 | 142 | 143
Planned Responses Complete Project PM Review
2003-11-14 | 2003-12-05 | 2003-12-19 | 2004-01-30 | 2004-02-13 | 2004-02-27 | 2004-03-12 | 2004-03-26 | 2004-04-09 | 2004-04-23 | 2004-05-14
13 | 22 | 39 | 54 | 69 | 84 | 99 | 114 | 129 | 143 | 146
Responses Complete Project PM Review
2003-11-14 | 2003-12-08 | 2004-01-07 | 2004-02-19 | 2004-02-23 | 2004-03-02 | 2004-03-17 | 2004-03-30 | 2004-04-04 | 2004-04-15 | 2004-05-14 | 2004-05-19 | 2004-05-24 | 2004-05-25 | 2004-06-06 | 2004-06-09 | 2004-06-26 | 2004-07-13 | 2004-08-02 | 2004-08-16 | 2004-08-28 | 2004-09-07 | 2004-09-12 | 2004-09-15 | 2004-09-15
0 | 12 | 29 | 53 | 54 | 64 | 73 | 74 | 77 | 89 | 90 | 103 | 105 | 106 | 107 | 108 | 112 | 114 | 124 | 127 | 129 | 130 | 135 | 136 | 139
Responses Complete Originator Review
 | time axis 2003-12-14 to 2004-09-30
1 | 2 | 8 | 10 | 13 | 14 | 15 | 17 | 20 | 22 | 26 | 33 | 35 | 37 | 38 | 44 | 46 | 47 | 48 | 53 | 54 | 55 | 58 | 60 | 61 | 62 | 64 | 67 | 72 | 73 | 74 | 82 | 87 | 89 | 91 | 92 | 98 | 99 | 100 | 101 | 104 | 105 | 106 | 107 | 109 | 111 | 112 | 113 | 115 | 116 | 122 | 125 | 127 | 128 | 130 | 131
LAT PDR | GBM PDR | LAT DPDR | SCPDR | FSWPDR | LAT CDR | MPDR | GS SRR | M SRR | Sum
14 |  | 3 | 10 | 3 | 17 | 3 | 12 |  | 62 | Sys
[5 empty] | 11 |  |  |  | 11 | 2003-10-31
|  |  | 11 | 5 |  |  |  |  | 16 | 2003-11-21
|  |  | 7 | 4 |  | 6 |  |  | 17 | 2003-11-28
[5 empty] | 9 |  |  |  | 9 | 2003-12-01
|  |  | 3 | 2 |  |  |  |  | 5 | 2003-12-12
| 2 | [7 empty] | 2 | 2003-12-15
|  |  | 1 | [5 empty] | 1 | 2004-02-15
| 2 | [7 empty] | 2 | 2004-04-01
|  |  | 3 | [5 empty] | 3 | 2004-04-26
|  |  | 8 |  |  | 5 |  |  | 13 | "@ PM"
[7 empty] | 5 |  | 5 | need fromMike
43 | 23 | 17 | [5 empty] | 22 | 105 | 300 closed
57 | 27 | 20 | 43 | 14 | 37 | 14 | 17 | 22