## ACD
ACD Early Integration Test
Rev. 8/8/05 R.Baun
Item | STR No. | Sub-Series | Test | Purpose | Time (hr) | Totals | Time (hr)
1 |  | Integration | ACD Mechanical/Electrical Integration | Integrate the ACD to the grid
1a
1b | [5 empty] | Intg: | 0
2 |  | ACD Health | ACD Post-Installation Health Test | Check for post-install errors | 2
3 |  | Dataflow | AEM/ACD Clock Phase Bit Set Determination | Set Clock Phase Bit | 4
4 |  | Dataflow | AEM Tests | Check for TEM errors | 4
5 |  | Trigger | ACD Trigger Time-In | ACD TREQ & TACK Time-in | 8
6 |  | ACD CPT | ACD Full Functional | Post-install full ACD CPT | 8
7 |  | LAT LPT | LAT LPT (without ACD) | Post ACD install TKR/CAL Health | 4
8 |  | CALIB | ACD Threshold Calibration | Set ACD Thresholds | 8
9 |  | Trigger | ACD Trigger Tests | Trigger Efficiency & ROI Tests | 8
10 |  | LAT CPT | LAT CPT with ACD | Parallel test | 16
11 |  | SVAC | SVAC Testing with ACD
[6 empty] | TOTAL: | 62