## Schedule
| June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr
Refine Tracker and Cal tests
Document Trigger tests
Update SVAC and T&DF test cases
Release 2 tower plan
Verification Plan Review
DAQ box planning and qual test
Incorporate DAQ tests
Incorporate ACD tests
Incorporate FSW tests
Update SVAC and T&DF test cases
Define LAT/SC interface tests
Incorporate LAT verification plan review results
Incorporate Test bed lessons learned
Release final test plan
Tower Integration
DAQ and ACD integration
LAT System Test
Test bed
2 tower
power on and configuration using subsystem scripts
detector testing using subsystem scripts
tower interaction testing using subset of SVAC and ETE test lists
daq integration
Power on using FSW
Configuration using FSW
DAQ and tower interaction testing using larger subset of SVAC and ETE test lists
ACD integration
Complete power on using FSW
Complete configuration using FSW
Complete set of interaction testing
Complete set of calibration collection
Performance data collection

## Dates
Approach
Task completed by input date
Subcommittee reviews and adjusts as necessary for LAT level testing
Subcommittee results reviewed during Test Planning Meeting
Hascall incorporates results into test plan |  |  |  | Test Planning Meeting Dates
|  |  |  | 2004-06-28 | 2004-07-06 | 2004-07-12 | 2004-07-19 | 2004-07-26 | 2004-08-02 | 2004-08-09 | 2004-08-16 | 2004-08-23 | 2004-08-30 | 2004-09-06 | 2004-09-13 | 2004-09-20 | 2004-09-27 | 2004-10-04 | 2004-10-11 | 2004-10-18 | 2004-10-25
Task | Who | Input Date | Review or Release Date
Update Calorimeter test descriptions, CPT and LPT | Grove | 2004-07-15 | 2004-07-19 | bar: 2004-07-19
Update Tracker test descriptions, CPT and LPT | Tajima | 2004-07-08 | 2004-07-12 | bar: 2004-07-12
Add trigger tests | Hascall | 2004-07-01 | 2004-07-06 | bar: 2004-07-06
Complete End-to-end committee and SVAC test matrix for the two tower test | Eduardo | 2004-07-01 | 2004-07-06 | bar: 2004-07-06
Define interface tests (if any) | Hascall | 2004-07-08 | 2004-07-26 | bar: 2004-07-26
Update test matrix for testing through the two tower test | Hascall | 2004-07-19 | 2004-07-26 | bar: 2004-07-26
Release two tower test plan | Hascall |  | 2004-08-02 | bar: 2004-08-02
Provide GASU test descriptions | Haller designee | 2004-08-30 | 2004-09-06 | bar: 2004-09-06
Provide PDU test descriptions | Haller designee | 2004-08-30 | 2004-09-13 | bar: 2004-09-13
Provide EPU/SIU test descriptions | Haller designee | 2004-09-30 | 2004-10-04 | bar: 2004-10-04
Provide FSW test descriptions | DeKlotz | 2004-08-16 | 2004-09-27 | bar: 2004-09-27
Refine end-to-end committee definitions | Hascall | 2004-08-23 | 2004-08-23 | bar: 2004-08-23
Complete verification flowdown audit and add tests to complete verification | Bright | 2004-10-01 | 2004-11-01
Provide ACD test descriptions | Thompson | tbd
Coordinate T&DF startup tests vs FSW startup tests | DeKlotz | 2004-09-15 | 2004-09-20 | bar: 2004-09-20
Complete matrix of required data collection to include SVAC and end-to-end test committee requirements | Eduardo | 2004-09-27 | 2004-09-27 | bar: 2004-09-27
Add system interface test definition - coordinate with FSW and DAQ tests | Bielawski | 2004-10-15
Review test bed for lessons learned | Haller designee | tbd
Finalize test matrix | Hascall | 2004-11-15
Release final test plan | Hascall |  | 2004-01-01